## Financal report 3
Version control: 1.0 - Date: 29/04/2020
Financial Report III | Date: 29/04/2020 | SWEng Group 4
Author: | Codev Financial Manager | Louis Newman
Week number | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31
Week dates | Sep. 30, 2019-Oct. 6, 2019 | Oct. 7, 2019-Oct. 13, 2019 | Oct. 14, 2019-Oct. 20, 2019 | Oct. 21, 2019-Oct. 27, 2019 | Oct. 28, 2019-Nov. 3, 2019 | Nov. 4, 2019-Nov. 10, 2019 | Nov. 11, 2019-Nov. 17, 2019 | Nov. 18, 2019-Nov. 24, 2019 | Nov. 25, 2019-Dec. 1, 2019 | Dec. 2, 2019-Dec. 8, 2019 | Dec. 9, 2019-Dec. 15, 2019 | Dec. 16, 2019-Dec. 22, 2019 | Dec. 23, 2019-Dec. 29, 2019 | Dec. 30, 2019-Jan. 5, 2020 | Jan. 6, 2020-Jan. 12, 2020 | Jan. 13, 2020-Jan. 19, 2020 | Jan. 20, 2020-Jan. 26, 2020 | Jan. 27, 2020-Feb. 2, 2020 | Feb. 3, 2020-Feb. 9, 2020 | Feb. 10, 2020-Feb. 16, 2020 | Feb. 17, 2020-Feb. 23, 2020 | Feb. 24, 2020-Mar. 1, 2020 | Mar. 2, 2020-Mar. 8, 2020 | Mar. 9, 2020-Mar. 15, 2020 | Mar. 16, 2020-Mar. 22, 2020 | Mar. 23, 2020-Mar. 29, 2020 | Mar. 30, 2020-Apr. 5, 2020 | Apr. 6, 2020-Apr. 12, 2020 | Apr. 13, 2020-Apr. 19, 2020 | Apr. 20, 2020-Apr. 26, 2020 | Apr. 27, 2020-May 3, 2020
Term week | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | Christmas | Christmas | Christmas | Christmas | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | Easter | Easter | Easter | Easter | 1 | 2 | 3
Project Iteration Stage | Preparation | Preparation | Preparation | Preparation | Preparation | Preparation | Preparation | Preparation | Preparation | Preparation | Preparation | Preparation | Preparation | Preparation | Preparation | Preparation | Preparation | Preparation | Iteration 1, week 1 | Iteration 1, week 2 | Iteration 1, week 3 | Iteration 1, week 4 | Iteration 1, week 5 | Iteration 1, week 6 | Iteration 2, week 1 | Iteration 2, week 2 | Iteration 2, week 3 | Iteration 2, week 4 | Iteration 2, week 5 | Iteration 3, week 1 | Iteration 3, week 2
Predicted
Predicted Module sales (IN)
Predicted Module purchases (OUT) | [21 empty] | -100 |  | -300
Predicted weekly hours | 0 | 0 | 0 | 7 | 8.25 | 8.25 | 8.5 | 7.75 | 20.25 | 14 | 0 | 0 | 0 | 0 | 0 | 45.25 | 67.5 | 35 | 47.75 | 59 | 58.5 | 42.5 | 46 | 29.25 | 47.25 | 34.75 | 28.5 | 43.5 | 43.5 | 37.25 | 47.25
Predicted Closing Balance | 0 | 0 | 0 | -2618.2692 | -2721.3942 | -3724.5192 | -5728.8462 | -5825.7212 | -6078.8462 | -8751.9231 | -8751.9231 | -8751.9231 | -8751.9231 | -8751.9231 | -8751.9231 | -9317.5481 | -10161.2981 | -15660.3365 | -16257.2115 | 9656.8626 | 6935.9627 | 6213.1398 | 5546.5668 | 2291.2919 | 1609.0939 | 1083.1459 | 635.323 | -1.9327e-12 | 15645.9959 | 15035.8372 | 14300.6784
Actual
Actual hours | 0 | 0 | 0 | 7 | 8.25 | 8.25 | 8.5 | 7.75 | 20.25 | 14 | 0 | 0 | 0 | 0 | 0 | 45.25 | 67.5 | 35 | 40.5 | 70.25 | 32.5 | 56.25 | 46.75 | 40 | 38.25 | 73.25 | 48.25 | 23 | 44.25 | 27.5
IN
Loans (IN) | [19 empty] | 28243.1471 | [8 empty] | 16334.2796
Module sales (IN) | [21 empty] | 263.53 |  | 790.58
OUT
Premises Rent |  |  |  | -2530.7692 |  |  | -1898.0769 |  |  | -1898.0769 | [7 empty] | -5061.5385 |  |  | -1898.0769 |  |  | -1898.0769
Utilities Rent | [5 empty] | -300 |  |  |  | -200 | [9 empty] | -500 |  |  |  | -200
IT infrastructure | [5 empty] | -600 |  |  |  | -400 | [9 empty] | -1000 |  |  |  | -400
Cost of Labour (12.5 GBP per hour) | 0 | 0 | 0 | -87.5 | -103.125 | -103.125 | -106.25 | -96.875 | -253.125 | -175 | 0 | 0 | 0 | 0 | 0 | -565.625 | -843.75 | -437.5 | -506.25 | -878.125 | -406.25 | -703.125 | -584.375 | -500 | -478.125 | -915.625 | -603.125 | -287.5 | -553.125 | -343.75 | 0
Weekly interest (16.86% APR) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -91.573 | -91.573 | -91.573 | -91.573 | -91.573 | -91.573 | -91.573 | -91.573 | -91.573 | -144.5337 | -144.5337 | -144.5337
Module purchases (OUT) | [21 empty] | -115.33 |  | -345.99
Creditors
Total credit for loans | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28243.1471 | 28243.1471 | 28243.1471 | 28243.1471 | 28243.1471 | 28243.1471 | 28243.1471 | 28243.1471 | 28243.1471 | 44577.4268 | 44577.4268 | 44577.4268
Total credit recieved for modules | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 345.99 | 345.99 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total credit given for modules | [21 empty] | 790.58 | 790.58 | 0
Opening Balance | 0 | 0 | 0 | 0 | -2618.2692 | -2721.3942 | -3724.5192 | -5728.8462 | -5825.7212 | -6078.8462 | -8751.9231 | -8751.9231 | -8751.9231 | -8751.9231 | -8751.9231 | -8751.9231 | -9317.5481 | -10161.2981 | -15660.3365 | -16166.5865 | 9606.8626 | 7210.9627 | 6564.4648 | 5888.5168 | 3243.4569 | 2673.7589 | 1666.5609 | 971.863 | 592.79 | 16229.4109 | 15741.1272
OUT total | 0 | 0 | 0 | -2618.2692 | -103.125 | -1003.125 | -2004.3269 | -96.875 | -253.125 | -2673.0769 | 0 | 0 | 0 | 0 | 0 | -565.625 | -843.75 | -5499.0385 | -506.25 | -2469.698 | -2395.8999 | -910.028 | -675.948 | -3435.6399 | -569.698 | -1007.198 | -694.698 | -379.073 | -697.6587 | -488.2837 | -144.5337
IN total | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28243.1471 | 0 | 263.53 | 0 | 790.58 | 0 | 0 | 0 | 0 | 16334.2796 | 0 | 0
Closing Balance | 0 | 0 | 0 | -2618.2692 | -2721.3942 | -3724.5192 | -5728.8462 | -5825.7212 | -6078.8462 | -8751.9231 | -8751.9231 | -8751.9231 | -8751.9231 | -8751.9231 | -8751.9231 | -9317.5481 | -10161.2981 | -15660.3365 | -16166.5865 | 9606.8626 | 7210.9627 | 6564.4648 | 5888.5168 | 3243.4569 | 2673.7589 | 1666.5609 | 971.863 | 592.79 | 16229.4109 | 15741.1272 | 15596.5934
Difference to prediction | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 90.625 | -50 | 275 | 351.325 | 341.95 | 952.165 | 1064.665 | 583.415 | 336.54 | 592.79 | 583.415 | 705.29
Estimated time - Week 23
Role | Name | Software | Design | Testing | Meetings | Finance | Administration | Total
Project Manager | James Pearson |  |  |  | 1 |  | 2 | 3
Finance Manager | Louis Newman | 8 |  |  | 1 | 2 |  | 11
Design & Specification Manager | Joe Butler |  | 3.5 |  | 1 |  |  | 4.5
Lead Software Developer | James Clawley | 17 |  |  | 1 |  |  | 18
Testing & Integration Manager | Nathan Billis |  |  | 3.5 | 1 |  |  | 4.5
Marketing Manager | Becky Anderson | 3 |  |  | 1 |  |  | 4
XML & Server Manager | Jun Ma |  |  |  | 1 |  |  | 1
[7 empty] | Total: | 46
Reason for predicted hour distribution: | Hours assigned to team member taking lead on story to delegate as they see fit.
Actual timesheet - Week 23
Project | User | 03/02/2020 | 03/03/2020 | 03/04/2020 | 03/05/2020 | 03/06/2020 | 03/07/2020 | 03/08/2020 | Total | Billable total
Finance - SWEng Group 4 |  | 00:00:00 | 01:00:00 | 00:00:00 | 00:30:00 | 00:00:00 | 00:00:00 | 00:00:00 | 01:30:00 | 01:30:00
| Louis Newman | 00:00:00 | 01:00:00 | 00:00:00 | 00:30:00 | 00:00:00 | 00:00:00 | 00:00:00 | 01:30:00 | 01:30:00
Meetings - SWEng Group 4 |  | 03:30:00 | 01:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 04:30:00 | 04:30:00
| James Pearson | 00:30:00 | 00:30:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 01:00:00 | 01:00:00
| Louis Newman | 00:30:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:30:00 | 00:30:00
| Rebecca Anderson | 00:30:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:30:00 | 00:30:00
| Nathan Billis | 00:30:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:30:00 | 00:30:00
| Jun Ma | 00:30:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:30:00 | 00:30:00
| Joe Butler | 00:30:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:30:00 | 00:30:00
| James Clawley | 00:30:00 | 00:30:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 01:00:00 | 01:00:00
Software - SWEng Group 4 |  | 01:00:00 | 01:00:00 | 02:00:00 | 15:15:00 | 04:30:00 | 04:30:00 | 03:00:00 | 31:15:00 | 31:15:00
| Louis Newman | 01:00:00 | 00:00:00 | 00:00:00 | 03:30:00 | 00:00:00 | 03:00:00 | 02:00:00 | 09:30:00 | 09:30:00
| Rebecca Anderson | 00:00:00 | 00:00:00 | 00:00:00 | 02:45:00 | 00:00:00 | 01:00:00 | 00:00:00 | 03:45:00 | 03:45:00
| Nathan Billis | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:30:00 | 00:30:00 | 00:30:00
| Jun Ma | 00:00:00 | 00:00:00 | 02:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 02:00:00 | 02:00:00
| Joe Butler | 00:00:00 | 00:00:00 | 00:00:00 | 07:00:00 | 02:30:00 | 00:30:00 | 00:30:00 | 10:30:00 | 10:30:00
| James Clawley | 00:00:00 | 01:00:00 | 00:00:00 | 02:00:00 | 02:00:00 | 00:00:00 | 00:00:00 | 05:00:00 | 05:00:00
Testing - SWEng Group 4 |  | 00:00:00 | 00:00:00 | 00:00:00 | 00:15:00 | 00:00:00 | 00:00:00 | 00:30:00 | 00:45:00 | 00:45:00
| Nathan Billis | 00:00:00 | 00:00:00 | 00:00:00 | 00:15:00 | 00:00:00 | 00:00:00 | 00:30:00 | 00:45:00 | 00:45:00
Administration - SWEng Group 4 |  | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 01:30:00 | 00:00:00 | 00:15:00 | 01:45:00 | 01:45:00
| James Pearson | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:15:00 | 00:15:00 | 00:15:00
| James Clawley | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 01:30:00 | 00:00:00 | 00:00:00 | 01:30:00 | 01:30:00
User Stories - SWEng Group 4 |  | 00:00:00 | 00:30:00 | 00:00:00 | 02:00:00 | 00:00:00 | 01:30:00 | 00:00:00 | 04:00:00 | 04:00:00
| James Pearson | 00:00:00 | 00:30:00 | 00:00:00 | 02:00:00 | 00:00:00 | 01:30:00 | 00:00:00 | 04:00:00 | 04:00:00
Test and integration plan - SWEng Group 4 |  | 00:00:00 | 00:00:00 | 01:00:00 | 01:30:00 | 00:30:00 | 00:00:00 | 00:00:00 | 03:00:00 | 03:00:00
| Nathan Billis | 00:00:00 | 00:00:00 | 01:00:00 | 01:30:00 | 00:30:00 | 00:00:00 | 00:00:00 | 03:00:00 | 03:00:00
TOTAL |  | 04:30:00 | 03:30:00 | 03:00:00 | 19:30:00 | 06:30:00 | 06:00:00 | 03:45:00 | 46:45:00 | 46:45:00 | Difference to predicted: | -0.75
[9 empty] | Billable total: | 46.75
Notes on labour for week 23:
| Finance manager comment from weekly timesheet: | Over by 0.75 hours this week with an estimated hours of 46, we are ahead overall with 7.5 hours more than we have used. We are about where we should be with user stories with the meal planner pushed back to Iteration 2 but with us using the time we had allocated to these user stories we are mildly behind schedule in terms of hours used. No hours seem out of place in this weeks timesheet.
| Team lead comment from weekly timesheet: | N/A
Other comments for week 23: | N/A
Estimated time - Week 24
Role | Name | Software | Design | Testing | Meetings | Finance | Administration | Total
Project Manager | James Pearson | 4 |  |  | 1 |  | 2 | 7
Finance Manager | Louis Newman |  |  |  | 1 | 2 |  | 3
Design & Specification Manager | Joe Butler | 2 | 1.75 |  | 1 |  |  | 4.75
Lead Software Developer | James Clawley | 8 |  |  | 1 |  |  | 9
Testing & Integration Manager | Nathan Billis |  |  | 1.75 | 1 |  |  | 2.75
Marketing Manager | Becky Anderson |  |  |  | 1 |  |  | 1
XML & Server Manager | Jun Ma |  |  |  | 1 |  |  | 1
[7 empty] | Total: | 28.5
Reason for predicted hour distribution: | Hours assigned to team member taking lead on story to delegate as they see fit.
Actual timesheet - Week 24
Project | User | 03/09/2020 | 03/10/2020 | 03/11/2020 | 03/12/2020 | 03/13/2020 | 03/14/2020 | 03/15/2020 | Total | Billable total
Finance - SWEng Group 4 |  | 00:00:00 | 00:15:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:15:00 | 00:15:00
| Louis Newman | 00:00:00 | 00:15:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:15:00 | 00:15:00
Meetings - SWEng Group 4 |  | 03:15:00 | 00:00:00 | 00:30:00 | 00:00:00 | 01:00:00 | 00:00:00 | 00:00:00 | 04:45:00 | 04:45:00
| James Pearson | 00:30:00 | 00:00:00 | 00:30:00 | 00:00:00 | 00:15:00 | 00:00:00 | 00:00:00 | 01:15:00 | 01:15:00
| Louis Newman | 00:30:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:15:00 | 00:00:00 | 00:00:00 | 00:45:00 | 00:45:00
| Rebecca Anderson | 00:30:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:30:00 | 00:30:00
| Nathan Billis | 00:30:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:15:00 | 00:00:00 | 00:00:00 | 00:45:00 | 00:45:00
| Jun Ma | 00:30:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:30:00 | 00:30:00
| James Clawley | 00:45:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:15:00 | 00:00:00 | 00:00:00 | 01:00:00 | 01:00:00
Quality Manual - SWEng Group 4 |  | 00:00:00 | 00:00:00 | 00:15:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:15:00 | 00:15:00
| James Pearson | 00:00:00 | 00:00:00 | 00:15:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:15:00 | 00:15:00
Software - SWEng Group 4 |  | 02:45:00 | 03:15:00 | 00:00:00 | 04:00:00 | 02:30:00 | 00:00:00 | 00:00:00 | 12:30:00 | 12:30:00
| Louis Newman | 02:00:00 | 00:00:00 | 00:00:00 | 02:00:00 | 00:30:00 | 00:00:00 | 00:00:00 | 04:30:00 | 04:30:00
| Rebecca Anderson | 00:00:00 | 00:45:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:45:00 | 00:45:00
| Joe Butler | 00:45:00 | 01:30:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 02:15:00 | 02:15:00
| James Clawley | 00:00:00 | 01:00:00 | 00:00:00 | 02:00:00 | 02:00:00 | 00:00:00 | 00:00:00 | 05:00:00 | 05:00:00
Testing - SWEng Group 4 |  | 00:00:00 | 02:00:00 | 00:00:00 | 01:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 03:00:00 | 03:00:00
| Rebecca Anderson | 00:00:00 | 02:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 02:00:00 | 02:00:00
| Nathan Billis | 00:00:00 | 00:00:00 | 00:00:00 | 01:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 01:00:00 | 01:00:00
Marketing - SWEng Group 4 |  | 00:00:00 | 00:45:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:15:00 | 01:00:00 | 01:00:00
| Rebecca Anderson | 00:00:00 | 00:45:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:15:00 | 01:00:00 | 01:00:00
Administration - SWEng Group 4 |  | 00:15:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:15:00 | 00:15:00
| Rebecca Anderson | 00:15:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:15:00 | 00:15:00
Design - SWEng Group 4 |  | 00:00:00 | 00:00:00 | 00:00:00 | 01:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 01:00:00 | 01:00:00
| James Pearson | 00:00:00 | 00:00:00 | 00:00:00 | 01:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 01:00:00 | 01:00:00
Test and integration plan - SWEng Group 4 |  | 00:00:00 | 01:30:00 | 05:00:00 | 10:00:00 | 00:30:00 | 00:00:00 | 00:00:00 | 17:00:00 | 17:00:00
| James Pearson | 00:00:00 | 00:00:00 | 00:45:00 | 02:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 02:45:00 | 02:45:00
| Louis Newman | 00:00:00 | 00:00:00 | 01:00:00 | 02:30:00 | 00:00:00 | 00:00:00 | 00:00:00 | 03:30:00 | 03:30:00
| Rebecca Anderson | 00:00:00 | 00:00:00 | 00:45:00 | 01:30:00 | 00:00:00 | 00:00:00 | 00:00:00 | 02:15:00 | 02:15:00
| Nathan Billis | 00:00:00 | 01:30:00 | 01:00:00 | 01:00:00 | 00:30:00 | 00:00:00 | 00:00:00 | 04:00:00 | 04:00:00
| Jun Ma | 00:00:00 | 00:00:00 | 00:00:00 | 03:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 03:00:00 | 03:00:00
| Joe Butler | 00:00:00 | 00:00:00 | 01:30:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 01:30:00 | 01:30:00
TOTAL |  | 06:15:00 | 07:45:00 | 05:45:00 | 16:00:00 | 04:00:00 | 00:00:00 | 00:15:00 | 40:00:00 | 40:00:00
[9 empty] | Total billable | 40 | Difference to predicted: | -11.5
Notes on labour for week 24:
| Finance manager comment from weekly timesheet: | The team had predicted 29.25 hours for this week, finishing iteration 1. It was found however that a team oversight had lead to no time allocation for the Test and Iteration plan. We have had 25 % of user stories given to testing in general, but nothing had gone into the Test and Iteration plan. During this week, 17 hours has gone into the Test and Iteration plan, last week 3 hours went into it. When asked during the predition phase of the project, the test team had not brought up this deliverable and thus was missed. Due to this oversight we are over budget this week, taking from the balance of time the team have built up over Iteration 1, the team is now 3.25 hours over going into Iteration 2. Looking at the current financial situation of the group as a whole this week however, we can identify that, due to excellent sales of Modules, we have £952.17 more in the bank than predicted. This will enable to team to put in extra hours where necessary during this iteration to finish in a strong position, with all necessary features completed.
| Team lead comment from weekly timesheet: | As project leader I take full responsibility for the oversight that has led to extra hours needing to be worked for this week. My initial assumptions on what was required for the Testing and Integration plan were greatly underestimated when originally put forward to the group in our initial predictions. This then led to the needing of extra hours from other members of the development team. All in all, finances are healthy and having the financial buffer to cover for any problems that may arise going forward is a great asset.
Other comments for week 24: | Second instalment of module sales came into the accounts along with second installment of module purchases leaving the accounts, this aligned with agreed timetable in contracts and boosted teams financial position dramatically.
Estimated time - Week 25
Role | Name | Software | Design | Testing | Meetings | Finance | Administration | Total
Project Manager | James Pearson |  |  |  | 1 |  | 2 | 3
Finance Manager | Louis Newman | 29 |  |  | 1 | 2 |  | 32
Design & Specification Manager | Joe Butler |  | 3.625 |  | 1 |  |  | 4.625
Lead Software Developer | James Clawley |  |  |  | 1 |  |  | 1
Testing & Integration Manager | Nathan Billis |  |  | 3.625 | 1 |  |  | 4.625
Marketing Manager | Becky Anderson |  |  |  | 1 |  |  | 1
XML & Server Manager | Jun Ma |  |  |  | 1 |  |  | 1
[7 empty] | Total: | 47.25
Reason for predicted hour distribution: | Hours assigned to team member taking lead on story to delegate as they see fit.
Actual timesheet - Week 25
Project | User | 03/16/2020 | 03/17/2020 | 03/18/2020 | 03/19/2020 | 03/20/2020 | 03/21/2020 | 03/22/2020 | Total | Billable total
Finance - SWEng Group 4 |  | 00:30:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:30:00 | 00:30:00
| Louis Newman | 00:30:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:30:00 | 00:30:00
Software - SWEng Group 4 |  | 01:00:00 | 11:45:00 | 10:00:00 | 03:15:00 | 03:00:00 | 05:00:00 | 02:00:00 | 36:00:00 | 36:00:00
| James Pearson | 00:00:00 | 00:00:00 | 04:00:00 | 03:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 07:00:00 | 07:00:00
| Louis Newman | 00:00:00 | 05:00:00 | 04:00:00 | 00:15:00 | 00:00:00 | 00:00:00 | 00:00:00 | 09:15:00 | 09:15:00
| Rebecca Anderson | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 02:00:00 | 02:00:00 | 02:00:00
| Nathan Billis | 00:00:00 | 01:30:00 | 02:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 03:30:00 | 03:30:00
| Jun Ma | 01:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 01:00:00 | 01:00:00
| Joe Butler | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 03:00:00 | 05:00:00 | 00:00:00 | 08:00:00 | 08:00:00
| James Clawley | 00:00:00 | 05:15:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 05:15:00 | 05:15:00
Testing - SWEng Group 4 |  | 00:00:00 | 00:30:00 | 00:30:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:30:00 | 01:30:00 | 01:30:00
| Nathan Billis | 00:00:00 | 00:30:00 | 00:30:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:30:00 | 01:30:00 | 01:30:00
Administration - SWEng Group 4 |  | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:15:00 | 00:15:00 | 00:15:00
| James Pearson | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:15:00 | 00:15:00 | 00:15:00
TOTAL |  | 01:30:00 | 12:15:00 | 10:30:00 | 03:15:00 | 03:00:00 | 05:00:00 | 02:45:00 | 38:15:00 | 38:15:00
[9 empty] | Total billable | 38.25 | Difference to predicted: | 9
Notes on labour for week 25:
| Finance manager comment from weekly timesheet: | The team had predicted 47.25 hours for this week, starting Iteration 2. Taking our previous weeks balance into account, the team is now under our predicted hours by 5.75 hours. Compared with our total predicted location, the team has an extra £1,064.67 in the bank. Again this is mainly due to the team selling modules at an excellent price and this retains the buffer to enable extra labour hours as and where we require them in order to deliver the product envisioned in the tender presentation. Analysing the teams position with respect to the Financial Business Plan, we are behind in our expected position as we should be well under way with the social aspect of the application. However as the team has pushed the meal planner back to iteration 2, we are where we should be taking this into account. The strong financial position of the team should enable the team to catch up to our predicted position as members are able to put in the extra hours required to get to this position.
| Team lead comment from weekly timesheet: | Observations made by the Financial Manager are accurate and with big features like the meal planner and the social aspect being done now or coming up, The extra funds will cover any problems that arise in the coming development time.
Other comments for week 25: | N/A
Estimated time - Week 26
Role | Name | Software | Design | Testing | Meetings | Finance | Administration | Total
Project Manager | James Pearson |  |  |  | 1 |  | 2 | 3
Finance Manager | Louis Newman | 19 |  |  | 1 | 2 |  | 22
Design & Specification Manager | Joe Butler |  | 2.25 |  | 1 |  |  | 3.25
Lead Software Developer | James Clawley |  |  |  | 1 |  |  | 1
Testing & Integration Manager | Nathan Billis |  |  | 2.5 | 1 |  |  | 3.5
Marketing Manager | Becky Anderson |  |  |  | 1 |  |  | 1
XML & Server Manager | Jun Ma |  |  |  | 1 |  |  | 1
[7 empty] | Total: | 34.75
Reason for predicted hour distribution: | Hours assigned to team member taking lead on story to delegate as they see fit.
Actual timesheet - Week 26
Project | User | 03/23/2020 | 03/24/2020 | 03/25/2020 | 03/26/2020 | 03/27/2020 | 03/28/2020 | 03/29/2020 | Total | Total billable
Finance - SWEng Group 4 |  | 00:45:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:45:00 | 00:45:00
| Louis Newman | 00:45:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:45:00 | 00:45:00
Meetings - SWEng Group 4 |  | 02:00:00 | 05:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 07:00:00 | 07:00:00
| James Pearson | 00:00:00 | 01:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 01:00:00 | 01:00:00
| Louis Newman | 00:00:00 | 01:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 01:00:00 | 01:00:00
| Rebecca Anderson | 01:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 01:00:00 | 01:00:00
| Nathan Billis | 00:00:00 | 01:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 01:00:00 | 01:00:00
| Jun Ma | 00:00:00 | 01:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 01:00:00 | 01:00:00
| Joe Butler | 00:00:00 | 01:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 01:00:00 | 01:00:00
| James Clawley | 01:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 01:00:00 | 01:00:00
Software - SWEng Group 4 |  | 03:00:00 | 07:30:00 | 10:00:00 | 12:00:00 | 07:00:00 | 02:00:00 | 15:30:00 | 57:00:00 | 57:00:00
| James Pearson | 03:00:00 | 04:00:00 | 00:00:00 | 01:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 08:00:00 | 08:00:00
| Louis Newman | 00:00:00 | 01:30:00 | 03:00:00 | 03:00:00 | 02:00:00 | 00:00:00 | 07:30:00 | 17:00:00 | 17:00:00
| Rebecca Anderson | 00:00:00 | 00:00:00 | 01:00:00 | 00:00:00 | 00:00:00 | 02:00:00 | 03:00:00 | 06:00:00 | 06:00:00
| Nathan Billis | 00:00:00 | 00:00:00 | 01:00:00 | 00:00:00 | 02:00:00 | 00:00:00 | 00:00:00 | 03:00:00 | 03:00:00
| Jun Ma | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 01:00:00 | 01:00:00 | 01:00:00
| Joe Butler | 00:00:00 | 00:00:00 | 02:00:00 | 06:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 08:00:00 | 08:00:00
| James Clawley | 00:00:00 | 02:00:00 | 03:00:00 | 02:00:00 | 03:00:00 | 00:00:00 | 04:00:00 | 14:00:00 | 14:00:00
Testing - SWEng Group 4 |  | 00:00:00 | 00:00:00 | 03:00:00 | 02:30:00 | 00:00:00 | 00:00:00 | 00:00:00 | 05:30:00 | 05:30:00
| Nathan Billis | 00:00:00 | 00:00:00 | 02:00:00 | 02:30:00 | 00:00:00 | 00:00:00 | 00:00:00 | 04:30:00 | 04:30:00
| Jun Ma | 00:00:00 | 00:00:00 | 01:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 01:00:00 | 01:00:00
Administration - SWEng Group 4 |  | 00:30:00 | 00:00:00 | 00:15:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:15:00 | 01:00:00 | 01:00:00
| James Pearson | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:15:00 | 00:15:00 | 00:15:00
| Rebecca Anderson | 00:30:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:30:00 | 00:30:00
| Nathan Billis | 00:00:00 | 00:00:00 | 00:15:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:15:00 | 00:15:00
Design - SWEng Group 4 |  | 00:00:00 | 00:00:00 | 00:00:00 | 01:00:00 | 01:00:00 | 00:00:00 | 00:00:00 | 02:00:00 | 02:00:00
| Jun Ma | 00:00:00 | 00:00:00 | 00:00:00 | 01:00:00 | 01:00:00 | 00:00:00 | 00:00:00 | 02:00:00 | 02:00:00
TOTAL |  | 06:15:00 | 12:30:00 | 13:15:00 | 15:30:00 | 08:00:00 | 02:00:00 | 15:45:00 | 73:15:00 | 73:15:00
[9 empty] | Total billable | 73.25 | Difference to predicted: | -38.5
Notes on labour for week 26:
| Finance manager comment from weekly timesheet: | The team had predicted 34.75 hours for this week, week 2 of iteration 2. We have gone over on estimated hours in total of 32.75 for the entire project. At then end of last week, the team had an extra £1,064.67, this week we are still in the positive but from the extra work that has gone in this week we are at £583.42 extra in the pot, using up some of this redundancy. The reason for this this over time is due to the team attempting to catch up with our estimated plan location. Along with this our 30 minute meeting slot is being stretched as we now have to meet in a virtual domain, meeting are being elongated with this domain. The presentation is nearly all together and the meal planner has been completed. Along with this, the social stories planned for weeks 1 & 2, iteration 2, are nearly where they should be. Overall Corona-Virus is having an impact on the operation of the team, however we are nearly where we estimated we should be with user stories and financially. Having this extra money in the bank should enable to team to completely catch up with our previously estimated location before the end of iteration 2.
| Team lead comment from weekly timesheet: | COVID-19 impact - Pair programming is out the window, getting people to ask for help when needed is top priority and delegating that help to a member of the development team with the correct skills is imperative to make sure that there is no extra time wasted going round in circles looking for fix. Weekly meetings online aren't as streamlined as one would hope but they are doing a job keeping everyone in the loop as to what is going on. Bugs with the presentation and Louis working on the Social Aspect is taking a chunk of extra time but when these and the user created recipes is done, everything else should be relatively straight forward. Building on what we already have.
Other comments for week 26: | N/A
Estimated time - Week 26
Role | Name | Software | Design | Testing | Meetings | Finance | Administration | Total
Project Manager | James Pearson |  |  |  | 1 |  | 2 | 3
Finance Manager | Louis Newman |  |  |  | 1 | 2 |  | 3
Design & Specification Manager | Joe Butler |  | 1.75 |  | 1 |  |  | 2.75
Lead Software Developer | James Clawley |  |  |  | 1 |  |  | 1
Testing & Integration Manager | Nathan Billis | 14 |  | 1.75 | 1 |  |  | 16.75
Marketing Manager | Becky Anderson |  |  |  | 1 |  |  | 1
XML & Server Manager | Jun Ma |  |  |  | 1 |  |  | 1
[7 empty] | Total: | 28.5
Reason for predicted hour distribution: | Hours assigned to team member taking lead on story to delegate as they see fit.
Actual timesheet - Week 27
Project | User | 03/30/2020 | 03/31/2020 | 04/01/2020 | 04/02/2020 | 04/03/2020 | 04/04/2020 | 04/05/2020 | Total | Billable hours
Finance - SWEng Group 4 |  | 00:30:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:30:00 | 00:30:00
| Louis Newman | 00:30:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:30:00 | 00:30:00
Meetings - SWEng Group 4 |  | 04:15:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 04:15:00 | 04:15:00
| James Pearson | 00:30:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:30:00 | 00:30:00
| Louis Newman | 00:30:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:30:00 | 00:30:00
| Rebecca Anderson | 00:30:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:30:00 | 00:30:00
| Nathan Billis | 00:30:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:30:00 | 00:30:00
| Jun Ma | 00:45:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:45:00 | 00:45:00
| Joe Butler | 00:45:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:45:00 | 00:45:00
| James Clawley | 00:45:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:45:00 | 00:45:00
Software - SWEng Group 4 |  | 08:00:00 | 07:00:00 | 09:00:00 | 09:00:00 | 09:00:00 | 01:00:00 | 00:00:00 | 43:00:00 | 43:00:00
| James Pearson | 00:00:00 | 00:00:00 | 02:00:00 | 02:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 04:00:00 | 04:00:00
| Louis Newman | 00:00:00 | 02:00:00 | 02:00:00 | 01:00:00 | 01:00:00 | 01:00:00 | 00:00:00 | 07:00:00 | 07:00:00
| Rebecca Anderson | 00:00:00 | 02:00:00 | 00:00:00 | 01:00:00 | 02:00:00 | 00:00:00 | 00:00:00 | 05:00:00 | 05:00:00
| Nathan Billis | 00:00:00 | 00:00:00 | 01:00:00 | 02:00:00 | 04:00:00 | 00:00:00 | 00:00:00 | 07:00:00 | 07:00:00
| Jun Ma | 00:00:00 | 00:00:00 | 00:00:00 | 01:00:00 | 01:00:00 | 00:00:00 | 00:00:00 | 02:00:00 | 02:00:00
| Joe Butler | 08:00:00 | 00:00:00 | 01:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 09:00:00 | 09:00:00
| James Clawley | 00:00:00 | 03:00:00 | 03:00:00 | 02:00:00 | 01:00:00 | 00:00:00 | 00:00:00 | 09:00:00 | 09:00:00
Administration - SWEng Group 4 |  | 00:30:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:30:00 | 00:30:00
| Rebecca Anderson | 00:30:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:30:00 | 00:30:00
TOTAL |  | 13:15:00 | 07:00:00 | 09:00:00 | 09:00:00 | 09:00:00 | 01:00:00 | 00:00:00 | 48:15:00 | 48:15:00
[9 empty] | Total billable | 48.25 | Difference to predicted: | -19.75
Notes on labour for week 27:
| Finance manager comment from weekly timesheet: | The team had predicted 28.5 hours for this week, week 3 of iteration 2. We have gone over on estimated hours in total of 52.5 for the entire project. At then end of last week, the team had an extra £583.42, this week we are still in the positive but from the extra work that has gone in this week we are at £336.54 extra in the pot, using up some of this redundancy. The reason for this this over time is due to the team spending extra time on the most crutial parts of the application. These include adding recipes, building a strong searching capability and building the social feature that will work and promote repeat customers within our userbase. With these features holding the key selling points of the application it is crutial to get these correct, moreover as these key feature develop the team is uncovering new challenges and new solutions which will make the application not only functional but bring relish to these aspects. As a result of this, the team has gone over estimations for these stories, along with previous stories needing to be revisited to function with these stories. With active financial management I am allowing for this overtime with the spare capacity the team currently holds.
| Team lead comment from weekly timesheet: | N/A
Other comments for week 27: | N/A
Estimated time - Week 28
Role | Name | Software | Design | Testing | Meetings | Finance | Administration | Total | stories not assigned
Project Manager | James Pearson |  |  |  | 1 |  | 2 | 3 | C13 & C32
Finance Manager | Louis Newman |  |  |  | 1 | 2 |  | 3
Design & Specification Manager | Joe Butler |  | 1.25 |  | 1 |  |  | 2.25
Lead Software Developer | James Clawley |  |  |  | 1 |  |  | 1
Testing & Integration Manager | Nathan Billis | 10 |  | 1.25 | 1 |  |  | 12.25
Marketing Manager | Becky Anderson |  |  |  | 1 |  |  | 1
XML & Server Manager | Jun Ma |  |  |  | 1 |  |  | 1
[7 empty] | Total: | 23.5
Reason for predicted hour distribution: | Hours assigned to team member taking lead on story to delegate as they see fit. | [5 empty] | Not assigned | 20
Actual timesheet - Week 28
Project | User | 04/06/2020 | 04/07/2020 | 04/08/2020 | 04/09/2020 | 04/10/2020 | 04/11/2020 | 04/12/2020 | Total | Billable total
Finance - SWEng Group 4 |  | 00:15:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:15:00 | 00:15:00
| Louis Newman | 00:15:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:15:00 | 00:15:00
Meetings - SWEng Group 4 |  | 04:30:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 04:30:00 | 04:30:00
| James Pearson | 00:45:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:45:00 | 00:45:00
| Louis Newman | 00:45:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:45:00 | 00:45:00
| Rebecca Anderson | 00:45:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:45:00 | 00:45:00
| Nathan Billis | 00:45:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:45:00 | 00:45:00
| Jun Ma | 00:45:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:45:00 | 00:45:00
| James Clawley | 00:45:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:45:00 | 00:45:00
Quality Manual - SWEng Group 4 |  | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:15:00 | 00:00:00 | 00:15:00 | 00:15:00
| James Pearson | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:15:00 | 00:00:00 | 00:15:00 | 00:15:00
Software - SWEng Group 4 |  | 05:00:00 | 02:00:00 | 06:30:00 | 02:00:00 | 00:30:00 | 00:00:00 | 00:00:00 | 16:00:00 | 16:00:00
| James Pearson | 00:00:00 | 00:00:00 | 01:00:00 | 02:00:00 | 00:30:00 | 00:00:00 | 00:00:00 | 03:30:00 | 03:30:00
| Louis Newman | 00:00:00 | 02:00:00 | 02:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 04:00:00 | 04:00:00
| Jun Ma | 01:00:00 | 00:00:00 | 01:45:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 02:45:00 | 02:45:00
| Joe Butler | 00:00:00 | 00:00:00 | 01:45:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 01:45:00 | 01:45:00
| James Clawley | 04:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 04:00:00 | 04:00:00
Marketing - SWEng Group 4 |  | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 02:00:00 | 00:00:00 | 00:00:00 | 02:00:00 | 02:00:00
| Rebecca Anderson | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 02:00:00 | 00:00:00 | 00:00:00 | 02:00:00 | 02:00:00
TOTAL |  | 09:45:00 | 02:00:00 | 06:30:00 | 02:00:00 | 02:30:00 | 00:15:00 | 00:00:00 | 23:00:00 | 23:00:00
[9 empty] | Total billable | 23 | Difference to predicted: | 0.5
Notes on labour for week 28: | Alterations from this prediction: | Two stories not picked up and assosiated time altered in change log.
| Finance manager comment from weekly timesheet: | The team had predicted 43.5 hours for this week, week 4 of iteration 2. We have gone under this week by 20.5 hours but in total is over on estimated hours by 32 for the entire project. At then end of last week, the team had an extra £336.54, this week we are still in the positive but from the extra work that has gone in this week we are at £592.79 extra in the pot, adding to our redundancy. The reason the team has gone under this week is due to the entire team effort being direrted to another module assignment brought about by Covid-19. This was unexpected and unforeseen in our estimations. However the team now has this redundancy in hours, where stories not completed this week must be pushed and made up in either the last week of this Iteration or the first weeks of Iteration 3. Some progress has been made this week but nothing substantial. The team has the hours available to catch up to where is should be but story estimates are going over in several areas. Specifics on this will be left to the team lead.
| Team lead comment from weekly timesheet: | Currently we are behind in our estimations on where we should be in the development of the application. The decision has been made to move the Healthy Living feature to the bottom of the plan as our idea of what the application is has changed since first conception. The change log has been updated to reflect these changes. Due to this, more hours from the second iteration should be available to put in to catching up. More pressure will need to be applied in areas to try and speed up development while not impacting the quality of the application and the ability for members of the team to focus in other areas of study. With some of the best developers tied up in big features, moving resources around to try and move things along will be tricky.
Other comments for week 28: | N/A
Estimated time - Week 29
Role | Name | Software | Design | Testing | Meetings | Finance | Administration | Total | stories not assigned
Project Manager | James Pearson |  |  |  | 1 |  | 2 | 3 | A13
Finance Manager | Louis Newman |  |  |  | 1 | 2 |  | 3
Design & Specification Manager | Joe Butler |  | 1.75 |  | 1 |  |  | 2.75
Lead Software Developer | James Clawley | 14 |  |  | 1 |  |  | 15
Testing & Integration Manager | Nathan Billis |  |  | 1.75 | 1 |  |  | 2.75
Marketing Manager | Becky Anderson |  |  |  | 1 |  |  | 1
XML & Server Manager | Jun Ma |  |  |  | 1 |  |  | 1
[7 empty] | Total: | 28.5
Reason for predicted hour distribution: | Hours assigned to team member taking lead on story to delegate as they see fit. | [5 empty] | Not assigned | 15
Actual timesheet - Week 29
Project | User | 04/13/2020 | 04/14/2020 | 04/15/2020 | 04/16/2020 | 04/17/2020 | 04/18/2020 | 04/19/2020 | Total | Billable total
Finance - SWEng Group 4 |  | 00:00:00 | 00:00:00 | 00:15:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:15:00 | 00:15:00
| Louis Newman | 00:00:00 | 00:00:00 | 00:15:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:15:00 | 00:15:00
Meetings - SWEng Group 4 |  | 03:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 03:00:00 | 03:00:00
| James Pearson | 00:30:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:30:00 | 00:30:00
| Louis Newman | 00:30:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:30:00 | 00:30:00
| Rebecca Anderson | 00:30:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:30:00 | 00:30:00
| Nathan Billis | 00:30:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:30:00 | 00:30:00
| Joe Butler | 00:30:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:30:00 | 00:30:00
| James Clawley | 00:30:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:30:00 | 00:30:00
Quality Manual - SWEng Group 4 |  | 00:30:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:30:00 | 00:30:00
| Rebecca Anderson | 00:15:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:15:00 | 00:15:00
| Nathan Billis | 00:15:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:15:00 | 00:15:00
Software - SWEng Group 4 |  | 00:00:00 | 03:00:00 | 00:30:14 | 02:00:00 | 03:00:00 | 05:00:00 | 18:30:00 | 32:00:14 | 32:00:14
| James Pearson | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 03:00:00 | 02:00:00 | 05:00:00 | 05:00:00
| Louis Newman | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 10:00:00 | 10:00:00 | 10:00:00
| Rebecca Anderson | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 01:30:00 | 01:30:00 | 01:30:00
| Nathan Billis | 00:00:00 | 00:00:00 | 00:00:00 | 02:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 02:00:00 | 02:00:00
| Joe Butler | 00:00:00 | 03:00:00 | 00:30:14 | 00:00:00 | 03:00:00 | 00:00:00 | 01:00:00 | 07:30:14 | 07:30:14
| James Clawley | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 02:00:00 | 04:00:00 | 06:00:00 | 06:00:00
Testing - SWEng Group 4 |  | 00:00:00 | 00:00:00 | 00:30:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:30:00 | 00:30:00
| Nathan Billis | 00:00:00 | 00:00:00 | 00:30:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:30:00 | 00:30:00
Marketing - SWEng Group 4 |  | 00:00:00 | 03:00:00 | 00:00:00 | 01:45:00 | 00:00:00 | 01:00:00 | 00:00:00 | 05:45:00 | 05:45:00
| Rebecca Anderson | 00:00:00 | 03:00:00 | 00:00:00 | 01:45:00 | 00:00:00 | 01:00:00 | 00:00:00 | 05:45:00 | 05:45:00
Administration - SWEng Group 4 |  | 00:15:00 | 00:00:00 | 00:00:00 | 00:15:00 | 00:00:00 | 00:30:00 | 00:15:00 | 01:15:00 | 01:15:00
| James Pearson | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:30:00 | 00:15:00 | 00:45:00 | 00:45:00
| Rebecca Anderson | 00:15:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:15:00 | 00:15:00
| Nathan Billis | 00:00:00 | 00:00:00 | 00:00:00 | 00:15:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:15:00 | 00:15:00
Design - SWEng Group 4 |  | 00:00:00 | 01:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 01:00:00 | 01:00:00
| Joe Butler | 00:00:00 | 01:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 01:00:00 | 01:00:00
TOTAL |  | 03:45:00 | 07:00:00 | 01:15:14 | 04:00:00 | 03:00:00 | 06:30:00 | 18:45:00 | 44:15:14 | 44:15:14
[9 empty] | Total billable | 44.25 | Difference to predicted: | -15.75
Notes on labour for week 29: | Alterations from this prediction: | One story not picked up and assosiated time altered in change log.
| Finance manager comment from weekly timesheet: | The team had predicted 43.5 hours for this week, week 5 of iteration 2. We have gone over on estimated hours in total of 32.75 for the entire project. We have only gone over on hours by 0.75 so have used up a very small amount of the company redundancy and so still have £583.41 extra in the pot. The company remains in a comfortable place financially. Timings have been close to expected with regards to the financial business plan, some stories have gone over so story progress is not entirely accurate. This time over in stories is mainly due to ensuring the product retains the quality envisioned. The financial redundancy should get the team through to completion however some stores have been dropped and recorded in the change log, however the team lead will elaborate on this aspect.
| Team lead comment from weekly timesheet: | Financially the company is on track but overall we are behind on feature development. Some features have had to be cut or pushed back depending on their overall importance to the companies vision of the application. The change log is updated with all these plan alterations. Overall the company is in a healthy position and if we stay on track with the revised plan we will hit our targets for an application that has unique features to bring value to the customers.
Other comments for week 29: | N/A
Estimated time - Week 30
Role | Name | Software | Design | Testing | Meetings | Finance | Administration | Total | stories not assigned
Project Manager | James Pearson | 12 |  |  | 1 |  | 2 | 15 | C10
Finance Manager | Louis Newman | 6 |  |  | 1 | 2 |  | 9
Design & Specification Manager | Joe Butler |  | 2.25 |  | 1 |  |  | 3.25
Lead Software Developer | James Clawley |  |  |  | 1 |  |  | 1
Testing & Integration Manager | Nathan Billis |  |  | 2.25 | 1 |  |  | 3.25
Marketing Manager | Becky Anderson |  |  |  | 1 |  |  | 1
XML & Server Manager | Jun Ma |  |  |  | 1 |  |  | 1
[7 empty] | Total: | 33.5
Reason for predicted hour distribution: | Hours assigned to team member taking lead on story to delegate as they see fit. | [5 empty] | Not assigned | 3.75
Actual timesheet - Week 30
Project | User | 04/20/2020 | 04/21/2020 | 04/22/2020 | 04/23/2020 | 04/24/2020 | 04/25/2020 | 04/26/2020 | Total | Billable total
Finance - SWEng Group 4 |  | 00:00:00 | 00:00:00 | 00:15:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:15:00 | 00:15:00
| Louis Newman | 00:00:00 | 00:00:00 | 00:15:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:15:00 | 00:15:00
Meetings - SWEng Group 4 |  | 03:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 03:00:00 | 03:00:00
| James Pearson | 00:30:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:30:00 | 00:30:00
| Louis Newman | 00:30:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:30:00 | 00:30:00
| Rebecca Anderson | 00:30:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:30:00 | 00:30:00
| Nathan Billis | 00:30:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:30:00 | 00:30:00
| Joe Butler | 00:30:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:30:00 | 00:30:00
| James Clawley | 00:30:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:30:00 | 00:30:00
Software - SWEng Group 4 |  | 02:00:00 | 02:00:00 | 02:00:00 | 05:00:00 | 05:00:00 | 03:30:00 | 03:00:00 | 22:30:00 | 22:30:00
| James Pearson | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 02:00:00 | 02:30:00 | 00:00:00 | 04:30:00 | 04:30:00
| Louis Newman | 00:00:00 | 00:00:00 | 00:00:00 | 03:00:00 | 00:00:00 | 00:00:00 | 03:00:00 | 06:00:00 | 06:00:00
| Rebecca Anderson | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 03:00:00 | 01:00:00 | 00:00:00 | 04:00:00 | 04:00:00
| Jun Ma | 00:00:00 | 02:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 02:00:00 | 02:00:00
| James Clawley | 02:00:00 | 00:00:00 | 02:00:00 | 02:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 06:00:00 | 06:00:00
Testing - SWEng Group 4 |  | 00:15:00 | 00:00:00 | 00:00:00 | 00:30:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:45:00 | 00:45:00
| Nathan Billis | 00:15:00 | 00:00:00 | 00:00:00 | 00:30:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:45:00 | 00:45:00
Administration - SWEng Group 4 |  | 00:30:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:30:00 | 00:30:00
| Rebecca Anderson | 00:30:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:30:00 | 00:30:00
HTML Tour - SWEng Group 4 |  | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:30:00 | 00:00:00 | 00:00:00 | 00:30:00 | 00:30:00
| Nathan Billis | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:30:00 | 00:00:00 | 00:00:00 | 00:30:00 | 00:30:00
TOTAL |  | 05:45:00 | 02:00:00 | 02:15:00 | 05:30:00 | 05:30:00 | 03:30:00 | 03:00:00 | 27:30:00 | 27:30:00
[9 empty] | Total billable | 27.5 | Difference to predicted: | 6
Notes on labour for week 30: | Alterations from this prediction: | One story not picked up and assosiated time altered in change log.
| Finance manager comment from weekly timesheet: | The team had predicted 37.25 hours for this week, week 1 of iteration 3. We have gone over on estimated hours in total of 23 hours for the entire project. This week alone we have gone under by 9.75 hours so have added to the company redundancy and so now have £705.41 extra in the pot. The company remains in a comfortable place financially. With the team having exams and assignment due dates coming up, some are focusing on these which has lead to the miscalculation is user time this week. We have not missed this mark by too much as a lot of the other members are still on task. As the team enters iteration 3, the application is all starting to come together nicely. Final usability is being added and in reference to the financial business plan, taking the change log into account, the team is on track to finish on time and in a comfortable financial position.
| Team lead comment from weekly timesheet: | With the reshuffling of the plan to focus on the more important aspects of the application, more hours can be assigned to the main features to flesh them out and make sure a quality product will be delivered in the coming weeks. Progress is coming along well on our main features. Overall, progress is good. Two members of the development team have been paired up on a problem to get that rectified this coming week which will put us in a good position coming towards the end of the project.
Other comments for week 30: | N/A
Financial updates from reporting period: | During this reporting period there have been a number of financial changes that are either a direct consequence of COVID-19 or due to development of the application requiring specific features. These features are required in order to bring increased capabilities to the application with the aim to increase user retention and usability.
Marteking update: | In light of COVID-19, our marketing strategy has to change. Getting rid of all face to face advertising. This however is not a bad thing, our marketing surveys tell us that 89% of people find out about a new app online. Focusing on this will reduce our overall marketing cost.
Author: Marketing Manager |  |  |  | Type of marketing | Price
|  |  |  | Social media ads & People working | 1500
|  |  |  | Influencers pay | 800
|  |  |  | Total | 2300
These figures come from 8 influencers with 10,000 mainly on Instagram and Facebook and the social media ads and people working covers the wage of someone who is in charge of the social media sites and the paid ads on different platforms I will need a total of 15 hours for the 3rd iteration to complete what is set out in the marketing plan
In-app search capability update: | Algolia Searching Finance Details
Author: Testing Manager | Pricing | Records | Operations | Additional Usage
| $29/mo | 50K | 250K | 100k operations: $10/month
20k records: $10/month
| $499/mo | 1M | 5M | 100k operations: $5/month
20k records: $5/month
https://www.algolia.com/pricing/
Benefits:
Search analytics
Abilities to roll out search updates without having to change the codebase
Used by industry leaders
99.999% uptime
We retain owners of our data at all times
Searching scales as the company scales
Our Analytics from the past 30 days (16/4/20)
Comments on update:
Initially Algolia will cost $29/month, once we reach 250k operations and 50k records. For every 100k operations over that it will cost $10/mo additional and for every 20k records it will also add $10/mo.
Team lead comments from reporting period: | Heading into iteration 3, changes have been made to the plan to increase the focus on the more important features of the application. The company’s vision of a cooking application with a social media aspect has taken priority over the healthy living system feature that was to implement calorie tracking and healthy diet options. These changes are reflected in the company’s change log with some user stories being removed from the plan completely or pushed to the end with the aim to implement if time allows. Hours for the stories moved off plan have been redistributed to newer stories that focus on the social media side of the app. This is with the aim of fully fleshing out our niche market feature and making sure that quality is delivered to the customer. Progress on the plan is going ok with some great strides being made. Some issues arose that slowed some progression but overall the company is in a healthy position and should deliver a quality application on time.
Final comments from Finance Manager: | The company remains in a strong and stable financial position. Where not all time estimations were correct and stories have over run in several places. Active financial management and strong negotiation during module sales has allowed the team to be slightly more flexible with the key stories to attain the quality level desired by the project. While there have been these under estimations in time and some over estimations in programmer capabilities, the majority of stories have aligned with predictions and the team is on course to complete all key stories for main application and USP with minor alterations within the change log. Even with the alterations brought on with COVID-19, the team is financially on track for a successful project.