## Financal Summary
Version control: 1.0 - Date: 22/05/2020
Financial Summary | Date: 22/05/2020 | SWEng Group 4
Author: | Codev Financial Manager | Louis Newman
Week number | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38
Week dates | Sep. 30, 2019-Oct. 6, 2019 | Oct. 7, 2019-Oct. 13, 2019 | Oct. 14, 2019-Oct. 20, 2019 | Oct. 21, 2019-Oct. 27, 2019 | Oct. 28, 2019-Nov. 3, 2019 | Nov. 4, 2019-Nov. 10, 2019 | Nov. 11, 2019-Nov. 17, 2019 | Nov. 18, 2019-Nov. 24, 2019 | Nov. 25, 2019-Dec. 1, 2019 | Dec. 2, 2019-Dec. 8, 2019 | Dec. 9, 2019-Dec. 15, 2019 | Dec. 16, 2019-Dec. 22, 2019 | Dec. 23, 2019-Dec. 29, 2019 | Dec. 30, 2019-Jan. 5, 2020 | Jan. 6, 2020-Jan. 12, 2020 | Jan. 13, 2020-Jan. 19, 2020 | Jan. 20, 2020-Jan. 26, 2020 | Jan. 27, 2020-Feb. 2, 2020 | Feb. 3, 2020-Feb. 9, 2020 | Feb. 10, 2020-Feb. 16, 2020 | Feb. 17, 2020-Feb. 23, 2020 | Feb. 24, 2020-Mar. 1, 2020 | Mar. 2, 2020-Mar. 8, 2020 | Mar. 9, 2020-Mar. 15, 2020 | Mar. 16, 2020-Mar. 22, 2020 | Mar. 23, 2020-Mar. 29, 2020 | Mar. 30, 2020-Apr. 5, 2020 | Apr. 6, 2020-Apr. 12, 2020 | Apr. 13, 2020-Apr. 19, 2020 | Apr. 20, 2020-Apr. 26, 2020 | Apr. 27, 2020-May 3, 2020 | May 4, 2020-May 10, 2020 | May 11, 2020-May 17, 2020 | May 18, 2020-May 24, 2020 | May 25, 2020-May 31, 2020 | June 1, 2020-June 7, 2020 | June 8, 2020-June 14, 2020 | June 15, 2020-June 21, 2020
Term week | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | Christmas | Christmas | Christmas | Christmas | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | Easter | Easter | Easter | Easter | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10
Project Iteration Stage | Preparation | Preparation | Preparation | Preparation | Preparation | Preparation | Preparation | Preparation | Preparation | Preparation | Preparation | Preparation | Preparation | Preparation | Preparation | Preparation | Preparation | Preparation | Iteration 1, week 1 | Iteration 1, week 2 | Iteration 1, week 3 | Iteration 1, week 4 | Iteration 1, week 5 | Iteration 1, week 6 | Iteration 2, week 1 | Iteration 2, week 2 | Iteration 2, week 3 | Iteration 2, week 4 | Iteration 2, week 5 | Iteration 3, week 1 | Iteration 3, week 2 | Iteration 3, week 3 | Iteration 3, week 4 | Iteration 3, week 5 | Presentation preparation | Presentation & hand in
Predicted
Predicted Module sales (IN)
Predicted Module purchases (OUT) | [21 empty] | -100 |  | -300
Predicted weekly hours | 0 | 0 | 0 | 7 | 8.25 | 8.25 | 8.5 | 7.75 | 20.25 | 14 | 0 | 0 | 0 | 0 | 0 | 45.25 | 67.5 | 35 | 47.75 | 59 | 58.5 | 42.5 | 46 | 29.25 | 47.25 | 34.75 | 28.5 | 43.5 | 43.5 | 37.25 | 47.25 | 29.75 | 31 | 43.5 | 75.25 | 7 | 0 | 0
Closing Balance | 0 | 0 | 0 | -2618.2692 | -2721.3942 | -3724.5192 | -5728.8462 | -5825.7212 | -6078.8462 | -8751.9231 | -8751.9231 | -8751.9231 | -8751.9231 | -8751.9231 | -8751.9231 | -9317.5481 | -10161.2981 | -15660.3365 | -16257.2115 | 9656.8626 | 6935.9627 | 6213.1398 | 5546.5668 | 2291.2919 | 1609.0939 | 1083.1459 | 635.323 | -1.9327e-12 | 15645.9959 | 15035.8372 | 14300.6784 | 14300.6784 | 8722.7312 | 8190.6975 | 6002.4138 | 3019.1781 | 2787.1444 | 2642.6107
Actual
Actual hours | 0 | 0 | 0 | 7 | 8.25 | 8.25 | 8.5 | 7.75 | 20.25 | 14 | 0 | 0 | 0 | 0 | 0 | 45.25 | 67.5 | 35 | 40.5 | 70.25 | 32.5 | 56.25 | 46.75 | 40 | 38.25 | 73.25 | 48.25 | 23 | 44.25 | 27.5 | 32.25 | 23.25 | 50.75
IN
Loans (IN) | [19 empty] | 28243.1471 | [8 empty] | 16334.2796
Module sales (IN) | [21 empty] | 263.53 |  | 790.58
OUT
Premises Rent |  |  |  | -2530.7692 |  |  | -1898.0769 |  |  | -1898.0769 | [7 empty] | -5061.5385 |  |  | -1898.0769 |  |  | -1898.0769 | [7 empty] | -5061.5385 |  |  | -1898.0769 |  |  | -1898.0769
Utilities Rent | [5 empty] | -300 |  |  |  | -200 | [9 empty] | -500 |  |  |  | -200 | [9 empty] | -500 |  |  |  | -200
IT infrastructure | [5 empty] | -600 |  |  |  | -400 | [9 empty] | -1000 |  |  |  | -400 | [9 empty] | -1000 |  |  |  | -400
Cost of Labour (12.5 GBP per hour) | 0 | 0 | 0 | -87.5 | -103.125 | -103.125 | -106.25 | -96.875 | -253.125 | -175 | 0 | 0 | 0 | 0 | 0 | -565.625 | -843.75 | -437.5 | -506.25 | -878.125 | -406.25 | -703.125 | -584.375 | -500 | -478.125 | -915.625 | -603.125 | -287.5 | -553.125 | -343.75 | -403.125 | -290.625 | -634.375 | 0 | 0 | 0 | 0 | 0
Weekly interest (16.86% APR) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -91.573 | -91.573 | -91.573 | -91.573 | -91.573 | -91.573 | -91.573 | -91.573 | -91.573 | -144.5337 | -144.5337 | -144.5337 | -144.5337 | -144.5337 | -144.5337 | -144.5337 | -144.5337 | -144.5337 | -144.5337
Module purchases (OUT) | [21 empty] | -115.33 |  | -345.99
Creditors
Total credit for loans | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28243.1471 | 28243.1471 | 28243.1471 | 28243.1471 | 28243.1471 | 28243.1471 | 28243.1471 | 28243.1471 | 28243.1471 | 44577.4268 | 44577.4268 | 44577.4268 | 44577.4268 | 44577.4268 | 44577.4268 | 44577.4268 | 44577.4268 | 44577.4268 | 44577.4268
Total credit recieved for modules | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 345.99 | 345.99 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total credit given for modules | [21 empty] | 790.58 | 790.58 | 0
Opening Balance | 0 | 0 | 0 | 0 | -2618.2692 | -2721.3942 | -3724.5192 | -5728.8462 | -5825.7212 | -6078.8462 | -8751.9231 | -8751.9231 | -8751.9231 | -8751.9231 | -8751.9231 | -8751.9231 | -9317.5481 | -10161.2981 | -15660.3365 | -16166.5865 | 9606.8626 | 7210.9627 | 6564.4648 | 5888.5168 | 3243.4569 | 2673.7589 | 1666.5609 | 971.863 | 592.79 | 16229.4109 | 15741.1272 | 15193.4684 | 9696.7712 | 8917.8625 | 7273.3288 | 5230.7181 | 5086.1844 | 4941.6507
OUT total | 0 | 0 | 0 | -2618.2692 | -103.125 | -1003.125 | -2004.3269 | -96.875 | -253.125 | -2673.0769 | 0 | 0 | 0 | 0 | 0 | -565.625 | -843.75 | -5499.0385 | -506.25 | -2469.698 | -2395.8999 | -910.028 | -675.948 | -3435.6399 | -569.698 | -1007.198 | -694.698 | -379.073 | -697.6587 | -488.2837 | -547.6587 | -5496.6972 | -778.9087 | -1644.5337 | -2042.6107 | -144.5337 | -144.5337 | -2642.6107
IN total | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28243.1471 | 0 | 263.53 | 0 | 790.58 | 0 | 0 | 0 | 0 | 16334.2796 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Closing Balance | 0 | 0 | 0 | -2618.2692 | -2721.3942 | -3724.5192 | -5728.8462 | -5825.7212 | -6078.8462 | -8751.9231 | -8751.9231 | -8751.9231 | -8751.9231 | -8751.9231 | -8751.9231 | -9317.5481 | -10161.2981 | -15660.3365 | -16166.5865 | 9606.8626 | 7210.9627 | 6564.4648 | 5888.5168 | 3243.4569 | 2673.7589 | 1666.5609 | 971.863 | 592.79 | 16229.4109 | 15741.1272 | 15193.4684 | 9696.7712 | 8917.8625 | 7273.3288 | 5230.7181 | 5086.1844 | 4941.6507 | 2299.04
Difference to prediction | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 90.625 | -50 | 275 | 351.325 | 341.95 | 952.165 | 1064.665 | 583.415 | 336.54 | 592.79 | 583.415 | 705.29 | 892.79 | 974.04 | 727.165 | 1270.915 | 2211.54 | 2299.04 | 2299.04 | 2299.04
Financial Reporting week 31-33
Estimated time - Week 31
Role | Name | Software | Design | Testing | Meetings | Finance | Administration | Total
Project Manager | James Pearson | 6 |  |  | 1 |  | 2 | 9 | Stories not taken | Type | Hours | [23 empty] | -632.6923
Finance Manager | Louis Newman |  |  |  | 1 | 2 |  | 3 | C25 | reccomended recipes | 10 | [21 empty] | rent 1 week
Design & Specification Manager | Joe Butler |  | 1.625 |  | 1 |  |  | 2.625 | C30 | recipe questions | 6 | [21 empty] | 450 util
Lead Software Developer | James Clawley |  |  |  | 1 |  |  | 1 | total not used: | (with design & testing) | 20 | [21 empty] | 900 IT
Testing & Integration Manager | Nathan Billis |  |  | 1.625 | 1 |  |  | 2.625
Marketing Manager | Becky Anderson | 7 |  |  | 1 |  |  | 8
XML & Server Manager | Jun Ma |  |  |  | 1 |  |  | 1 | [24 empty] | 632.6923
[7 empty] | Total: | 27.25 | [24 empty] | 450
Reason for predicted hour distribution: | Hours assigned to team member taking lead on story to delegate as they see fit. | [31 empty] | 900
1982.6923
Actual timesheet - Week 31
Project | User | 04/27/2020 | 04/28/2020 | 04/29/2020 | 04/30/2020 | 05/01/2020 | 05/02/2020 | 05/03/2020 | Total | Total billable
Finance - SWEng Group 4 |  | 00:00:00 | 00:00:00 | 02:45:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 02:45:00 | 02:45:00
| Louis Newman | 00:00:00 | 00:00:00 | 02:45:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 02:45:00 | 02:45:00
Meetings - SWEng Group 4 |  | 03:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 03:00:00 | 03:00:00
| James Pearson | 00:30:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:30:00 | 00:30:00
| Louis Newman | 00:30:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:30:00 | 00:30:00
| Rebecca Anderson | 00:30:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:30:00 | 00:30:00
| Nathan Billis | 00:30:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:30:00 | 00:30:00
| Jun Ma | 00:30:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:30:00 | 00:30:00
| James Clawley | 00:30:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:30:00 | 00:30:00
Software - SWEng Group 4 |  | 01:30:00 | 06:00:00 | 00:00:00 | 01:30:00 | 03:00:00 | 05:00:00 | 00:00:00 | 17:00:00 | 17:00:00
| James Pearson | 00:00:00 | 03:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 03:00:00 | 03:00:00
| Louis Newman | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 05:00:00 | 00:00:00 | 05:00:00 | 05:00:00
| Rebecca Anderson | 00:00:00 | 03:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 03:00:00 | 03:00:00
| Joe Butler | 01:30:00 | 00:00:00 | 00:00:00 | 01:30:00 | 03:00:00 | 00:00:00 | 00:00:00 | 06:00:00 | 06:00:00
Testing - SWEng Group 4 |  | 02:00:00 | 00:00:00 | 01:30:00 | 01:15:00 | 00:00:00 | 00:00:00 | 00:00:00 | 04:45:00 | 04:45:00
| Nathan Billis | 02:00:00 | 00:00:00 | 01:30:00 | 01:15:00 | 00:00:00 | 00:00:00 | 00:00:00 | 04:45:00 | 04:45:00
Administration - SWEng Group 4 |  | 00:45:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:15:00 | 01:00:00 | 01:00:00
| James Pearson | 00:15:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:15:00 | 00:30:00 | 00:30:00
| Rebecca Anderson | 00:30:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:30:00 | 00:30:00
Design - SWEng Group 4 |  | 00:00:00 | 00:00:00 | 00:00:00 | 02:30:00 | 00:00:00 | 00:00:00 | 00:00:00 | 02:30:00 | 02:30:00
| James Pearson | 00:00:00 | 00:00:00 | 00:00:00 | 02:30:00 | 00:00:00 | 00:00:00 | 00:00:00 | 02:30:00 | 02:30:00
HTML Tour - SWEng Group 4 |  | 01:15:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 01:15:00 | 01:15:00
| Joe Butler | 01:15:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 01:15:00 | 01:15:00
TOTAL |  | 08:30:00 | 06:00:00 | 04:15:00 | 05:15:00 | 03:00:00 | 05:00:00 | 00:15:00 | 32:15:00 | 32:15:00
[9 empty] | Billable total: | 32.25 | Difference to predicted: | -5
Notes on labour for week 31:
| Finance manager comment from weekly timesheet: | The team had predicted 47.25 hours for this week, week 2 of iteration 3. We have gone over on estimated hours in total of 8 for the entire project. We have gone under on hours this week by 15 so have added to the company redundancy which now stands at £892.79 extra in the pot. The company remains in a comfortable place financially. Due to deadlines and exams fast approaching, not all team members have been fully involved this week. With all change log items in place, the team is where is expected to be with regards to the Financial Business Plan. The team has the finances and hours required to finish the application. One item of note is that there was a mistake on C34 offering 5 hours of programming time when only 2 hours was budgeted. This mistake can be rectified with the company financial redundancy. Even with this extra time, the story is now finished but again went over this 5 hour limit coming out at 9.25 hours. Design manager leading this story may require some remedial training to stay on a specific task.
| Team lead comment from weekly timesheet: | Financially we're are in a good position but more alterations to the plan need to be made. Due to exams and other assignments production is down so focus needs to be on delivering our main features that have been backed up by the recent survey. This features are looking to be finished before the release in good time.
Other comments for week 31: | N/A
Estimated time - Week 32
Role | Name | Software | Design | Testing | Meetings | Finance | Administration | Total | Stories not taken | Type | Hours
Project Manager | James Pearson | 6 |  |  | 1 |  | 2 | 9 | A14 | recipe icons | 3
Finance Manager | Louis Newman |  |  |  | 1 | 2 |  | 3
Design & Specification Manager | Joe Butler | 6 | 1.5 |  | 1 |  |  | 8.5 | total not used: | (with design & testing) | 3.75
Lead Software Developer | James Clawley |  |  |  | 1 |  |  | 1
Testing & Integration Manager | Nathan Billis |  |  | 1.5 | 1 |  |  | 2.5
Marketing Manager | Becky Anderson |  |  |  | 1 |  |  | 1
XML & Server Manager | Jun Ma |  |  |  | 1 |  |  | 1
[7 empty] | Total: | 26
Reason for predicted hour distribution: | Hours assigned to team member taking lead on story to delegate as they see fit.
Actual timesheet - Week 32
Project | User | 05/04/2020 | 05/05/2020 | 05/06/2020 | 05/07/2020 | 05/08/2020 | 05/09/2020 | 05/10/2020 | Total | Billable total
Finance - SWEng Group 4 |  | 00:00:00 | 00:00:00 | 00:15:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:15:00 | 00:15:00
| Louis Newman | 00:00:00 | 00:00:00 | 00:15:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:15:00 | 00:15:00
Meetings - SWEng Group 4 |  | 03:30:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 03:30:00 | 03:30:00
| James Pearson | 00:30:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:30:00 | 00:30:00
| Louis Newman | 00:30:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:30:00 | 00:30:00
| Rebecca Anderson | 00:30:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:30:00 | 00:30:00
| Nathan Billis | 00:30:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:30:00 | 00:30:00
| Jun Ma | 00:30:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:30:00 | 00:30:00
| Joe Butler | 00:30:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:30:00 | 00:30:00
| James Clawley | 00:30:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:30:00 | 00:30:00
Software - SWEng Group 4 |  | 00:00:00 | 02:00:00 | 00:00:00 | 05:00:00 | 08:00:00 | 01:30:00 | 00:00:00 | 16:30:00 | 16:30:00
| James Pearson | 00:00:00 | 00:00:00 | 00:00:00 | 02:00:00 | 03:00:00 | 00:00:00 | 00:00:00 | 05:00:00 | 05:00:00
| Louis Newman | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 03:00:00 | 00:00:00 | 00:00:00 | 03:00:00 | 03:00:00
| Nathan Billis | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 01:30:00 | 00:00:00 | 01:30:00 | 01:30:00
| James Clawley | 00:00:00 | 02:00:00 | 00:00:00 | 03:00:00 | 02:00:00 | 00:00:00 | 00:00:00 | 07:00:00 | 07:00:00
Design - SWEng Group 4 |  | 01:30:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 01:30:00 | 01:30:00
| Joe Butler | 01:30:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 01:30:00 | 01:30:00
HTML Tour - SWEng Group 4 |  | 01:30:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 01:30:00 | 01:30:00
| Joe Butler | 01:30:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 01:30:00 | 01:30:00
TOTAL |  | 06:30:00 | 02:00:00 | 00:15:00 | 05:00:00 | 08:00:00 | 01:30:00 | 00:00:00 | 23:15:00 | 23:15:00
[9 empty] | Total billable | 23.25 | Difference to predicted: | 2.75
Notes on labour for week 32:
| Finance manager comment from weekly timesheet: | The team had predicted 29.75 hours for this week, week 3 of iteration 3. We have gone over on estimated hours in total of 1.5 for the entire project. We have gone under on hours this week by 6.5 so have added to the company redundancy which now stands at £974.04 extra in the pot. The company remains in a comfortable place financially. Team members have been preoccupied by other commitments recently due to other deadlines and exams, however this period is coming to a close and the company having a large financial redundancy due to the sale of modules still, some of the hourly restrictions and being slightly loosened in order to allow team members to finish the project to the high standard we have come to expect. Hours will remain closely watched, but members are no longer required to request extra hours and instead, trust is in place that all extra hours used during this period are going toward perfecting all aspects of the application ready for the completion of iteration 3.
| Team lead comment from weekly timesheet: | Final push to get everything done we can. I have diverted some of our resources to the development of the HTML tour and to the start of the Presentation to allow us some breathing room towards the end. Main features are looking polished and are near completion. Financially, in a very solid position giving us the ability to have a strong push before release to make sure that all features work as intended and that we have the quality of product that we strive for.
Other comments for week 32:
Estimated time - Week 33
Role | Name | Software | Design | Testing | Meetings | Finance | Administration | Total | Stories not taken | Type | Hours
Project Manager | James Pearson |  |  |  | 1 |  | 2 | 3 | C15 | disliked recipes | 3
Finance Manager | Louis Newman | 6 |  |  | 1 | 2 |  | 9
Design & Specification Manager | Joe Butler |  | 1.625 |  | 1 |  |  | 2.625 | total not used: | (with design & testing) | 3.75
Lead Software Developer | James Clawley |  |  |  | 1 |  |  | 1
Testing & Integration Manager | Nathan Billis |  |  | 1.625 | 1 |  |  | 2.625
Marketing Manager | Becky Anderson |  |  |  | 1 |  |  | 1
XML & Server Manager | Jun Ma | 7 |  |  | 1 |  |  | 8
[7 empty] | Total: | 27.25
Reason for predicted hour distribution: | Hours assigned to team member taking lead on story to delegate as they see fit.
Actual timesheet - Week 33
Project | User | 05/11/2020 | 05/12/2020 | 05/13/2020 | 05/14/2020 | 05/15/2020 | 05/16/2020 | 05/17/2020 | Total | total billable
Finance - SWEng Group 4 |  | 00:00:00 | 00:00:00 | 00:15:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:15:00 | 00:15:00
| Louis Newman | 00:00:00 | 00:00:00 | 00:15:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:15:00 | 00:15:00
Meetings - SWEng Group 4 |  | 01:45:00 | 03:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 04:45:00 | 04:45:00
| James Pearson | 00:00:00 | 00:45:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:45:00 | 00:45:00
| Louis Newman | 00:00:00 | 00:45:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:45:00 | 00:45:00
| Rebecca Anderson | 00:00:00 | 00:45:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:45:00 | 00:45:00
| Nathan Billis | 00:00:00 | 00:45:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:45:00 | 00:45:00
| Jun Ma | 00:30:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:30:00 | 00:30:00
| Joe Butler | 00:45:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:45:00 | 00:45:00
| James Clawley | 00:30:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:30:00 | 00:30:00
Software - SWEng Group 4 |  | 06:00:00 | 03:00:00 | 00:00:00 | 05:00:00 | 10:30:00 | 13:30:00 | 03:00:00 | 41:00:00 | 41:00:00
| James Pearson | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 03:00:00 | 04:00:00 | 00:00:00 | 07:00:00 | 07:00:00
| Louis Newman | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 05:00:00 | 06:00:00 | 03:00:00 | 14:00:00 | 14:00:00
| Rebecca Anderson | 00:00:00 | 02:30:00 | 00:00:00 | 03:00:00 | 01:30:00 | 02:00:00 | 00:00:00 | 09:00:00 | 09:00:00
| Nathan Billis | 03:00:00 | 00:30:00 | 00:00:00 | 00:00:00 | 01:00:00 | 00:00:00 | 00:00:00 | 04:30:00 | 04:30:00
| Jun Ma | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 01:30:00 | 00:00:00 | 01:30:00 | 01:30:00
| James Clawley | 03:00:00 | 00:00:00 | 00:00:00 | 02:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 05:00:00 | 05:00:00
Testing - SWEng Group 4 |  | 00:00:00 | 00:00:00 | 00:00:00 | 00:15:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:15:00 | 00:15:00
| Nathan Billis | 00:00:00 | 00:00:00 | 00:00:00 | 00:15:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:15:00 | 00:15:00
Marketing - SWEng Group 4 |  | 00:00:00 | 01:00:00 | 00:00:00 | 00:30:00 | 00:00:00 | 00:00:00 | 00:00:00 | 01:30:00 | 01:30:00
| Rebecca Anderson | 00:00:00 | 01:00:00 | 00:00:00 | 00:30:00 | 00:00:00 | 00:00:00 | 00:00:00 | 01:30:00 | 01:30:00
Administration - SWEng Group 4 |  | 00:15:00 | 00:30:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:15:00 | 01:00:00 | 01:00:00
| James Pearson | 00:15:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:15:00 | 00:30:00 | 00:30:00
| Rebecca Anderson | 00:00:00 | 00:30:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:30:00 | 00:30:00
Design - SWEng Group 4 |  | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 01:30:00 | 00:00:00 | 00:00:00 | 01:30:00 | 01:30:00
| Joe Butler | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 01:30:00 | 00:00:00 | 00:00:00 | 01:30:00 | 01:30:00
HTML Tour - SWEng Group 4 |  | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:30:00 | 00:00:00 | 00:00:00 | 00:30:00 | 00:30:00
| Nathan Billis | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:30:00 | 00:00:00 | 00:00:00 | 00:30:00 | 00:30:00
TOTAL |  | 08:00:00 | 07:30:00 | 00:15:00 | 05:45:00 | 12:30:00 | 13:30:00 | 03:15:00 | 50:45:00 | 50:45:00
[9 empty] | Total billable | 50.75 | Difference to predicted: | -23.5
Notes on labour for week 33:
| Finance manager comment from weekly timesheet: | The team had predicted 31 hours for this week, week 4 of iteration 3. We have gone over on estimated hours in total of 21.25 for the entire project. We have gone over on hours this week by 19.75 so have reduced the company redundancy which now stands at £727.17 extra in the pot. The company remains in a comfortable place financially. From going under last week, some of the team still have some exams left but the team is starting to return concentration to the SWEng effort in order to bring iteration 3 to a strong ending. To that end the team has gone over in hours but we have the redundancy to do so and since lifting hour restrictions last week the team has taken that into play with this week of labour. The team remains in a strong place financially and the restriction will remain off until the team has finished with a product we can be proud of.
| Team lead comment from weekly timesheet: | Echoing the Financial Manager, The company looks to be in a healthy position right up until the release date of the application. With maximum focus being brought back onto the project, we will be looking at ramping up the hours in development to make sure the application is as polished as possible and that any changes that need to be made as per the Design Survey results, can be made.
Other comments for week 33: | N/A
Financial updates from reporting period: | A better estimate of Firebase pricing is now avaliable due to usage data across several months with 7 developers. Particularly paying close attention to the last month of data, the application now hosts the majority of initial lauch expected capabilities giving a clearer picture of what costs may look like upon release.
Team lead comments on story alterations | Due to re-evaluating the plan the following user stories have been removed and will no longer be flagged for development. C25 has been removed due its complexity. The story is to produce recipes based on categories of recipes the user has made before. This requires a machine learning algorithm to implement and with the potential of having an incredible number of categories due to user created recipes, this is a little out of reach for the time we have available. C30 has been removed as a story as its very similar to another user story that was a part of the social side. Users are able to leave comments and reviews, so this story has effectively already been done. A14 has been removed as the time it would take to implement icons for every recipe and ingredient properly would be too long. This also adds no real value to application so spending critical development time on something that adds nothing it terms of functionality is a waste of the precious time we have left. C15 was removed completely as users can remove meals from the plan at any time, they like so it is now irrelevant. Due to these changes in the plan, 27.5 hours in total have been accrued. This time has already been reassigned to other areas of development.
Team lead comments from reporting period: | In the last few weeks development has slowed due to external factors such as exams and assignments. Within this time good progress has been made in some of key areas. The social aspect has made great strides and is very near completion. The team have also implemented a new search function that allows for a more robust searching. Coming towards the end of the third iteration and having the development team back at full capacity, we can make a final push to make sure that everything is polished and in fully working order. Due to the slowdown in development and the reorganising of the plan we have enough hours and financial strength to divert all resources to the tasks at hand.
Financial Project Summary
Team lead comments on financial status from project | Over the course of the project the company has been financially solid. There are numerous factors to consider why this has been the case. During Iteration 2, the decision was made to lower the time the group spent in meetings and to lower the time allocated to design after the first Iteration and design phase to allow more financial flexibility. This would allow us more funds to assign to features that would develop issues and take longer to implement. A big factor in the financial stability the company has had throughout the project is down to the contract negotiations and selling of our modules. Due to the successful negotiations the company accrued a large redundancy pot that could be allocated to the features that were very important and time consuming. For example, the social media side of the application was larger than originally estimated and the redundancy allowed the development to proceed as planned and for however long it took to get right. As we approach the end of the development phase and towards the release of the application, the company remains in a healthy financial position.
Breakdown of team labour over project-(30/09/19 - 10/05/20)
Project Labour Summary | Labour estimations have been mostly accurate throughout the project. We have gone over our estimate several times but the spare capacity from module sales allowed us this leeway. This over time allowed stories to be completed to the required standard and will pay dividends upon release.
Project overall financial summary | The team has remained in a strong place financially. All financial matters were directed though myself and I have been firm but fair with the team with labour and extra costs. I took the decision following the sale of modules to keep this money within the company instead of paying the bank back a small sum in order to relieve some of the interest we will pay in later months. I still believe this was the correct decision as it allowed the team to go over allocated hours in some stories to maintain our standards. All other costs have been set via contracts so predicted costs have matched up as expected. Estimating user time via hours allocated to contracts has worked well, where not completely accurate at times, the rough estimates have rounded out to expected costs.
Lessons learnt | All estimates should be made carefully, with significant research and group deliberation. The team should be firm with estimates and push to come in on time and target, however the team should also remember that these were purely estimates and in some cases leeway is sometimes required.
30/09/19 - 10/05/20 totals
|  | Premises Rent | 22144.2308
|  | Utilities Rent | 1700
|  | IT infrastructure | 3400
|  | Labour | 10859.375
|  | Weekly interest | 1835.8929
|  | Module purchases | 461.32
| CoDev Profit & Loss (30/09/19 - 10/05/20) |  |  | CoDev Balance sheet (10/05/20)
| Sales Revenue | 1054.11 |  | Fixed Assets
| Cost of Sales | 184.38 |  |  | Tangible fixed assets |  | 0
| Gross Profit | 869.73 |  |  | Financial fixed assets |  | 0
| Overheads | 24307.47
| Net Profit (PBIT) | -23437.74 |  | Current Assets
| Interest | 1546.83 |  |  | Cash in hand & at bank |  | 8917.86
| Profit Before Taxation | -24984.57 |  |  | Stock |  | 0
[5 empty] | Debtors |  | 0
Current Liabilities
Creditors
[5 empty] | Rent | -632.6923
[5 empty] | IT Infastructure | -900
[5 empty] | Utilities | -450
[5 empty] | Total: |  | -1982.6923
|  |  |  | Long term liabilities |  |  | -43030.6
|  |  |  | Net Assets |  |  | -36095.4323
Financial Performance over project | From the outset it was evident that learning the mechanics of the team, letting everyone work in their own best method while still attempting to hold the team to estimations of time would be difficult. Together as a team we estimated how long each story would take to program, at the beginning these estimations were slightly out due to must of the team overestimating their programming capabilities. As the project progressed, abilities caught up with projections and estimation got more accurate. For the most part, the team adhered to my guidelines, although some members still put in significantly more work than others, targets were met for the most part. A strong negotiation during the module sales enabled the team to have significantly extra money in the bank that allowed some restrictions on time to be relieved. This enabled the team to put extra time into key selling features and has led to a better product. The financial platform for the company has been solid throughout the project. Moving forward into deployment, we hope this solid financial platform gives investors reassurance that the company has what it takes to take Scran Plan to market for a strong return on investment.