## Financal report 2
Financial Report II | SWEng Group 4
Version Control
Author: | Position: | Date: | Version: | Notes:
Louis Newman | Codev Financial Manager | 2020-03-03 | 1 | Full build, comments from group lead added.
Content: | Financial report covering between 17/02/2020 - 01/03/2020
Predicted forcast:
Week number | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23
Week dates | Sep. 30, 2019-Oct. 6, 2019 | Oct. 7, 2019-Oct. 13, 2019 | Oct. 14, 2019-Oct. 20, 2019 | Oct. 21, 2019-Oct. 27, 2019 | Oct. 28, 2019-Nov. 3, 2019 | Nov. 4, 2019-Nov. 10, 2019 | Nov. 11, 2019-Nov. 17, 2019 | Nov. 18, 2019-Nov. 24, 2019 | Nov. 25, 2019-Dec. 1, 2019 | Dec. 2, 2019-Dec. 8, 2019 | Dec. 9, 2019-Dec. 15, 2019 | Dec. 16, 2019-Dec. 22, 2019 | Dec. 23, 2019-Dec. 29, 2019 | Dec. 30, 2019-Jan. 5, 2020 | Jan. 6, 2020-Jan. 12, 2020 | Jan. 13, 2020-Jan. 19, 2020 | Jan. 20, 2020-Jan. 26, 2020 | Jan. 27, 2020-Feb. 2, 2020 | Feb. 3, 2020-Feb. 9, 2020 | Feb. 10, 2020-Feb. 16, 2020 | Feb. 17, 2020-Feb. 23, 2020 | Feb. 24, 2020-Mar. 1, 2020 | Mar. 2, 2020-Mar. 8, 2020
Term week | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | Christmas | Christmas | Christmas | Christmas | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9
Project Iteration Stage | Preparation | Preparation | Preparation | Preparation | Preparation | Preparation | Preparation | Preparation | Preparation | Preparation | Preparation | Preparation | Preparation | Preparation | Preparation | Preparation | Preparation | Preparation | Iteration 1, week 1 | Iteration 1, week 2 | Iteration 1, week 3 | Iteration 1, week 4 | Iteration 1, week 5
Predicted weekly hours | 0 | 0 | 0 | 7 | 8.25 | 8.25 | 8.5 | 7.75 | 20.25 | 14 | 0 | 0 | 0 | 0 | 0 | 45.25 | 67.5 | 35 | 47.75 | 59 | 58.5 | 42.5 | 46
IN
Loans (IN) | [19 empty] | 28243.1471
Module sales (IN)
OUT
Premises Rent |  |  |  | -2530.7692 |  |  | -1898.0769 |  |  | -1898.0769 | [7 empty] | -5061.5385 |  |  | -1898.0769
Utilities Rent | [5 empty] | -300 |  |  |  | -200 | [9 empty] | -500
IT infrastructure | [5 empty] | -600 |  |  |  | -400 | [9 empty] | -1000
Cost of Labour (12.5 GBP per hour) | 0 | 0 | 0 | -87.5 | -103.125 | -103.125 | -106.25 | -96.875 | -253.125 | -175 | 0 | 0 | 0 | 0 | 0 | -565.625 | -843.75 | -437.5 | -596.875 | -737.5 | -731.25 | -531.25 | -575
Weekly interest (16.86% APR) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -91.573 | -91.573 | -91.573 | -91.573
Module purchases (OUT) | [21 empty] | -100
Creditors
Total credit for loans | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28243.1471 | 28243.1471 | 28243.1471 | 28243.1471
Total credit for modules | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 300 | 300
Opening Balance | 0 | 0 | 0 | 0 | -2618.2692 | -2721.3942 | -3724.5192 | -5728.8462 | -5825.7212 | -6078.8462 | -8751.9231 | -8751.9231 | -8751.9231 | -8751.9231 | -8751.9231 | -8751.9231 | -9317.5481 | -10161.2981 | -15660.3365 | -16257.2115 | 9656.8626 | 6935.9627 | 6213.1398
OUT total | 0 | 0 | 0 | -2618.2692 | -103.125 | -1003.125 | -2004.3269 | -96.875 | -253.125 | -2673.0769 | 0 | 0 | 0 | 0 | 0 | -565.625 | -843.75 | -5499.0385 | -596.875 | -2329.073 | -2720.8999 | -722.823 | -666.573
IN total | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28243.1471 | 0 | 0 | 0
Closing Balance | 0 | 0 | 0 | -2618.2692 | -2721.3942 | -3724.5192 | -5728.8462 | -5825.7212 | -6078.8462 | -8751.9231 | -8751.9231 | -8751.9231 | -8751.9231 | -8751.9231 | -8751.9231 | -9317.5481 | -10161.2981 | -15660.3365 | -16257.2115 | 9656.8626 | 6935.9627 | 6213.1398 | 5546.5668
Actual forcast:
Week number | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23
Week dates | Sep. 30, 2019-Oct. 6, 2019 | Oct. 7, 2019-Oct. 13, 2019 | Oct. 14, 2019-Oct. 20, 2019 | Oct. 21, 2019-Oct. 27, 2019 | Oct. 28, 2019-Nov. 3, 2019 | Nov. 4, 2019-Nov. 10, 2019 | Nov. 11, 2019-Nov. 17, 2019 | Nov. 18, 2019-Nov. 24, 2019 | Nov. 25, 2019-Dec. 1, 2019 | Dec. 2, 2019-Dec. 8, 2019 | Dec. 9, 2019-Dec. 15, 2019 | Dec. 16, 2019-Dec. 22, 2019 | Dec. 23, 2019-Dec. 29, 2019 | Dec. 30, 2019-Jan. 5, 2020 | Jan. 6, 2020-Jan. 12, 2020 | Jan. 13, 2020-Jan. 19, 2020 | Jan. 20, 2020-Jan. 26, 2020 | Jan. 27, 2020-Feb. 2, 2020 | Feb. 3, 2020-Feb. 9, 2020 | Feb. 10, 2020-Feb. 16, 2020 | Feb. 17, 2020-Feb. 23, 2020 | Feb. 24, 2020-Mar. 1, 2020 | Mar. 2, 2020-Mar. 8, 2020
Term week | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | Christmas | Christmas | Christmas | Christmas | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9
Project Iteration Stage | Preparation | Preparation | Preparation | Preparation | Preparation | Preparation | Preparation | Preparation | Preparation | Preparation | Preparation | Preparation | Preparation | Preparation | Preparation | Preparation | Preparation | Preparation | Iteration 1, week 1 | Iteration 1, week 2 | Iteration 1, week 3 | Iteration 1, week 4 | Iteration 1, week 5
Predicted weekly hours | 0 | 0 | 0 | 7 | 8.25 | 8.25 | 8.5 | 7.75 | 20.25 | 14 | 0 | 0 | 0 | 0 | 0 | 45.25 | 67.5 | 35 | 47.75 | 59 | 58.5 | 42.5 | 46
Actual weekly hours | 0 | 0 | 0 | 7 | 8.25 | 8.25 | 8.5 | 7.75 | 20.25 | 14 | 0 | 0 | 0 | 0 | 0 | 45.25 | 67.5 | 35 | 40.5 | 70.25 | 32.5 | 55.75 | Current week
IN
Loans (IN) | [19 empty] | 28243.1471
Module sales (IN) | [21 empty] | 263.53
OUT
Premises Rent |  |  |  | -2530.7692 |  |  | -1898.0769 |  |  | -1898.0769 | [7 empty] | -5061.5385 |  |  | -1898.0769
Utilities Rent | [5 empty] | -300 |  |  |  | -200 | [9 empty] | -500
IT infrastructure | [5 empty] | -600 |  |  |  | -400 | [9 empty] | -1000
Cost of Labour (12.5 GBP per hour) | 0 | 0 | 0 | -87.5 | -103.125 | -103.125 | -106.25 | -96.875 | -253.125 | -175 | 0 | 0 | 0 | 0 | 0 | -565.625 | -843.75 | -437.5 | -506.25 | -878.125 | -406.25 | -696.875 | 0
Weekly interest (16.86% APR) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -91.573 | -91.573 | -91.573 | -91.573
Module purchases (OUT) | [21 empty] | -115.33
Creditors
Total credit for loans | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28243.1471 | 28243.1471 | 28243.1471 | 28243.1471
Total credit recieved for modules | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 345.99 | 345.99
Total credit given for modules | [21 empty] | 790.58 | 790.58
Opening Balance | 0 | 0 | 0 | 0 | -2618.2692 | -2721.3942 | -3724.5192 | -5728.8462 | -5825.7212 | -6078.8462 | -8751.9231 | -8751.9231 | -8751.9231 | -8751.9231 | -8751.9231 | -8751.9231 | -9317.5481 | -10161.2981 | -15660.3365 | -16166.5865 | 9606.8626 | 7210.9627 | 6570.7148
OUT total | 0 | 0 | 0 | -2618.2692 | -103.125 | -1003.125 | -2004.3269 | -96.875 | -253.125 | -2673.0769 | 0 | 0 | 0 | 0 | 0 | -565.625 | -843.75 | -5499.0385 | -506.25 | -2469.698 | -2395.8999 | -903.778 | -91.573
IN total | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28243.1471 | 0 | 263.53 | 0
Closing Balance | 0 | 0 | 0 | -2618.2692 | -2721.3942 | -3724.5192 | -5728.8462 | -5825.7212 | -6078.8462 | -8751.9231 | -8751.9231 | -8751.9231 | -8751.9231 | -8751.9231 | -8751.9231 | -9317.5481 | -10161.2981 | -15660.3365 | -16166.5865 | 9606.8626 | 7210.9627 | 6570.7148 | 6479.1418
Week 21 predictions: | Week 3 - Iteration 1 (Feb. 17, 2020-Feb. 23, 2020)
| User stories: | Main Home Screen User Stories: C6 (3), C7 (2.5), C18 (4.5) User Profiles + Privacy User Stories: A3 (2), A5 (2), A11 (5)
| All predictions: | Story total hours: 19, Added for pair-programming, design and code review: 28.5, Added for finance and management: 4 Added for meetings: 7, Total for week 3: 58.5
Estimated time - Week 21
Role | Name | Software | Design | Testing | Meetings | Finance | Administration | Total
Project Manager | James Pearson |  |  |  | 1 |  | 2 | 3
Finance Manager | Louis Newman | 19 |  |  | 1 | 2 |  | 22
Design & Specification Manager | Joe Butler | 10 | 4.75 |  | 1 |  |  | 15.75
Lead Software Developer | James Clawley |  |  |  | 1 |  |  | 1
Testing & Integration Manager | Nathan Billis |  |  | 4.75 | 1 |  |  | 5.75
Marketing Manager | Becky Anderson |  |  |  | 1 |  |  | 1
XML & Server Manager | Jun Ma | 9 |  |  | 1 |  |  | 10
[7 empty] | Total: | 58.5
Reason for predicted hour distribution: | From the stories required for completion in this week, the person taking lead on each of them was assiged the full duration for them to delegate where appropriate.
Actual timesheet - Week 21
Project | User | 02/17/2020 | 02/18/2020 | 02/19/2020 | 02/20/2020 | 02/21/2020 | 02/22/2020 | 02/23/2020 | Total | Billable Total
Finance - SWEng Group 4 |  | 00:00:00 | 00:00:00 | 02:00:00 | 01:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 03:00:00 | 03:00:00
| Louis Newman | 00:00:00 | 00:00:00 | 02:00:00 | 01:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 03:00:00 | 03:00:00
Meetings - SWEng Group 4 |  | 05:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 05:00:00 | 05:00:00
| Jp1439 | 01:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 01:00:00 | 01:00:00
| Louis Newman | 01:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 01:00:00 | 01:00:00
| Rea524 | 01:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 01:00:00 | 01:00:00
| nathanbillis | 01:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 01:00:00 | 01:00:00
| Jm2285 | 01:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 01:00:00 | 01:00:00
Software - SWEng Group 4 |  | 00:00:00 | 00:00:00 | 00:00:00 | 05:00:00 | 03:00:00 | 01:30:00 | 05:45:00 | 15:15:00 | 15:15:00
| Jp1439 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 01:30:00 | 00:30:00 | 02:00:00 | 02:00:00
| Louis Newman | 00:00:00 | 00:00:00 | 00:00:00 | 01:00:00 | 00:00:00 | 00:00:00 | 01:30:00 | 02:30:00 | 02:30:00
| Rea524 | 00:00:00 | 00:00:00 | 00:00:00 | 02:00:00 | 00:00:00 | 00:00:00 | 00:45:00 | 02:45:00 | 02:45:00
| Jb2200 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 03:00:00 | 03:00:00 | 03:00:00
| James Clawley | 00:00:00 | 00:00:00 | 00:00:00 | 02:00:00 | 03:00:00 | 00:00:00 | 00:00:00 | 05:00:00 | 05:00:00
Administration - SWEng Group 4 |  | 00:00:00 | 02:00:00 | 01:00:00 | 00:00:00 | 00:30:00 | 01:00:00 | 00:00:00 | 04:30:00 | 04:30:00
| Jp1439 | 00:00:00 | 02:00:00 | 01:00:00 | 00:00:00 | 00:00:00 | 01:00:00 | 00:00:00 | 04:00:00 | 04:00:00
| Louis Newman | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:30:00 | 00:00:00 | 00:00:00 | 00:30:00 | 00:30:00
Design - SWEng Group 4 |  | 00:00:00 | 00:00:00 | 00:00:00 | 00:45:00 | 00:00:00 | 02:00:00 | 02:00:00 | 04:45:00 | 04:45:00
| Jm2285 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 02:00:00 | 02:00:00 | 04:00:00 | 0:00 | No proof of any work completed
| Jb2200 | 00:00:00 | 00:00:00 | 00:00:00 | 00:45:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:45:00 | 00:45:00
Tender presentation - SWEng Group 4 |  | 04:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 04:00:00 | 04:00:00
| Louis Newman | 01:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 01:00:00 | 01:00:00
| Rea524 | 01:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 01:00:00 | 01:00:00
| Jm2285 | 01:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 01:00:00 | 01:00:00
| James Clawley | 01:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 01:00:00 | 01:00:00
TOTAL |  | 09:00:00 | 02:00:00 | 03:00:00 | 06:45:00 | 03:30:00 | 04:30:00 | 07:45:00 | 36:30:00 | 36.30.00
[9 empty] | Total billable: | 32.5 | Difference to predicted: | 26
Notes on labour for week 21: | Comment on hour dispersion: | Some stories within this week relied on stories from previous weeks being completed. Due to this lack some were put on hold and others were completed in less time than was predicted, this led to the team having 22 hours spare at the end of the week that would be required to finish the stories that have been put on hold.
| Alterations from this prediction: | Jun, our XML & Server Manager, took the story C18, this story was found to be far from his capabilities, with the application of pair programming this was still found to be beyond possible scope and Jun was pulled off this story and the hours were re-distributed to myself, Louis, our Finance Manager. Jun has been tasked with a new story taken from iteration 3 in order to give him a viable starting point with Android programming.
| Comment on rejected hours: | Jun had input four hours of work for the design of C18, when asked to show the group evidence of this design he was found to have nothing to show and be lacking in the download of either Github or the full download of Android Studio. It is for this reason; those four hours were rejected by the team lead and Jun was assigned Louis as a pair-programming partner to deal with C18 as a pair. This was the session where it was found this story was beyond Jun's capabilities and pair-programming with such a complex story was not a good idea, leading to Jun being assigned an easier story to get him started with programming with Java in and Android environment. He was then also given a lesson from Joe, our Design & Specification Manager, to get up and running with Github and Android Studio.
| Labour summary: | As a team we were significantly under the estimation for this week, this has been predominantly due to the group still getting to grips with programming in Java in an Android environment. Individuals are being addressed but the team remains behind on finishing the user stories required for this week.
Other comments for week 21: | Other things that happened in this week include negotiations for module purchases, we were able to purchase the required modules in at 75 GBP more than our estimate for these. The good news here is that we were also able to sell two modules that were already being built by the team and achieve a very good price for these two modules with some tough negotiation on our behalf. Selling both modules for a total just over 1000 GBP we should be in a good state financially to support the team in any hours we go over during the first iteration.
Week 22 predictions: | Week 4 - Iteration 1 (Feb. 24, 2020-Mar. 1, 2020)
| User stories: | Main Home Screen User Stories: C6 (3), C7 (2.5), C18 (4.5) User Profiles + Privacy User Stories: A3 (2), A5 (2), A11 (5)
| All predictions: | Story total hours: 19, Added for pair-programming, design and code review: 28.5, Added for finance and management: 4, Added for meetings: 7, Total for week 3: 58.5
Estimated time - Week 22
Role | Name | Software | Design | Testing | Meetings | Finance | Administration | Total
Project Manager | James Pearson |  |  |  | 1 |  | 4 | 5
Finance Manager | Louis Newman |  |  |  | 1 | 2 | 2 | 5
Design & Specification Manager | Joe Butler | 2 | 2.75 |  | 1 |  |  | 5.75
Lead Software Developer | James Clawley | 20 |  |  | 1 |  |  | 21
Testing & Integration Manager | Nathan Billis |  |  | 2.75 | 1 |  |  | 3.75
Marketing Manager | Becky Anderson |  |  |  | 1 |  |  | 1
XML & Server Manager | Jun Ma |  |  |  | 1 |  |  | 1
[7 empty] | Total: | 42.5
Reason for predicted hour distribution: | This week was the week for the presentation build within the application, all software was to be based around this. The lead programmer, James C, took lead and control of this effort and was given the full hour distribution for this task to delegate where he saw fit. Joe had a small task within this week of connecting a previous user story to one that was built and asked to run as the second in command on the presentation build.
Actual timesheet - Week 22
Project | User | 02/24/2020 | 02/25/2020 | 02/26/2020 | 02/27/2020 | 02/28/2020 | 02/29/2020 | 03/01/2020 | Total | Billable total
Meetings - SWEng Group 4 |  | 04:45:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 04:45:00 | 04:45:00
| James Pearson | 00:45:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:45:00 | 00:45:00
| Louis Newman | 00:45:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:45:00 | 00:45:00
| Rebecca Anderson | 00:45:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:45:00 | 00:45:00
| Nathan Billis | 00:45:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:45:00 | 00:45:00
| Jun Ma | 01:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 01:00:00 | 0:45
| James Clawley | 00:45:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:45:00 | 00:45:00
| Joe Butler | 0:45 | [7 empty] | 0:45
Software - SWEng Group 4 |  | 01:00:00 | 00:00:00 | 12:00:00 | 12:00:00 | 07:45:00 | 04:00:00 | 02:45:00 | 39:30:00 | 39:30:00
| Louis Newman | 00:00:00 | 00:00:00 | 01:00:00 | 03:30:00 | 00:00:00 | 00:00:00 | 02:00:00 | 06:30:00 | 06:30:00
| Rebecca Anderson | 00:00:00 | 00:00:00 | 03:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:45:00 | 03:45:00 | 03:45:00
| Nathan Billis | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 02:00:00 | 00:00:00 | 00:00:00 | 02:00:00 | 02:00:00
| Joe Butler | 01:00:00 | 00:00:00 | 00:00:00 | 02:30:00 | 00:45:00 | 04:00:00 | 00:00:00 | 08:15:00 | 08:15:00
| James Clawley | 00:00:00 | 00:00:00 | 08:00:00 | 06:00:00 | 05:00:00 | 00:00:00 | 00:00:00 | 19:00:00 | 19:00:00
Testing - SWEng Group 4 |  | 00:00:00 | 00:45:00 | 00:00:00 | 00:30:00 | 00:00:00 | 00:00:00 | 00:00:00 | 01:15:00 | 01:15:00
| Nathan Billis | 00:00:00 | 00:45:00 | 00:00:00 | 00:30:00 | 00:00:00 | 00:00:00 | 00:00:00 | 01:15:00 | 01:15:00
Administration - SWEng Group 4 |  | 00:00:00 | 00:00:00 | 00:30:00 | 01:15:00 | 00:00:00 | 00:00:00 | 00:00:00 | 01:45:00 | 01:45:00
| James Pearson | 00:00:00 | 00:00:00 | 00:30:00 | 01:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 01:30:00 | 01:30:00
| Nathan Billis | 00:00:00 | 00:00:00 | 00:00:00 | 00:15:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:15:00 | 00:15:00
User Stories - SWEng Group 4 |  | 00:00:00 | 00:00:00 | 00:00:00 | 01:00:00 | 00:00:00 | 01:00:00 | 02:00:00 | 04:00:00 | 04:00:00
| James Pearson | 00:00:00 | 00:00:00 | 00:00:00 | 01:00:00 | 00:00:00 | 01:00:00 | 02:00:00 | 04:00:00 | 04:00:00
Design - SWEng Group 4 |  | 00:00:00 | 00:00:00 | 00:00:00 | 01:30:00 | 01:30:00 | 01:30:00 | 00:00:00 | 04:30:00 | 04:30:00
| Jun Ma | 00:00:00 | 00:00:00 | 00:00:00 | 01:30:00 | 01:30:00 | 01:30:00 | 00:00:00 | 04:30:00 | 04:30:00
TOTAL |  | 05:45:00 | 00:45:00 | 12:30:00 | 16:15:00 | 09:15:00 | 06:30:00 | 04:45:00 | 55:45:00 | 56.25.00
[9 empty] | Total billable | 56.25 | Difference to predicted: | -13.75
Notes on labour for week 22: | Comment on rejected hours: | The only rejected hours during this week were that Jun had put in too much time for a meeting, the extra time input was rejected.
| Comment on dicrepency: | A significant proportion of the presentation was completed during this week along with completion of stories that were unable to be completed in previoud weeks. We went over by nearly 14 hours but due to last weeks discepencies these were all accounted for.
| Comment on hour dispersion: | James C took lead as he was supposed to on the Presentation, He decided to get the bulk of this done in his own time. He was supposed to be working with Joe but Joe had gone over on a previous week’s story and was now trying to put together this week’s story on top of that and didn't get around to fulfilling the role he has suggested he would play. All other programming hours used went into finishing stories from previous weeks other than Jun now having a story from iteration 3 to get him up and running with programming in Java in an android environment.
Other comments for week 22: | Finalising of contracts and negotiations took place in this week, we used less labour hours than predicted and got exactly what we wanted out of these negotiations so the team in in a good place financially in reference to this.
Comments on reporting period: | With where we are in terms of the Iteration 1 programming effort, we are very slightly behind the predicted position. However, the short comings in programming ability of the team are being addressed and the slow pace that came at the start of the iteration is now being gained on. The team is showing all the correct signs that we will be where we predicted we would be at the end of iteration 1. The short comings in programming ability are still being addressed with pair programming the weak with the strong and lessons for those not up to the standard required. The product is really now starting to come together with a strong backend data structure and a front end that it taking up functionality with every new branch merge. The team has taken to the addressing of shorted meetings and these have been worked down in 15-minute intervals from 1 hour to 30 minutes. Contract negations went better than could have been expected, paying 75 GBP more than we wanted to but then making the sales of over 1000 GBP. The production of these modules is going spectacularly well with the majority of these nearly finished as they came as part of the presentation user stories.
30th September - 3rd March 2020.
Comments from team lead: | After a slow start to development and becoming aware of some early weaknesses within the team, we can now go forward with the awareness of how to effectively pair up team members on particular user stories to get the most out of our time while getting everyone up to speed on the different aspects the application will reveal. Proud of what was achieved with the module negotions which i believe is a fair reflection of the effort that needs to be applied. After speaking to the Financial backer and customer about pushiing a feature from the first iteration, we look on track to deliver as specified.