## Full & Predicted
Group 4 Financial Buisness Plan | 38 weeks total
Section | Quantity | price details | Agreed price num | Cost per week in GBP | Total known costs | Date Due | Contract end date
Cost of Labour | 7 | 12.5 GBP per employee per hour | 12.5 | dependant on timesheet |  | Weekly, one week in arrears subject to correct time sheet
Premises Rent | 1400 | 23.50 GBP per sq ft per annum | 23.5 | 632.6923 | 24042.3077 | End of weeks 4, 7 and 10 of each term | Summer end week 10
Utilities Rent | 1 | 50 GBP per week | 50 | 50 | 1900 | End of weeks 6 and 10 of each term | Summer end week 10
IT infrastructure | 1 | 100 GBP per week | 100 | 100 | 3800 | End of weeks 6 and 10 of each term. | Summer end week 10
Interest rates | 1 | 16.86% of balance owed in that week | 0.1686 |  |  | Deducted weekly
Cost of hosting | x1 (single application) |  |  |  | total owed in rent, IT and utilities
Cost of deployment to Play Store | x1 (single application) | 25 USD per application | 25 |  | 29742.3077
Marketing
0
goal seek
borrowed money | 44577.4268
clockify for recording meeting time etc
Actual finances
Predicted weekly hours | 0 | 0 | 0 | 7 | 8.25 | 8.25 | 8.5 | 7.75 | 20.25 | 14 | 0 | 0 | 0 | 0 | 0 | 45.25 | 67.5 | 35 | 47.75 | 59 | 58.5 | 42.5 | 46 | 29.25 | 47.25 | 34.75 | 28.5 | 43.5 | 43.5 | 37.25 | 47.25 | 29.75 | 31 | 43.5 | 75.25 | 7 | 0 | 0
Eiggle room | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7.25 | -4 | 22 | 8.25 | 7.5 | -3.25 | 5.75 | -32.75 | -52.5 | -32 | -32.75 | -23 | -8 | -1.5 | -21.25 | -54 | -81.75 | -79.25 | -79.25 | -79.25
Weekly outgoings table:
Week number | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38
Week dates | Sep. 30, 2019-Oct. 6, 2019 | Oct. 7, 2019-Oct. 13, 2019 | Oct. 14, 2019-Oct. 20, 2019 | Oct. 21, 2019-Oct. 27, 2019 | Oct. 28, 2019-Nov. 3, 2019 | Nov. 4, 2019-Nov. 10, 2019 | Nov. 11, 2019-Nov. 17, 2019 | Nov. 18, 2019-Nov. 24, 2019 | Nov. 25, 2019-Dec. 1, 2019 | Dec. 2, 2019-Dec. 8, 2019 | Dec. 9, 2019-Dec. 15, 2019 | Dec. 16, 2019-Dec. 22, 2019 | Dec. 23, 2019-Dec. 29, 2019 | Dec. 30, 2019-Jan. 5, 2020 | Jan. 6, 2020-Jan. 12, 2020 | Jan. 13, 2020-Jan. 19, 2020 | Jan. 20, 2020-Jan. 26, 2020 | Jan. 27, 2020-Feb. 2, 2020 | Feb. 3, 2020-Feb. 9, 2020 | Feb. 10, 2020-Feb. 16, 2020 | Feb. 17, 2020-Feb. 23, 2020 | Feb. 24, 2020-Mar. 1, 2020 | Mar. 2, 2020-Mar. 8, 2020 | Mar. 9, 2020-Mar. 15, 2020 | Mar. 16, 2020-Mar. 22, 2020 | Mar. 23, 2020-Mar. 29, 2020 | Mar. 30, 2020-Apr. 5, 2020 | Apr. 6, 2020-Apr. 12, 2020 | Apr. 13, 2020-Apr. 19, 2020 | Apr. 20, 2020-Apr. 26, 2020 | Apr. 27, 2020-May 3, 2020 | May 4, 2020-May 10, 2020 | May 11, 2020-May 17, 2020 | May 18, 2020-May 24, 2020 | May 25, 2020-May 31, 2020 | June 1, 2020-June 7, 2020 | June 8, 2020-June 14, 2020 | June 15, 2020-June 21, 2020 | 1052.5
Term week | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | Christmas | Christmas | Christmas | Christmas | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | Easter | Easter | Easter | Easter | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10
Project Iteration Stage | Preparation | Preparation | Preparation | Preparation | Preparation | Preparation | Preparation | Preparation | Preparation | Preparation | Preparation | Preparation | Preparation | Preparation | Preparation | Preparation | Preparation | Preparation | Iteration 1, week 1 | Iteration 1, week 2 | Iteration 1, week 3 | Iteration 1, week 4 | Iteration 1, week 5 | Iteration 1, week 6 | Iteration 2, week 1 | Iteration 2, week 2 | Iteration 2, week 3 | Iteration 2, week 4 | Iteration 2, week 5 | Iteration 3, week 1 | Iteration 3, week 2 | Iteration 3, week 3 | Iteration 3, week 4 | Iteration 3, week 5 | Presentation preparation | Presentation & hand in
Actual hours | 0 | 0 | 0 | 7 | 8.25 | 8.25 | 8.5 | 7.75 | 20.25 | 14 | 0 | 0 | 0 | 0 | 0 | 45.25 | 67.5 | 35 | 40.5 | 70.25 | 32.5 | 56.25 | 46.75 | 40 | 38.25 | 73.25 | 48.25 | 23 | 44.25 | 27.5 | 32.25 | 23.25 | 50.75 | 76.25 | 103 | 4.5 | 0 | 0
IN | [38 empty] | sales rev = | 1054.11
Loans (IN) | [19 empty] | 28243.1471 | [8 empty] | 16334.2796 | [9 empty] | total loan | 44577.4268
Module sales (IN) | [21 empty] | 263.53 |  | 790.58
OUT
Premises Rent |  |  |  | -2530.7692 |  |  | -1898.0769 |  |  | -1898.0769 | [7 empty] | -5061.5385 |  |  | -1898.0769 |  |  | -1898.0769 | [7 empty] | -5061.5385 |  |  | -1898.0769 |  |  | -1898.0769
Utilities Rent | [5 empty] | -300 |  |  |  | -200 | [9 empty] | -500 |  |  |  | -200 | [9 empty] | -500 |  |  |  | -200
IT infrastructure | [5 empty] | -600 |  |  |  | -400 | [9 empty] | -1000 |  |  |  | -400 | [9 empty] | -1000 |  |  |  | -400
Cost of Labour (12.5 GBP per hour) | 0 | 0 | 0 | -87.5 | -103.125 | -103.125 | -106.25 | -96.875 | -253.125 | -175 | 0 | 0 | 0 | 0 | 0 | -565.625 | -843.75 | -437.5 | -506.25 | -878.125 | -406.25 | -703.125 | -584.375 | -500 | -478.125 | -915.625 | -603.125 | -287.5 | -553.125 | -343.75 | -403.125 | -290.625 | -634.375 | -953.125 | -1287.5 | -56.25 | 0 | 0
Weekly interest (16.86% APR) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -91.573 | -91.573 | -91.573 | -91.573 | -91.573 | -91.573 | -91.573 | -91.573 | -91.573 | -144.5337 | -144.5337 | -144.5337 | -144.5337 | -144.5337 | -144.5337 | -144.5337 | -144.5337 | -144.5337 | -144.5337 | total interest | -1546.8254
Module purchases (OUT) | [21 empty] | -115.33 |  | -345.99 | [15 empty] | 43030.6014
Creditors
Total credit for loans | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28243.1471 | 28243.1471 | 28243.1471 | 28243.1471 | 28243.1471 | 28243.1471 | 28243.1471 | 28243.1471 | 28243.1471 | 44577.4268 | 44577.4268 | 44577.4268 | 44577.4268 | 44577.4268 | 44577.4268 | 44577.4268 | 44577.4268 | 44577.4268 | 44577.4268
Total credit recieved for modules | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 345.99 | 345.99 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OH | -23846.1538
Total credit given for modules | [21 empty] | 790.58 | 790.58 | 0 | [15 empty] | -461.32
Opening Balance | 0 | 0 | 0 | 0 | -2618.2692 | -2721.3942 | -3724.5192 | -5728.8462 | -5825.7212 | -6078.8462 | -8751.9231 | -8751.9231 | -8751.9231 | -8751.9231 | -8751.9231 | -8751.9231 | -9317.5481 | -10161.2981 | -15660.3365 | -16166.5865 | 9606.8626 | 7210.9627 | 6564.4648 | 5888.5168 | 3243.4569 | 2673.7589 | 1666.5609 | 971.863 | 592.79 | 16229.4109 | 15741.1272 | 15193.4684 | 9696.7712 | 8917.8625 | 6320.2038 | 2990.0931 | 2789.3094 | 2644.7757 |  | 24307.4738
OUT total | 0 | 0 | 0 | -2618.2692 | -103.125 | -1003.125 | -2004.3269 | -96.875 | -253.125 | -2673.0769 | 0 | 0 | 0 | 0 | 0 | -565.625 | -843.75 | -5499.0385 | -506.25 | -2469.698 | -2395.8999 | -910.028 | -675.948 | -3435.6399 | -569.698 | -1007.198 | -694.698 | -379.073 | -697.6587 | -488.2837 | -547.6587 | -5496.6972 | -778.9087 | -2597.6587 | -3330.1107 | -200.7837 | -144.5337 | -2642.6107
IN total | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28243.1471 | 0 | 263.53 | 0 | 790.58 | 0 | 0 | 0 | 0 | 16334.2796 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | int | -1546.8254
Closing Balance | 0 | 0 | 0 | -2618.2692 | -2721.3942 | -3724.5192 | -5728.8462 | -5825.7212 | -6078.8462 | -8751.9231 | -8751.9231 | -8751.9231 | -8751.9231 | -8751.9231 | -8751.9231 | -9317.5481 | -10161.2981 | -15660.3365 | -16166.5865 | 9606.8626 | 7210.9627 | 6564.4648 | 5888.5168 | 3243.4569 | 2673.7589 | 1666.5609 | 971.863 | 592.79 | 16229.4109 | 15741.1272 | 15193.4684 | 9696.7712 | 8917.8625 | 6320.2038 | 2990.0931 | 2789.3094 | 2644.7757 | 2.165 |  | 1546.8254
predicted
Week number | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38
Week dates | Sep. 30, 2019-Oct. 6, 2019 | Oct. 7, 2019-Oct. 13, 2019 | Oct. 14, 2019-Oct. 20, 2019 | Oct. 21, 2019-Oct. 27, 2019 | Oct. 28, 2019-Nov. 3, 2019 | Nov. 4, 2019-Nov. 10, 2019 | Nov. 11, 2019-Nov. 17, 2019 | Nov. 18, 2019-Nov. 24, 2019 | Nov. 25, 2019-Dec. 1, 2019 | Dec. 2, 2019-Dec. 8, 2019 | Dec. 9, 2019-Dec. 15, 2019 | Dec. 16, 2019-Dec. 22, 2019 | Dec. 23, 2019-Dec. 29, 2019 | Dec. 30, 2019-Jan. 5, 2020 | Jan. 6, 2020-Jan. 12, 2020 | Jan. 13, 2020-Jan. 19, 2020 | Jan. 20, 2020-Jan. 26, 2020 | Jan. 27, 2020-Feb. 2, 2020 | Feb. 3, 2020-Feb. 9, 2020 | Feb. 10, 2020-Feb. 16, 2020 | Feb. 17, 2020-Feb. 23, 2020 | Feb. 24, 2020-Mar. 1, 2020 | Mar. 2, 2020-Mar. 8, 2020 | Mar. 9, 2020-Mar. 15, 2020 | Mar. 16, 2020-Mar. 22, 2020 | Mar. 23, 2020-Mar. 29, 2020 | Mar. 30, 2020-Apr. 5, 2020 | Apr. 6, 2020-Apr. 12, 2020 | Apr. 13, 2020-Apr. 19, 2020 | Apr. 20, 2020-Apr. 26, 2020 | Apr. 27, 2020-May 3, 2020 | May 4, 2020-May 10, 2020 | May 11, 2020-May 17, 2020 | May 18, 2020-May 24, 2020 | May 25, 2020-May 31, 2020 | June 1, 2020-June 7, 2020 | June 8, 2020-June 14, 2020 | June 15, 2020-June 21, 2020
Term week | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | Christmas | Christmas | Christmas | Christmas | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | Easter | Easter | Easter | Easter | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10
Project Iteration Stage | Preparation | Preparation | Preparation | Preparation | Preparation | Preparation | Preparation | Preparation | Preparation | Preparation | Preparation | Preparation | Preparation | Preparation | Preparation | Preparation | Preparation | Preparation | Iteration 1, week 1 | Iteration 1, week 2 | Iteration 1, week 3 | Iteration 1, week 4 | Iteration 1, week 5 | Iteration 1, week 6 | Iteration 2, week 1 | Iteration 2, week 2 | Iteration 2, week 3 | Iteration 2, week 4 | Iteration 2, week 5 | Iteration 3, week 1 | Iteration 3, week 2 | Iteration 3, week 3 | Iteration 3, week 4 | Iteration 3, week 5 | Presentation preparation | Presentation & hand in
Predicted hours | 0 | 0 | 0 | 7 | 8.25 | 8.25 | 8.5 | 7.75 | 20.25 | 14 | 0 | 0 | 0 | 0 | 0 | 45.25 | 67.5 | 35 | 47.75 | 59 | 58.5 | 42.5 | 46 | 29.25 | 47.25 | 34.75 | 28.5 | 43.5 | 43.5 | 37.25 | 47.25 | 29.75 | 31 | 43.5 | 75.25 | 7 | 0 | 0
IN
Loans (IN) | [19 empty] | 28243.1471 | [8 empty] | 16334.2796
Module sales (IN)
OUT
Premises Rent |  |  |  | -2530.7692 |  |  | -1898.0769 |  |  | -1898.0769 | [7 empty] | -5061.5385 |  |  | -1898.0769 |  |  | -1898.0769 | [7 empty] | -5061.5385 |  |  | -1898.0769 |  |  | -1898.0769
Utilities Rent | [5 empty] | -300 |  |  |  | -200 | [9 empty] | -500 |  |  |  | -200 | [9 empty] | -500 |  |  |  | -200
IT infrastructure | [5 empty] | -600 |  |  |  | -400 | [9 empty] | -1000 |  |  |  | -400 | [9 empty] | -1000 |  |  |  | -400
Cost of Labour (12.5 GBP per hour) | 0 | 0 | 0 | -87.5 | -103.125 | -103.125 | -106.25 | -96.875 | -253.125 | -175 | 0 | 0 | 0 | 0 | 0 | -565.625 | -843.75 | -437.5 | -596.875 | -737.5 | -731.25 | -531.25 | -575 | -365.625 | -590.625 | -434.375 | -356.25 | -543.75 | -543.75 | -465.625 | -590.625 | -371.875 | -387.5 | -543.75 | -940.625 | -87.5 | 0 | 0
Weekly interest (16.86% APR) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -91.573 | -91.573 | -91.573 | -91.573 | -91.573 | -91.573 | -91.573 | -91.573 | -91.573 | -144.5337 | -144.5337 | -144.5337 | -144.5337 | -144.5337 | -144.5337 | -144.5337 | -144.5337 | -144.5337 | -144.5337
Module purchases (OUT) | [21 empty] | -100 |  | -300
Creditors
Total credit for loans | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28243.1471 | 28243.1471 | 28243.1471 | 28243.1471 | 28243.1471 | 28243.1471 | 28243.1471 | 28243.1471 | 28243.1471 | 44577.4268 | 44577.4268 | 44577.4268 | 44577.4268 | 44577.4268 | 44577.4268 | 44577.4268 | 44577.4268 | 44577.4268 | 44577.4268
Total credit for modules | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 300 | 300 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Opening Balance | 0 | 0 | 0 | 0 | -2618.2692 | -2721.3942 | -3724.5192 | -5728.8462 | -5825.7212 | -6078.8462 | -8751.9231 | -8751.9231 | -8751.9231 | -8751.9231 | -8751.9231 | -8751.9231 | -9317.5481 | -10161.2981 | -15660.3365 | -16257.2115 | 9656.8626 | 6935.9627 | 6213.1398 | 5546.5668 | 2291.2919 | 1609.0939 | 1083.1459 | 635.323 | -1.9327e-12 | 15645.9959 | 15035.8372 | 14300.6784 | 8722.7312 | 8190.6975 | 6002.4138 | 3019.1781 | 2787.1444 | 2642.6107
OUT total | 0 | 0 | 0 | -2618.2692 | -103.125 | -1003.125 | -2004.3269 | -96.875 | -253.125 | -2673.0769 | 0 | 0 | 0 | 0 | 0 | -565.625 | -843.75 | -5499.0385 | -596.875 | -2329.073 | -2720.8999 | -722.823 | -666.573 | -3255.2749 | -682.198 | -525.948 | -447.823 | -635.323 | -688.2837 | -610.1587 | -735.1587 | -5577.9472 | -532.0337 | -2188.2837 | -2983.2357 | -232.0337 | -144.5337 | -2642.6107
IN total | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28243.1471 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16334.2796 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Closing Balance | 0 | 0 | 0 | -2618.2692 | -2721.3942 | -3724.5192 | -5728.8462 | -5825.7212 | -6078.8462 | -8751.9231 | -8751.9231 | -8751.9231 | -8751.9231 | -8751.9231 | -8751.9231 | -9317.5481 | -10161.2981 | -15660.3365 | -16257.2115 | 9656.8626 | 6935.9627 | 6213.1398 | 5546.5668 | 2291.2919 | 1609.0939 | 1083.1459 | 635.323 | -1.9327e-12 | 15645.9959 | 15035.8372 | 14300.6784 | 8722.7312 | 8190.6975 | 6002.4138 | 3019.1781 | 2787.1444 | 2642.6107 | 1.0004e-11
| 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 90.625 | -50 | 275 | 351.325 | 341.95 | 952.165 | 1064.665 | 583.415 | 336.54 | 592.79 | 583.415 | 705.29 | 892.79 | 974.04 | 727.165 | 317.79 | -29.085 | 2.165 | 2.165 | 2.165
0
[34 empty] | 25.4232 | 100.6732

## Financial report 1
Week number | 18 | 19 | 20 | 21 |  | Week number | 18 | 19 | 20 | 21
Week dates | Jan. 27, 2020-Feb. 2, 2020 | Feb. 3, 2020-Feb. 9, 2020 | Feb. 10, 2020-Feb. 16, 2020 | Feb. 17, 2020-Feb. 23, 2020 |  | Week dates | Jan. 27, 2020-Feb. 2, 2020 | Feb. 3, 2020-Feb. 9, 2020 | Feb. 10, 2020-Feb. 16, 2020 | Feb. 17, 2020-Feb. 23, 2020
Term week | 4 | 5 | 6 | 7 |  | Term week | 4 | 5 | 6 | 7
Project Iteration Stage | Preparation | Iteration 1, week 1 | Iteration 1, week 2 | Iteration 1, week 3 |  | Project Iteration Stage | Preparation | Iteration 1, week 1 | Iteration 1, week 2 | Iteration 1, week 3
Weekly hours | 35 | 47.75 | 59 | 58.5 |  | Predicted hours | 35 | 47.75 | 59 | 58.5
IN | [5 empty] | Actual hours | 35 | 40.5 | 70.25
Loans |  |  | 28243.15 |  |  | IN
Module sales | [5 empty] | Loans |  |  | 28243.15
OUT | [5 empty] | Module sales
Premises Rent | -5061.54 |  |  | -1898.08 |  | OUT
Utilities Rent |  |  | -500 |  |  | Premises Rent | -5061.54 |  |  | -1898.08
IT infrastructure |  |  | -1000 |  |  | Utilities Rent |  |  | -500
Cost of Labour | -437.5 | -596.88 | -737.5 | -731.25 |  | IT infrastructure |  |  | -1000
Weekly interest | 0 | 0 | -91.57 | -91.57 |  | Cost of Labour | -437.5 | -506.25 | -878.13 | 0
Module purchases | [5 empty] | Weekly interest | 0 | 0 | -91.57 | -91.57
Creditors | [5 empty] | Module purchases
Long term loans | 0 | 0 | 28243.15 | 28243.15 |  | Creditors
Owed on contracts | 0 | 0 | 0 | 0 |  | Long term loans | 0 | 0 | 28243.15 | 28243.15
Opening Balance | -10161.3 | -15660.34 | -16257.21 | 9656.86 |  | Owed on contracts | 0 | 0 | 0 | 0
OUT total | -5499.04 | -596.88 | -2329.07 | -2720.9 |  | Opening Balance | -10161.3 | -15660.34 | -16166.59 | 9606.86
IN total | 0 | 0 | 28243.15 | 0 |  | OUT total | -5499.04 | -506.25 | -2469.7 | -1989.65
Closing Balance | -15660.34 | -16257.21 | 9656.86 | 6935.96 |  | IN total | 0 | 0 | 28243.15 | 0
[6 empty] | Closing Balance | -15660.34 | -16166.59 | 9606.86 | 7617.21
Project | User | 02/03/2020 | 02/04/2020 | 02/05/2020 | 02/06/2020 | 02/07/2020 | 02/08/2020 | 02/09/2020 | Total | Billable total | Project | Client | Description | Task | User | Email | Tags | Billable | Start Date | Start Time | End Date | End Time | Duration (h) | Duration (decimal) | Hourly Rate (GBP) | Amount (GBP)
Finance - SWEng Group 4 |  | 06:00:00 | 02:00:00 | 04:15:00 | 00:00:00 | 01:00:00 | 00:00:00 | 00:00:00 | 13:15:00 | 13:15:00 | Meetings | SWEng Group 4 | Group weekly meeting |  | Rea524 | rea524@york.ac.uk |  | Yes | 02/03/2020 | 09:00:00 AM | 02/03/2020 | 10:00:00 AM | 01:00:00 | 1 | 12.5 | 12.5
| Louis Newman | 05:00:00 | 02:00:00 | 04:15:00 | 00:00:00 | 01:00:00 | 00:00:00 | 00:00:00 | 12:15:00 | 12:15:00 | Administration | SWEng Group 4 | writing up minutes and formatting |  | Rea524 | rea524@york.ac.uk |  | Yes | 02/03/2020 | 10:00:00 AM | 02/03/2020 | 10:30:00 AM | 00:30:00 | 0.5 | 12.5 | 6.25
| Jm2285 | 01:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 01:00:00 | 01:00:00 | Meetings | SWEng Group 4 | Team meeting |  | Louis Newman | lifn501@york.ac.uk |  | Yes | 02/03/2020 | 11:00:00 AM | 02/03/2020 | 12:00:00 PM | 01:00:00 | 1 | 12.5 | 12.5
Meetings - SWEng Group 4 |  | 07:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 01:00:00 | 00:00:00 | 00:15:00 | 08:15:00 | 08:15:00 | Meetings | SWEng Group 4 | Group meeting |  | nathanbillis | ncab500@york.ac.uk |  | Yes | 02/03/2020 | 11:00:00 AM | 02/03/2020 | 12:00:00 PM | 01:00:00 | 1 | 12.5 | 12.5
| Jp1439 | 01:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:15:00 | 01:15:00 | 01:15:00 | Meetings | SWEng Group 4 | Team meeting |  | Jb2200 | jb2200@york.ac.uk |  | Yes | 02/03/2020 | 11:00:00 AM | 02/03/2020 | 12:00:00 PM | 01:00:00 | 1 | 12.5 | 12.5
| Louis Newman | 01:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 01:00:00 | 01:00:00 | Meetings | SWEng Group 4 | Team meeting |  | James Clawley | jc2421@york.ac.uk |  | Yes | 02/03/2020 | 11:00:00 AM | 02/03/2020 | 12:00:00 PM | 01:00:00 | 1 | 12.5 | 12.5
| Rea524 | 01:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 01:00:00 | 01:00:00 | Meetings | SWEng Group 4 | Team meeting |  | Jm2285 | jm2285@york.ac.uk |  | Yes | 02/03/2020 | 11:00:00 AM | 02/03/2020 | 12:00:00 PM | 01:00:00 | 1 | 12.5 | 12.5
| nathanbillis | 01:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 01:00:00 | 01:00:00 | Meetings | SWEng Group 4 | General Meeting |  | Jp1439 | jp1439@york.ac.uk |  | Yes | 02/03/2020 | 11:00:00 AM | 02/03/2020 | 12:00:00 PM | 01:00:00 | 1 | 12.5 | 12.5
| Jm2285 | 01:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 01:00:00 | 01:00:00 | Finance | SWEng Group 4 | Financial business plan - put together all team estimates and build up a financial picture of the project so far |  | Louis Newman | lifn501@york.ac.uk |  | Yes | 02/03/2020 | 01:00:00 PM | 02/03/2020 | 06:00:00 PM | 05:00:00 | 5 | 12.5 | 62.5
| Jb2200 | 01:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 01:00:00 | 01:00:00 | Finance | SWEng Group 4 | Improve the estimation of cost of firebase |  | Jm2285 | jm2285@york.ac.uk |  | Yes | 02/03/2020 | 04:30:00 PM | 02/03/2020 | 05:30:00 PM | 01:00:00 | 1 | 12.5 | 12.5
| James Clawley | 01:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 01:00:00 | 00:00:00 | 00:00:00 | 02:00:00 | 02:00:00 | Software | SWEng Group 4 | Working on getting side menu to work. And learning more about android studio | User story C34 | nathanbillis | ncab500@york.ac.uk |  | Yes | 02/04/2020 | 04:00:00 PM | 02/04/2020 | 05:45:00 PM | 01:45:00 | 1.75 | 12.5 | 21.88
Software - SWEng Group 4 |  | 00:00:00 | 01:45:00 | 00:00:00 | 09:00:00 | 03:00:00 | 00:00:00 | 00:00:00 | 13:45:00 | 13:45:00 | Finance | SWEng Group 4 | Financial business plan - add marketing elements and help Jun with estimates and attempt to make his storage plan a viable addition |  | Louis Newman | lifn501@york.ac.uk |  | Yes | 02/04/2020 | 06:00:00 PM | 02/04/2020 | 08:00:00 PM | 02:00:00 | 2 | 12.5 | 25
| Jp1439 | 00:00:00 | 00:00:00 | 00:00:00 | 03:00:00 | 01:00:00 | 00:00:00 | 00:00:00 | 04:00:00 | 04:00:00 | Design | SWEng Group 4 | Design spec 2 intro + design guidelines |  | Jb2200 | jb2200@york.ac.uk |  | Yes | 02/05/2020 | 02:00:00 AM | 02/05/2020 | 02:30:00 AM | 00:30:00 | 0.5 | 12.5 | 6.25
| Louis Newman | 00:00:00 | 00:00:00 | 00:00:00 | 02:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 02:00:00 | 02:00:00 | Marketing | SWEng Group 4 | marketing finance sheet |  | Rea524 | rea524@york.ac.uk |  | Yes | 02/05/2020 | 09:00:00 AM | 02/05/2020 | 09:45:00 AM | 00:45:00 | 0.75 | 12.5 | 9.38
| Rea524 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 02:00:00 | 00:00:00 | 00:00:00 | 02:00:00 | 02:00:00 | Finance | SWEng Group 4 | Financial business plan - Last couple of sections and analysis of spreadsheet |  | Louis Newman | lifn501@york.ac.uk |  | Yes | 02/05/2020 | 11:45:00 AM | 02/05/2020 | 02:00:00 PM | 02:15:00 | 2.25 | 12.5 | 28.13
| nathanbillis | 00:00:00 | 01:45:00 | 00:00:00 | 02:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 03:45:00 | 03:45:00 | Finance | SWEng Group 4 | Financial business plan - finishing off |  | Louis Newman | lifn501@york.ac.uk |  | Yes | 02/05/2020 | 03:00:00 PM | 02/05/2020 | 05:00:00 PM | 02:00:00 | 2 | 12.5 | 25
| James Clawley | 00:00:00 | 00:00:00 | 00:00:00 | 02:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 02:00:00 | 02:00:00 | Design | SWEng Group 4 | UML class diagram (Recipes + Recipe Presentations) |  | Jb2200 | jb2200@york.ac.uk |  | Yes | 02/05/2020 | 10:00:00 PM | 02/05/2020 | 10:30:00 PM | 00:30:00 | 0.5 | 12.5 | 6.25
Marketing - SWEng Group 4 |  | 00:00:00 | 00:00:00 | 00:45:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:45:00 | 00:45:00 | Software | SWEng Group 4 | Developed and added sidebar | User story C35 | James Clawley | jc2421@york.ac.uk |  | Yes | 02/06/2020 | 12:00:00 PM | 02/06/2020 | 01:00:00 PM | 01:00:00 | 1 | 12.5 | 12.5
| Rea524 | 00:00:00 | 00:00:00 | 00:45:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:45:00 | 00:45:00 | Software | SWEng Group 4 | software - Helping team get up and running with their own user stories |  | Louis Newman | lifn501@york.ac.uk |  | Yes | 02/06/2020 | 01:00:00 PM | 02/06/2020 | 03:00:00 PM | 02:00:00 | 2 | 12.5 | 25
Administration - SWEng Group 4 |  | 00:30:00 | 00:00:00 | 00:00:00 | 00:00:00 | 01:00:00 | 00:00:00 | 00:00:00 | 01:30:00 | 01:30:00 | Software | SWEng Group 4 | Finish the user story and send pull request and start user story C2(?) | User story C34 | nathanbillis | ncab500@york.ac.uk |  | Yes | 02/06/2020 | 01:00:00 PM | 02/06/2020 | 03:00:00 PM | 02:00:00 | 2 | 12.5 | 25
| Louis Newman | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 01:00:00 | 00:00:00 | 00:00:00 | 01:00:00 | 01:00:00 | Software | SWEng Group 4 | Building layout basis for recipe images | User story C1 | James Clawley | jc2421@york.ac.uk |  | Yes | 02/06/2020 | 01:00:00 PM | 02/06/2020 | 02:00:00 PM | 01:00:00 | 1 | 12.5 | 12.5
| Rea524 | 00:30:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:30:00 | 00:30:00 | Design | SWEng Group 4 | Design the recipe xml schema |  | Jm2285 | jm2285@york.ac.uk |  | Yes | 02/06/2020 | 01:00:00 PM | 02/06/2020 | 02:00:00 PM | 01:00:00 | 1 | 12.5 | 12.5
Research - SWEng Group 4 |  | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 01:00:00 | 00:00:00 | 00:00:00 | 01:00:00 | 01:00:00 | Software | SWEng Group 4 | Writing functionality for C3. Getting used to android studio | User story C3 | Jp1439 | jp1439@york.ac.uk |  | Yes | 02/06/2020 | 01:00:00 PM | 02/06/2020 | 04:00:00 PM | 03:00:00 | 3 | 12.5 | 37.5
| Rea524 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 01:00:00 | 00:00:00 | 00:00:00 | 01:00:00 | 01:00:00 | Finance | SWEng Group 4 | Finish and hand in business plan |  | Louis Newman | lifn501@york.ac.uk |  | Yes | 02/07/2020 | 08:00:00 AM | 02/07/2020 | 09:00:00 AM | 01:00:00 | 1 | 12.5 | 12.5
Design - SWEng Group 4 |  | 00:00:00 | 00:00:00 | 01:00:00 | 01:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 02:00:00 | 02:00:00 | Software | SWEng Group 4 | working on user story C20. set up new section for initial user customisation. | User story C20 | Rea524 | rea524@york.ac.uk |  | Yes | 02/07/2020 | 09:00:00 AM | 02/07/2020 | 11:00:00 AM | 02:00:00 | 2 | 12.5 | 25
| Jm2285 | 00:00:00 | 00:00:00 | 00:00:00 | 01:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 01:00:00 | 01:00:00 | Administration | SWEng Group 4 | XML Scheme meeting and prep |  | Louis Newman | lifn501@york.ac.uk |  | Yes | 02/07/2020 | 10:00:00 AM | 02/07/2020 | 11:00:00 AM | 01:00:00 | 1 | 12.5 | 12.5
| Jb2200 | 00:00:00 | 00:00:00 | 01:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 01:00:00 | 01:00:00 | Research | SWEng Group 4 | researched how firebase stores user information and how to customise settings |  | Rea524 | rea524@york.ac.uk |  | Yes | 02/07/2020 | 11:00:00 AM | 02/07/2020 | 12:00:00 PM | 01:00:00 | 1 | 12.5 | 12.5
TOTAL |  | 13:30:00 | 03:45:00 | 06:00:00 | 10:00:00 | 07:00:00 | 00:00:00 | 00:15:00 | 40:30:00 | 40:30:00 | Meetings | SWEng Group 4 | Team Meeting |  | James Clawley | jc2421@york.ac.uk |  | Yes | 02/07/2020 | 11:00:00 AM | 02/07/2020 | 12:00:00 PM | 01:00:00 | 1 | 12.5 | 12.5
[11 empty] | Software | SWEng Group 4 | Finishing functionality | User story C3 | Jp1439 | jp1439@york.ac.uk |  | Yes | 02/07/2020 | 11:00:00 AM | 02/07/2020 | 12:00:00 PM | 01:00:00 | 1 | 12.5 | 12.5
[9 empty] | total: | 40.5 | Meetings | SWEng Group 4 | Setting up meeting & reading Schema |  | Jp1439 | jp1439@york.ac.uk |  | Yes | 02/09/2020 | 11:15:00 AM | 02/09/2020 | 11:30:00 AM | 00:15:00 | 0.25 | 12.5 | 3.13
Assigned
Time |  | Software | Design | Testing | Meetings | Finance | Administration | Marketing | Research | Total
Project Manager | James Pearson | 4 |  |  | 1 |  | 2 |  |  | 7
Finance Manager | Louis Newman | 6 |  |  | 1 | 8 |  |  |  | 15
Desgin & Specification Manager | Joe Butler |  | 2.75 |  | 1 |  |  |  |  | 3.75
Lead Software Developer | James Clawley | 4 |  | 3 | 1 |  |  |  |  | 8
Testing & Integration Manager | Nathan Billis | 4 |  |  | 1 |  |  |  |  | 5
Marketing Manager | Becky Anderson | 5 |  |  | 1 | 1 |  |  |  | 7
XML & Server Manager | Jun Ma |  |  |  | 1 | 1 |  |  |  | 2
Actual | [9 empty] | 47.75
Time |  | Software | Design | Testing | Meetings | Finance | Administration |  | Research | Total
Project Manager | James Pearson | 4 |  |  | 1 |  | 0.25 |  |  | 5.25
Finance Manager | Louis Newman | 2 |  |  | 1 | 12.25 | 1 |  |  | 16.25
Desgin & Specification Manager | Joe Butler |  | 1 |  | 1 |  |  |  |  | 2
Lead Software Developer | James Clawley | 2 | 1 |  | 1 |  |  |  |  | 4
Testing & Integration Manager | Nathan Billis | 3.75 |  |  | 1 |  |  |  |  | 4.75
Marketing Manager | Becky Anderson | 2 |  |  | 1 |  | 0.5 | 0.75 | 1 | 5.25
XML & Server Manager | Jun Ma |  | 1 |  | 1 | 1 |  |  |  | 3
40.5
Project | User | 02/10/2020 | 02/11/2020 | 02/12/2020 | 02/13/2020 | 02/14/2020 | 02/15/2020 | 02/16/2020 | Total | Billable total | Project | Client | Description | Task | User | Email | Tags | Billable | Start Date | Start Time | End Date | End Time | Duration (h) | Duration (decimal) | Hourly Rate (GBP) | Amount (GBP)
Finance - SWEng Group 4 |  | 00:30:00 | 00:00:00 | 01:30:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 02:00:00 | 02:00:00 | Meetings | SWEng Group 4 | Group weekly meeting |  | Rea524 | rea524@york.ac.uk |  | Yes | 02/10/2020 | 09:00:00 AM | 02/10/2020 | 10:00:00 AM | 01:00:00 | 1 | 12.5 | 12.5
| Louis Newman | 00:30:00 | 00:00:00 | 01:30:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 02:00:00 | 02:00:00 | Marketing | SWEng Group 4 | Marketing section for group tender presentation |  | Rea524 | rea524@york.ac.uk |  | Yes | 02/10/2020 | 10:00:00 AM | 02/10/2020 | 11:00:00 AM | 01:00:00 | 1 | 12.5 | 12.5
Meetings - SWEng Group 4 |  | 09:00:00 | 00:00:00 | 00:00:00 | 01:00:00 | 02:00:00 | 00:00:00 | 00:00:00 | 12:00:00 | 12:00:00 | Meetings | SWEng Group 4 | Group meeting and discussion of UML Diagrams |  | nathanbillis | ncab500@york.ac.uk |  | Yes | 02/10/2020 | 10:00:00 AM | 02/10/2020 | 12:00:00 PM | 02:00:00 | 2 | 12.5 | 25
| Jp1439 | 01:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 01:00:00 | 01:00:00 | Meetings | SWEng Group 4 | Design and Team meetings |  | Jb2200 | jb2200@york.ac.uk |  | Yes | 02/10/2020 | 10:00:00 AM | 02/10/2020 | 12:00:00 PM | 02:00:00 | 2 | 12.5 | 25
| Louis Newman | 01:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 01:00:00 | 01:00:00 | Finance | SWEng Group 4 | Weekly finances |  | Louis Newman | lifn501@york.ac.uk |  | Yes | 02/10/2020 | 10:30:00 AM | 02/10/2020 | 11:00:00 AM | 00:30:00 | 0.5 | 12.5 | 6.25
| Rea524 | 01:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 01:00:00 | 01:00:00 | Design | SWEng Group 4 | UML diagram design |  | James Clawley | jc2421@york.ac.uk |  | Yes | 02/10/2020 | 10:30:00 AM | 02/10/2020 | 11:00:00 AM | 00:30:00 | 0.5 | 12.5 | 6.25
| nathanbillis | 02:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 02:00:00 | 02:00:00 | Meetings | SWEng Group 4 | Group meeting |  | Louis Newman | lifn501@york.ac.uk |  | Yes | 02/10/2020 | 11:00:00 AM | 02/10/2020 | 12:00:00 PM | 01:00:00 | 1 | 12.5 | 12.5
| Jm2285 | 01:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 01:00:00 | 01:00:00 | Meetings | SWEng Group 4 | Team meeting |  | James Clawley | jc2421@york.ac.uk |  | Yes | 02/10/2020 | 11:00:00 AM | 02/10/2020 | 12:00:00 PM | 01:00:00 | 1 | 12.5 | 12.5
| Jb2200 | 02:00:00 | 00:00:00 | 00:00:00 | 01:00:00 | 02:00:00 | 00:00:00 | 00:00:00 | 05:00:00 | 05:00:00 | Meetings | SWEng Group 4 | team meeting |  | Jm2285 | jm2285@york.ac.uk |  | Yes | 02/10/2020 | 11:00:00 AM | 02/10/2020 | 12:00:00 PM | 01:00:00 | 1 | 12.5 | 12.5
| James Clawley | 01:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 01:00:00 | 01:00:00 | Meetings | SWEng Group 4 | General Meeting |  | Jp1439 | jp1439@york.ac.uk |  | Yes | 02/10/2020 | 11:00:00 AM | 02/10/2020 | 12:00:00 PM | 01:00:00 | 1 | 12.5 | 12.5
Software - SWEng Group 4 |  | 00:00:00 | 03:00:00 | 03:00:00 | 00:00:00 | 02:45:00 | 03:00:00 | 00:30:00 | 12:15:00 | 12:15:00 | Design | SWEng Group 4 | Updated XML design themes for Android studio, edited recipe uml class diagram and started editing uml login class diagram |  | Jb2200 | jb2200@york.ac.uk |  | Yes | 02/10/2020 | 04:00:00 PM | 02/10/2020 | 05:00:00 PM | 01:00:00 | 1 | 12.5 | 12.5
| Jp1439 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 02:00:00 | 02:00:00 | 00:00:00 | 04:00:00 | 04:00:00 | Design | SWEng Group 4 | Updated Trello with new UML specification attachment information |  | Jb2200 | jb2200@york.ac.uk |  | Yes | 02/10/2020 | 07:00:00 PM | 02/10/2020 | 07:15:00 PM | 00:15:00 | 0.25 | 12.5 | 3.13
| Louis Newman | 00:00:00 | 03:00:00 | 03:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 06:00:00 | 06:00:00 | Administration | SWEng Group 4 | Updated presentation PowerPoint slides for look & feel, iterations and platform |  | Jb2200 | jb2200@york.ac.uk |  | Yes | 02/11/2020 | 02:30:00 AM | 02/11/2020 | 03:00:00 AM | 00:30:00 | 0.5 | 12.5 | 6.25
| Rea524 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:30:00 | 00:30:00 | 00:30:00 | Software | SWEng Group 4 | Setting up link to firestore database and build of local data structures | User story A2 | Louis Newman | lifn501@york.ac.uk |  | Yes | 02/11/2020 | 07:00:00 PM | 02/11/2020 | 10:00:00 PM | 03:00:00 | 3 | 12.5 | 37.5
| James Clawley | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:45:00 | 01:00:00 | 00:00:00 | 01:45:00 | 01:45:00 | Tender presentation | SWEng Group 4 | Marketing section of presentation& logo design |  | Rea524 | rea524@york.ac.uk |  | Yes | 02/12/2020 | 09:00:00 AM | 02/12/2020 | 10:00:00 AM | 01:00:00 | 1 | 12.5 | 12.5
Testing - SWEng Group 4 |  | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 01:45:00 | 00:00:00 | 01:45:00 | 01:45:00 | Finance | SWEng Group 4 | Putting together and organising finances for display in tender presentation |  | Louis Newman | lifn501@york.ac.uk |  | Yes | 02/12/2020 | 11:30:00 AM | 02/12/2020 | 01:00:00 PM | 01:30:00 | 1.5 | 12.5 | 18.75
| nathanbillis | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 01:45:00 | 00:00:00 | 01:45:00 | 01:45:00 | Tender presentation | SWEng Group 4 | Meeting to discuss presentation |  | nathanbillis | ncab500@york.ac.uk |  | Yes | 02/12/2020 | 12:00:00 PM | 02/12/2020 | 01:00:00 PM | 01:00:00 | 1 | 12.5 | 12.5
Marketing - SWEng Group 4 |  | 01:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 01:00:00 | 01:00:00 | Tender presentation | SWEng Group 4 | Presentation planning |  | James Clawley | jc2421@york.ac.uk |  | Yes | 02/12/2020 | 12:00:00 PM | 02/12/2020 | 02:00:00 PM | 02:00:00 | 2 | 12.5 | 25
| Rea524 | 01:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 01:00:00 | 01:00:00 | Tender presentation | SWEng Group 4 | Discussion about presentation |  | Jm2285 | jm2285@york.ac.uk |  | Yes | 02/12/2020 | 12:00:00 PM | 02/12/2020 | 01:30:00 PM | 01:30:00 | 1.5 | 12.5 | 18.75
Administration - SWEng Group 4 |  | 00:00:00 | 00:30:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:30:00 | 00:30:00 | Tender presentation | SWEng Group 4 | Presentation prep |  | Jp1439 | jp1439@york.ac.uk |  | Yes | 02/12/2020 | 12:00:00 PM | 02/12/2020 | 02:00:00 PM | 02:00:00 | 2 | 12.5 | 25
| Jb2200 | 00:00:00 | 00:30:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:30:00 | 00:30:00 | Software | SWEng Group 4 | Finished and commented full stories for A1 and A2 | User story A1 | Louis Newman | lifn501@york.ac.uk |  | Yes | 02/12/2020 | 07:00:00 PM | 02/12/2020 | 10:00:00 PM | 03:00:00 | 3 | 12.5 | 37.5
Research - SWEng Group 4 |  | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 01:00:00 | 00:00:00 | 00:00:00 | 01:00:00 | 01:00:00 | Design | SWEng Group 4 | Made wireframe models for recipe screens (both free and paid). Produced UI diagrams for the mealplanner, including multiple versions and different screens. Updated UML recipe diagram briefly to include new meal planner information. |  | Jb2200 | jb2200@york.ac.uk |  | Yes | 02/12/2020 | 07:00:00 PM | 02/12/2020 | 11:00:00 PM | 04:00:00 | 4 | 12.5 | 50
| James Clawley | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 01:00:00 | 00:00:00 | 00:00:00 | 01:00:00 | 01:00:00 | Tender presentation | SWEng Group 4 | Working on presentation |  | nathanbillis | ncab500@york.ac.uk |  | Yes | 02/12/2020 | 07:24:00 PM | 02/12/2020 | 08:24:00 PM | 01:00:00 | 1 | 12.5 | 12.5
Design - SWEng Group 4 |  | 01:45:00 | 00:00:00 | 04:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 05:45:00 | 05:45:00 | Tender presentation | SWEng Group 4 | tender presentation work |  | Rea524 | rea524@york.ac.uk |  | Yes | 02/13/2020 | 09:00:00 AM | 02/13/2020 | 11:00:00 AM | 02:00:00 | 2 | 12.5 | 25
| Jb2200 | 01:15:00 | 00:00:00 | 04:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 05:15:00 | 05:15:00 | Meetings | SWEng Group 4 | Presentation meeting |  | Jb2200 | jb2200@york.ac.uk |  | Yes | 02/13/2020 | 12:20:00 PM | 02/13/2020 | 01:20:00 PM | 01:00:00 | 1 | 12.5 | 12.5
| James Clawley | 00:30:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:30:00 | 00:30:00 | Tender presentation | SWEng Group 4 | Worked on tender presentation |  | Louis Newman | lifn501@york.ac.uk |  | Yes | 02/13/2020 | 01:00:00 PM | 02/13/2020 | 03:00:00 PM | 02:00:00 | 2 | 12.5 | 25
Tender presentation - SWEng Group 4 |  | 00:00:00 | 00:00:00 | 08:30:00 | 13:00:00 | 12:00:00 | 00:30:00 | 00:00:00 | 34:00:00 | 34:00:00 | Tender presentation | SWEng Group 4 | Group meeting for presentation and meeting |  | nathanbillis | ncab500@york.ac.uk |  | Yes | 02/13/2020 | 01:00:00 PM | 02/13/2020 | 03:00:00 PM | 02:00:00 | 2 | 12.5 | 25
| Jp1439 | 00:00:00 | 00:00:00 | 02:00:00 | 02:00:00 | 02:00:00 | 00:00:00 | 00:00:00 | 06:00:00 | 06:00:00 | Tender presentation | SWEng Group 4 | Presentation planning |  | James Clawley | jc2421@york.ac.uk |  | Yes | 02/13/2020 | 01:00:00 PM | 02/13/2020 | 03:00:00 PM | 02:00:00 | 2 | 12.5 | 25
| Louis Newman | 00:00:00 | 00:00:00 | 00:00:00 | 03:00:00 | 02:00:00 | 00:00:00 | 00:00:00 | 05:00:00 | 05:00:00 | Tender presentation | SWEng Group 4 | Discussion about presentation |  | Jm2285 | jm2285@york.ac.uk |  | Yes | 02/13/2020 | 01:00:00 PM | 02/13/2020 | 03:00:00 PM | 02:00:00 | 2 | 12.5 | 25
| Rea524 | 00:00:00 | 00:00:00 | 01:00:00 | 02:00:00 | 02:00:00 | 00:30:00 | 00:00:00 | 05:30:00 | 05:30:00 | Tender presentation | SWEng Group 4 | Presentation prep |  | Jp1439 | jp1439@york.ac.uk |  | Yes | 02/13/2020 | 01:00:00 PM | 02/13/2020 | 03:00:00 PM | 02:00:00 | 2 | 12.5 | 25
| nathanbillis | 00:00:00 | 00:00:00 | 02:00:00 | 02:00:00 | 02:00:00 | 00:00:00 | 00:00:00 | 06:00:00 | 06:00:00 | Tender presentation | SWEng Group 4 | worked on tender pres |  | Louis Newman | lifn501@york.ac.uk |  | Yes | 02/13/2020 | 04:00:00 PM | 02/13/2020 | 05:00:00 PM | 01:00:00 | 1 | 12.5 | 12.5
| Jm2285 | 00:00:00 | 00:00:00 | 01:30:00 | 02:00:00 | 02:00:00 | 00:00:00 | 00:00:00 | 05:30:00 | 05:30:00 | Tender presentation | SWEng Group 4 | group work on presentation |  | Rea524 | rea524@york.ac.uk |  | Yes | 02/14/2020 | 09:00:00 AM | 02/14/2020 | 11:00:00 AM | 02:00:00 | 2 | 12.5 | 25
| James Clawley | 00:00:00 | 00:00:00 | 02:00:00 | 02:00:00 | 02:00:00 | 00:00:00 | 00:00:00 | 06:00:00 | 06:00:00 | Tender presentation | SWEng Group 4 | Run through of tender presentation |  | Louis Newman | lifn501@york.ac.uk |  | Yes | 02/14/2020 | 10:00:00 AM | 02/14/2020 | 12:00:00 PM | 02:00:00 | 2 | 12.5 | 25
TOTAL |  | 12:15:00 | 03:30:00 | 17:00:00 | 14:00:00 | 17:45:00 | 05:15:00 | 00:30:00 | 70:15:00 | 70:15:00 | Tender presentation | SWEng Group 4 | Group meeting to discuss presention |  | nathanbillis | ncab500@york.ac.uk |  | Yes | 02/14/2020 | 10:00:00 AM | 02/14/2020 | 12:00:00 PM | 02:00:00 | 2 | 12.5 | 25
[11 empty] | Meetings | SWEng Group 4 | Presentation meeting and final mock presentations + timings. |  | Jb2200 | jb2200@york.ac.uk |  | Yes | 02/14/2020 | 10:00:00 AM | 02/14/2020 | 12:00:00 PM | 02:00:00 | 2 | 12.5 | 25
[9 empty] | Total hours: | 70.25 | Tender presentation | SWEng Group 4 | Presentation planning |  | James Clawley | jc2421@york.ac.uk |  | Yes | 02/14/2020 | 10:00:00 AM | 02/14/2020 | 12:00:00 PM | 02:00:00 | 2 | 12.5 | 25
[11 empty] | Tender presentation | SWEng Group 4 | rehearse presentation and discussion about questions |  | Jm2285 | jm2285@york.ac.uk |  | Yes | 02/14/2020 | 10:00:00 AM | 02/14/2020 | 12:00:00 PM | 02:00:00 | 2 | 12.5 | 25
[11 empty] | Tender presentation | SWEng Group 4 | Presentation prep |  | Jp1439 | jp1439@york.ac.uk |  | Yes | 02/14/2020 | 10:00:00 AM | 02/14/2020 | 12:00:00 PM | 02:00:00 | 2 | 12.5 | 25
Assigned | [10 empty] | Software | SWEng Group 4 | Setting up scroll views to accept C3 when merging | User story C1 | James Clawley | jc2421@york.ac.uk |  | Yes | 02/14/2020 | 08:00:00 PM | 02/14/2020 | 08:45:00 PM | 00:45:00 | 0.75 | 12.5 | 9.38
Time |  | Software | Design | Testing | Meetings | Finance | Administration | Marketing | Tender Presentation | Total | Software | SWEng Group 4 | Changing from Activity to Dialog Fragmnet | User story C3 | Jp1439 | jp1439@york.ac.uk |  | Yes | 02/14/2020 | 08:00:00 PM | 02/14/2020 | 10:00:00 PM | 02:00:00 | 2 | 12.5 | 25
Project Manager | James Pearson |  |  |  | 1 |  | 2 |  | 6 | 9 | Research | SWEng Group 4 | Firebase documentation |  | James Clawley | jc2421@york.ac.uk |  | Yes | 02/14/2020 | 08:45:00 PM | 02/14/2020 | 09:45:00 PM | 01:00:00 | 1 | 12.5 | 12.5
Finance Manager | Louis Newman |  |  |  | 1 | 2 | 3 |  | 6 | 12 | Tender presentation | SWEng Group 4 | Personal presentation practice |  | Rea524 | rea524@york.ac.uk |  | Yes | 02/15/2020 | 09:00:00 AM | 02/15/2020 | 09:30:00 AM | 00:30:00 | 0.5 | 12.5 | 6.25
Desgin & Specification Manager | Joe Butler |  |  |  | 1 |  |  |  | 6 | 7 | Software | SWEng Group 4 | Getting tabs to work again, trying to Unit test fragments | User story C3 | Jp1439 | jp1439@york.ac.uk |  | Yes | 02/15/2020 | 09:00:00 AM | 02/15/2020 | 11:00:00 AM | 02:00:00 | 2 | 12.5 | 25
Lead Software Developer | James Clawley |  |  |  | 1 |  | 3 |  | 6 | 10 | Software | SWEng Group 4 | Programmed images being pulled from Firebase servers | User story C1 | James Clawley | jc2421@york.ac.uk |  | Yes | 02/15/2020 | 01:00:00 PM | 02/15/2020 | 02:00:00 PM | 01:00:00 | 1 | 12.5 | 12.5
Testing & Integration Manager | Nathan Billis |  |  |  | 1 |  |  |  | 6 | 7 | Testing | SWEng Group 4 | Testing and peer review of A1 A2 user stories and merging into the master |  | nathanbillis | ncab500@york.ac.uk |  | Yes | 02/15/2020 | 02:30:00 PM | 02/15/2020 | 04:15:00 PM | 01:45:00 | 1.75 | 12.5 | 21.88
Marketing Manager | Becky Anderson |  |  |  | 1 |  |  |  | 6 | 7 | Software | SWEng Group 4 | Redesigned Filter page, & researched firebase boolean connections | User story C20 | Rea524 | rea524@york.ac.uk |  | Yes | 02/16/2020 | 09:00:00 AM | 02/16/2020 | 09:30:00 AM | 00:30:00 | 0.5 | 12.5 | 6.25
XML & Server Manager | Jun Ma |  |  |  | 1 |  |  |  | 6 | 7
Actual | [8 empty] | Week total: | 59
Time |  | Software | Design | Testing | Meetings | Finance | Administration | Marketing | Tender Presentation | Total
Project Manager | James Pearson | 4 |  |  | 1 |  |  |  | 6 | 11
Finance Manager | Louis Newman | 6 |  |  | 1 | 2 |  |  | 5 | 14
Desgin & Specification Manager | Joe Butler |  | 7.75 |  | 1 |  |  |  | 2 | 10.75
Lead Software Developer | James Clawley | 2.75 | 0.5 |  | 1 |  |  |  | 6 | 10.25
Testing & Integration Manager | Nathan Billis |  | 1 | 1.75 | 1 |  |  |  | 6 | 9.75
Marketing Manager | Becky Anderson | 0.5 |  |  | 1 |  |  | 1 | 5.5 | 8
XML & Server Manager | Jun Ma |  |  |  | 1 |  |  |  | 5.5 | 6.5
[9 empty] | Week total: | 70.25
Assigned
Time |  | Software | Design | Testing | Meetings | Finance | Administration | Marketing | Research | Total
Project Manager | James Pearson | 4 |  |  | 1 |  | 2 |  |  | 7
Finance Manager | Louis Newman | 6 |  |  | 1 | 8 |  |  |  | 15
Desgin & Specification Manager | Joe Butler |  | 2.75 |  | 1 |  |  |  |  | 3.75
Lead Software Developer | James Clawley | 4 |  | 3 | 1 |  |  |  |  | 8
Testing & Integration Manager | Nathan Billis | 4 |  |  | 1 |  |  |  |  | 5
Marketing Manager | Becky Anderson | 5 |  |  | 1 | 1 |  |  |  | 7
XML & Server Manager | Jun Ma |  |  |  | 1 | 1 |  |  |  | 2
Actual | [8 empty] | Week total: | 47.75
Time |  | Software | Design | Testing | Meetings | Finance | Administration | Marketing | Research | Total
Project Manager | James Pearson | 4 |  |  | 1 |  | 0.25 |  |  | 5.25
Finance Manager | Louis Newman | 2 |  |  | 1 | 12.25 | 1 |  |  | 16.25
Desgin & Specification Manager | Joe Butler |  | 1 |  | 1 |  |  |  |  | 2
Lead Software Developer | James Clawley | 2 | 1 |  | 1 |  |  |  |  | 4
Testing & Integration Manager | Nathan Billis | 3.75 |  |  | 1 |  |  |  |  | 4.75
Marketing Manager | Becky Anderson | 2 |  |  | 1 |  | 0.5 | 0.75 | 1 | 5.25
XML & Server Manager | Jun Ma |  | 1 |  | 1 | 1 |  |  |  | 3
[9 empty] | Week total: | 40.5

## Financal report 2
Version control: 1.0 - 03/03/2020
Financial Report II | Date: 03/03/2020 | SWEng Group 4
Author: | Codev Financial Manager | Louis Newman
Week number | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23
Week dates | Sep. 30, 2019-Oct. 6, 2019 | Oct. 7, 2019-Oct. 13, 2019 | Oct. 14, 2019-Oct. 20, 2019 | Oct. 21, 2019-Oct. 27, 2019 | Oct. 28, 2019-Nov. 3, 2019 | Nov. 4, 2019-Nov. 10, 2019 | Nov. 11, 2019-Nov. 17, 2019 | Nov. 18, 2019-Nov. 24, 2019 | Nov. 25, 2019-Dec. 1, 2019 | Dec. 2, 2019-Dec. 8, 2019 | Dec. 9, 2019-Dec. 15, 2019 | Dec. 16, 2019-Dec. 22, 2019 | Dec. 23, 2019-Dec. 29, 2019 | Dec. 30, 2019-Jan. 5, 2020 | Jan. 6, 2020-Jan. 12, 2020 | Jan. 13, 2020-Jan. 19, 2020 | Jan. 20, 2020-Jan. 26, 2020 | Jan. 27, 2020-Feb. 2, 2020 | Feb. 3, 2020-Feb. 9, 2020 | Feb. 10, 2020-Feb. 16, 2020 | Feb. 17, 2020-Feb. 23, 2020 | Feb. 24, 2020-Mar. 1, 2020 | Mar. 2, 2020-Mar. 8, 2020
Term week | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | Christmas | Christmas | Christmas | Christmas | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9
Project Iteration Stage | Preparation | Preparation | Preparation | Preparation | Preparation | Preparation | Preparation | Preparation | Preparation | Preparation | Preparation | Preparation | Preparation | Preparation | Preparation | Preparation | Preparation | Preparation | Iteration 1, week 1 | Iteration 1, week 2 | Iteration 1, week 3 | Iteration 1, week 4 | Iteration 1, week 5
Predicted weekly hours | 0 | 0 | 0 | 7 | 8.25 | 8.25 | 8.5 | 7.75 | 20.25 | 14 | 0 | 0 | 0 | 0 | 0 | 45.25 | 67.5 | 35 | 47.75 | 59 | 58.5 | 42.5 | 46
Actual weekly hours | 0 | 0 | 0 | 7 | 8.25 | 8.25 | 8.5 | 7.75 | 20.25 | 14 | 0 | 0 | 0 | 0 | 0 | 45.25 | 67.5 | 35 | 40.5 | 70.25 | 32.5 | 55.75 | Current week
IN
Loans (IN) | [19 empty] | 28243.1471
Module sales (IN) | [21 empty] | 263.53
OUT
Premises Rent |  |  |  | -2530.7692 |  |  | -1898.0769 |  |  | -1898.0769 | [7 empty] | -5061.5385 |  |  | -1898.0769
Utilities Rent | [5 empty] | -300 |  |  |  | -200 | [9 empty] | -500
IT infrastructure | [5 empty] | -600 |  |  |  | -400 | [9 empty] | -1000
Cost of Labour (12.5 GBP per hour) | 0 | 0 | 0 | -87.5 | -103.125 | -103.125 | -106.25 | -96.875 | -253.125 | -175 | 0 | 0 | 0 | 0 | 0 | -565.625 | -843.75 | -437.5 | -506.25 | -878.125 | -406.25 | -696.875 | 0
Weekly interest (16.86% APR) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -91.573 | -91.573 | -91.573 | -91.573
Module purchases (OUT) | [21 empty] | -115.33
Creditors
Total credit for loans | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28243.1471 | 28243.1471 | 28243.1471 | 28243.1471
Total credit recieved for modules | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 345.99 | 345.99
Total credit given for modules | [21 empty] | 790.58 | 790.58
Opening Balance | 0 | 0 | 0 | 0 | -2618.2692 | -2721.3942 | -3724.5192 | -5728.8462 | -5825.7212 | -6078.8462 | -8751.9231 | -8751.9231 | -8751.9231 | -8751.9231 | -8751.9231 | -8751.9231 | -9317.5481 | -10161.2981 | -15660.3365 | -16166.5865 | 9606.8626 | 7210.9627 | 6570.7148
OUT total | 0 | 0 | 0 | -2618.2692 | -103.125 | -1003.125 | -2004.3269 | -96.875 | -253.125 | -2673.0769 | 0 | 0 | 0 | 0 | 0 | -565.625 | -843.75 | -5499.0385 | -506.25 | -2469.698 | -2395.8999 | -903.778 | -91.573
IN total | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28243.1471 | 0 | 263.53 | 0
Closing Balance | 0 | 0 | 0 | -2618.2692 | -2721.3942 | -3724.5192 | -5728.8462 | -5825.7212 | -6078.8462 | -8751.9231 | -8751.9231 | -8751.9231 | -8751.9231 | -8751.9231 | -8751.9231 | -9317.5481 | -10161.2981 | -15660.3365 | -16166.5865 | 9606.8626 | 7210.9627 | 6570.7148 | 6479.1418
Estimated time - Week 21
Role | Name | Software | Design | Testing | Meetings | Finance | Administration | Total
Project Manager | James Pearson |  |  |  | 1 |  | 2 | 3
Finance Manager | Louis Newman | 19 |  |  | 1 | 2 |  | 22
Design & Specification Manager | Joe Butler | 10 | 4.75 |  | 1 |  |  | 15.75
Lead Software Developer | James Clawley |  |  |  | 1 |  |  | 1
Testing & Integration Manager | Nathan Billis |  |  | 4.75 | 1 |  |  | 5.75
Marketing Manager | Becky Anderson |  |  |  | 1 |  |  | 1
XML & Server Manager | Jun Ma | 9 |  |  | 1 |  |  | 10
[7 empty] | Total: | 58.5
Reason for predicted hour distribution: | From the stories required for completion in this week, the person taking lead on each of them was assiged the full duration for them to delegate where appropriate.
Actual timesheet - Week 21
Project | User | 02/17/2020 | 02/18/2020 | 02/19/2020 | 02/20/2020 | 02/21/2020 | 02/22/2020 | 02/23/2020 | Total | Billable Total
Finance - SWEng Group 4 |  | 00:00:00 | 00:00:00 | 02:00:00 | 01:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 03:00:00 | 03:00:00
| Louis Newman | 00:00:00 | 00:00:00 | 02:00:00 | 01:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 03:00:00 | 03:00:00
Meetings - SWEng Group 4 |  | 05:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 05:00:00 | 05:00:00
| Jp1439 | 01:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 01:00:00 | 01:00:00
| Louis Newman | 01:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 01:00:00 | 01:00:00
| Rea524 | 01:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 01:00:00 | 01:00:00
| nathanbillis | 01:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 01:00:00 | 01:00:00
| Jm2285 | 01:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 01:00:00 | 01:00:00
Software - SWEng Group 4 |  | 00:00:00 | 00:00:00 | 00:00:00 | 05:00:00 | 03:00:00 | 01:30:00 | 05:45:00 | 15:15:00 | 15:15:00
| Jp1439 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 01:30:00 | 00:30:00 | 02:00:00 | 02:00:00
| Louis Newman | 00:00:00 | 00:00:00 | 00:00:00 | 01:00:00 | 00:00:00 | 00:00:00 | 01:30:00 | 02:30:00 | 02:30:00
| Rea524 | 00:00:00 | 00:00:00 | 00:00:00 | 02:00:00 | 00:00:00 | 00:00:00 | 00:45:00 | 02:45:00 | 02:45:00
| Jb2200 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 03:00:00 | 03:00:00 | 03:00:00
| James Clawley | 00:00:00 | 00:00:00 | 00:00:00 | 02:00:00 | 03:00:00 | 00:00:00 | 00:00:00 | 05:00:00 | 05:00:00
Administration - SWEng Group 4 |  | 00:00:00 | 02:00:00 | 01:00:00 | 00:00:00 | 00:30:00 | 01:00:00 | 00:00:00 | 04:30:00 | 04:30:00
| Jp1439 | 00:00:00 | 02:00:00 | 01:00:00 | 00:00:00 | 00:00:00 | 01:00:00 | 00:00:00 | 04:00:00 | 04:00:00
| Louis Newman | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:30:00 | 00:00:00 | 00:00:00 | 00:30:00 | 00:30:00
Design - SWEng Group 4 |  | 00:00:00 | 00:00:00 | 00:00:00 | 00:45:00 | 00:00:00 | 02:00:00 | 02:00:00 | 04:45:00 | 04:45:00
| Jm2285 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 02:00:00 | 02:00:00 | 04:00:00 | 0:00 | No proof of any work completed
| Jb2200 | 00:00:00 | 00:00:00 | 00:00:00 | 00:45:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:45:00 | 00:45:00
Tender presentation - SWEng Group 4 |  | 04:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 04:00:00 | 04:00:00
| Louis Newman | 01:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 01:00:00 | 01:00:00
| Rea524 | 01:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 01:00:00 | 01:00:00
| Jm2285 | 01:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 01:00:00 | 01:00:00
| James Clawley | 01:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 01:00:00 | 01:00:00
TOTAL |  | 09:00:00 | 02:00:00 | 03:00:00 | 06:45:00 | 03:30:00 | 04:30:00 | 07:45:00 | 36:30:00 | 36.30.00
[9 empty] | Total billable: | 32.5 | Difference to predicted: | 26
Notes on labour for week 21: | Comment on hour dispersion: | Some stories within this week relied on stories from previous weeks being completed. Due to this lack some were put on hold and others were completed in less time than was predicted, this led to the team having 22 hours spare at the end of the week that would be required to finish the stories that have been put on hold.
| Alterations from this prediction: | Jun, our XML & Server Manager, took the story C18, this story was found to be far from his capabilities, with the application of pair programming this was still found to be beyond possible scope and Jun was pulled off this story and the hours were re-distributed to myself, Louis, our Finance Manager. Jun has been tasked with a new story taken from iteration 3 in order to give him a viable starting point with Android programming.
| Comment on rejected hours: | Jun had input four hours of work for the design of C18, when asked to show the group evidence of this design he was found to have nothing to show and be lacking in the download of either Github or the full download of Android Studio. It is for this reason; those four hours were rejected by the team lead and Jun was assigned Louis as a pair-programming partner to deal with C18 as a pair. This was the session where it was found this story was beyond Jun's capabilities and pair-programming with such a complex story was not a good idea, leading to Jun being assigned an easier story to get him started with programming with Java in and Android environment. He was then also given a lesson from Joe, our Design & Specification Manager, to get up and running with Github and Android Studio.
| Labour summary: | As a team we were significantly under the estimation for this week, this has been predominantly due to the group still getting to grips with programming in Java in an Android environment. Individuals are being addressed but the team remains behind on finishing the user stories required for this week.
Other comments for week 21: | Other things that happened in this week include negotiations for module purchases, we were able to purchase the required modules in at 75 GBP more than our estimate for these. The good news here is that we were also able to sell two modules that were already being built by the team and achieve a very good price for these two modules with some tough negotiation on our behalf. Selling both modules for a total just over 1000 GBP we should be in a good state financially to support the team in any hours we go over during the first iteration.
Estimated time - Week 22
Role | Name | Software | Design | Testing | Meetings | Finance | Administration | Total
Project Manager | James Pearson |  |  |  | 1 |  | 4 | 5
Finance Manager | Louis Newman |  |  |  | 1 | 2 | 2 | 5
Design & Specification Manager | Joe Butler | 2 | 2.75 |  | 1 |  |  | 5.75
Lead Software Developer | James Clawley | 20 |  |  | 1 |  |  | 21
Testing & Integration Manager | Nathan Billis |  |  | 2.75 | 1 |  |  | 3.75
Marketing Manager | Becky Anderson |  |  |  | 1 |  |  | 1
XML & Server Manager | Jun Ma |  |  |  | 1 |  |  | 1
[7 empty] | Total: | 42.5
Reason for predicted hour distribution: | This week was the week for the presentation build within the application, all software was to be based around this. The lead programmer, James C, took lead and control of this effort and was given the full hour distribution for this task to delegate where he saw fit. Joe had a small task within this week of connecting a previous user story to one that was built and asked to run as the second in command on the presentation build.
Actual timesheet - Week 22
Project | User | 02/24/2020 | 02/25/2020 | 02/26/2020 | 02/27/2020 | 02/28/2020 | 02/29/2020 | 03/01/2020 | Total | Billable total
Meetings - SWEng Group 4 |  | 04:45:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 04:45:00 | 04:45:00
| James Pearson | 00:45:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:45:00 | 00:45:00
| Louis Newman | 00:45:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:45:00 | 00:45:00
| Rebecca Anderson | 00:45:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:45:00 | 00:45:00
| Nathan Billis | 00:45:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:45:00 | 00:45:00
| Jun Ma | 01:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 01:00:00 | 0:45
| James Clawley | 00:45:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:45:00 | 00:45:00
| Joe Butler | 0:45 | [7 empty] | 0:45
Software - SWEng Group 4 |  | 01:00:00 | 00:00:00 | 12:00:00 | 12:00:00 | 07:45:00 | 04:00:00 | 02:45:00 | 39:30:00 | 39:30:00
| Louis Newman | 00:00:00 | 00:00:00 | 01:00:00 | 03:30:00 | 00:00:00 | 00:00:00 | 02:00:00 | 06:30:00 | 06:30:00
| Rebecca Anderson | 00:00:00 | 00:00:00 | 03:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:45:00 | 03:45:00 | 03:45:00
| Nathan Billis | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 02:00:00 | 00:00:00 | 00:00:00 | 02:00:00 | 02:00:00
| Joe Butler | 01:00:00 | 00:00:00 | 00:00:00 | 02:30:00 | 00:45:00 | 04:00:00 | 00:00:00 | 08:15:00 | 08:15:00
| James Clawley | 00:00:00 | 00:00:00 | 08:00:00 | 06:00:00 | 05:00:00 | 00:00:00 | 00:00:00 | 19:00:00 | 19:00:00
Testing - SWEng Group 4 |  | 00:00:00 | 00:45:00 | 00:00:00 | 00:30:00 | 00:00:00 | 00:00:00 | 00:00:00 | 01:15:00 | 01:15:00
| Nathan Billis | 00:00:00 | 00:45:00 | 00:00:00 | 00:30:00 | 00:00:00 | 00:00:00 | 00:00:00 | 01:15:00 | 01:15:00
Administration - SWEng Group 4 |  | 00:00:00 | 00:00:00 | 00:30:00 | 01:15:00 | 00:00:00 | 00:00:00 | 00:00:00 | 01:45:00 | 01:45:00
| James Pearson | 00:00:00 | 00:00:00 | 00:30:00 | 01:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 01:30:00 | 01:30:00
| Nathan Billis | 00:00:00 | 00:00:00 | 00:00:00 | 00:15:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:15:00 | 00:15:00
User Stories - SWEng Group 4 |  | 00:00:00 | 00:00:00 | 00:00:00 | 01:00:00 | 00:00:00 | 01:00:00 | 02:00:00 | 04:00:00 | 04:00:00
| James Pearson | 00:00:00 | 00:00:00 | 00:00:00 | 01:00:00 | 00:00:00 | 01:00:00 | 02:00:00 | 04:00:00 | 04:00:00
Design - SWEng Group 4 |  | 00:00:00 | 00:00:00 | 00:00:00 | 01:30:00 | 01:30:00 | 01:30:00 | 00:00:00 | 04:30:00 | 04:30:00
| Jun Ma | 00:00:00 | 00:00:00 | 00:00:00 | 01:30:00 | 01:30:00 | 01:30:00 | 00:00:00 | 04:30:00 | 04:30:00
TOTAL |  | 05:45:00 | 00:45:00 | 12:30:00 | 16:15:00 | 09:15:00 | 06:30:00 | 04:45:00 | 55:45:00 | 56.25.00
[9 empty] | Total billable | 56.25 | Difference to predicted: | -13.75
Notes on labour for week 22: | Comment on rejected hours: | The only rejected hours during this week were that Jun had put in too much time for a meeting, the extra time input was rejected.
| Comment on dicrepency: | A significant proportion of the presentation was completed during this week along with completion of stories that were unable to be completed in previoud weeks. We went over by nearly 14 hours but due to last weeks discepencies these were all accounted for.
| Comment on hour dispersion: | James C took lead as he was supposed to on the Presentation, He decided to get the bulk of this done in his own time. He was supposed to be working with Joe but Joe had gone over on a previous week’s story and was now trying to put together this week’s story on top of that and didn't get around to fulfilling the role he has suggested he would play. All other programming hours used went into finishing stories from previous weeks other than Jun now having a story from iteration 3 to get him up and running with programming in Java in an android environment.
Other comments for week 22: | Finalising of contracts and negotiations took place in this week, we used less labour hours than predicted and got exactly what we wanted out of these negotiations so the team in in a good place financially in reference to this.
Comments on reporting period: | With where we are in terms of the Iteration 1 programming effort, we are very slightly behind the predicted position. However, the short comings in programming ability of the team are being addressed and the slow pace that came at the start of the iteration is now being gained on. The team is showing all the correct signs that we will be where we predicted we would be at the end of iteration 1. The short comings in programming ability are still being addressed with pair programming the weak with the strong and lessons for those not up to the standard required. The product is really now starting to come together with a strong backend data structure and a front end that it taking up functionality with every new branch merge. The team has taken to the addressing of shorted meetings and these have been worked down in 15-minute intervals from 1 hour to 30 minutes. Contract negations went better than could have been expected, paying 75 GBP more than we wanted to but then making the sales of over 1000 GBP. The production of these modules is going spectacularly well with the majority of these nearly finished as they came as part of the presentation user stories.
30th September - 3rd March 2020.
Comments from team lead: | After a slow start to development and becoming aware of some early weaknesses within the team, we can now go forward with the awareness of how to effectively pair up team members on particular user stories to get the most out of our time while getting everyone up to speed on the different aspects the application will reveal. Proud of what was achieved with the module negotions which i believe is a fair reflection of the effort that needs to be applied. After speaking to the Financial backer and customer about pushiing a feature from the first iteration, we look on track to deliver as specified.

## Financal report 3
Version control: 1.0 - Date: 29/04/2020
Financial Report III | Date: 29/04/2020 | SWEng Group 4
Author: | Codev Financial Manager | Louis Newman
Week number | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31
Week dates | Sep. 30, 2019-Oct. 6, 2019 | Oct. 7, 2019-Oct. 13, 2019 | Oct. 14, 2019-Oct. 20, 2019 | Oct. 21, 2019-Oct. 27, 2019 | Oct. 28, 2019-Nov. 3, 2019 | Nov. 4, 2019-Nov. 10, 2019 | Nov. 11, 2019-Nov. 17, 2019 | Nov. 18, 2019-Nov. 24, 2019 | Nov. 25, 2019-Dec. 1, 2019 | Dec. 2, 2019-Dec. 8, 2019 | Dec. 9, 2019-Dec. 15, 2019 | Dec. 16, 2019-Dec. 22, 2019 | Dec. 23, 2019-Dec. 29, 2019 | Dec. 30, 2019-Jan. 5, 2020 | Jan. 6, 2020-Jan. 12, 2020 | Jan. 13, 2020-Jan. 19, 2020 | Jan. 20, 2020-Jan. 26, 2020 | Jan. 27, 2020-Feb. 2, 2020 | Feb. 3, 2020-Feb. 9, 2020 | Feb. 10, 2020-Feb. 16, 2020 | Feb. 17, 2020-Feb. 23, 2020 | Feb. 24, 2020-Mar. 1, 2020 | Mar. 2, 2020-Mar. 8, 2020 | Mar. 9, 2020-Mar. 15, 2020 | Mar. 16, 2020-Mar. 22, 2020 | Mar. 23, 2020-Mar. 29, 2020 | Mar. 30, 2020-Apr. 5, 2020 | Apr. 6, 2020-Apr. 12, 2020 | Apr. 13, 2020-Apr. 19, 2020 | Apr. 20, 2020-Apr. 26, 2020 | Apr. 27, 2020-May 3, 2020
Term week | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | Christmas | Christmas | Christmas | Christmas | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | Easter | Easter | Easter | Easter | 1 | 2 | 3
Project Iteration Stage | Preparation | Preparation | Preparation | Preparation | Preparation | Preparation | Preparation | Preparation | Preparation | Preparation | Preparation | Preparation | Preparation | Preparation | Preparation | Preparation | Preparation | Preparation | Iteration 1, week 1 | Iteration 1, week 2 | Iteration 1, week 3 | Iteration 1, week 4 | Iteration 1, week 5 | Iteration 1, week 6 | Iteration 2, week 1 | Iteration 2, week 2 | Iteration 2, week 3 | Iteration 2, week 4 | Iteration 2, week 5 | Iteration 3, week 1 | Iteration 3, week 2
Predicted
Predicted Module sales (IN)
Predicted Module purchases (OUT) | [21 empty] | -100 |  | -300
Predicted weekly hours | 0 | 0 | 0 | 7 | 8.25 | 8.25 | 8.5 | 7.75 | 20.25 | 14 | 0 | 0 | 0 | 0 | 0 | 45.25 | 67.5 | 35 | 47.75 | 59 | 58.5 | 42.5 | 46 | 29.25 | 47.25 | 34.75 | 28.5 | 43.5 | 43.5 | 37.25 | 47.25
Closing Balance | 0 | 0 | 0 | -2618.2692 | -2721.3942 | -3724.5192 | -5728.8462 | -5825.7212 | -6078.8462 | -8751.9231 | -8751.9231 | -8751.9231 | -8751.9231 | -8751.9231 | -8751.9231 | -9317.5481 | -10161.2981 | -15660.3365 | -16257.2115 | 9656.8626 | 6935.9627 | 6213.1398 | 5546.5668 | 2291.2919 | 1609.0939 | 1083.1459 | 635.323 | -1.9327e-12 | 15645.9959 | 15035.8372 | 14300.6784
Actual
Actual hours | 0 | 0 | 0 | 7 | 8.25 | 8.25 | 8.5 | 7.75 | 20.25 | 14 | 0 | 0 | 0 | 0 | 0 | 45.25 | 67.5 | 35 | 40.5 | 70.25 | 32.5 | 56.25 | 46.75 | 40 | 38.25 | 73.25 | 48.25 | 23 | 44.25 | 27.5
IN
Loans (IN) | [19 empty] | 28243.1471 | [8 empty] | 16334.2796
Module sales (IN) | [21 empty] | 263.53 |  | 790.58
OUT
Premises Rent |  |  |  | -2530.7692 |  |  | -1898.0769 |  |  | -1898.0769 | [7 empty] | -5061.5385 |  |  | -1898.0769 |  |  | -1898.0769
Utilities Rent | [5 empty] | -300 |  |  |  | -200 | [9 empty] | -500 |  |  |  | -200
IT infrastructure | [5 empty] | -600 |  |  |  | -400 | [9 empty] | -1000 |  |  |  | -400
Cost of Labour (12.5 GBP per hour) | 0 | 0 | 0 | -87.5 | -103.125 | -103.125 | -106.25 | -96.875 | -253.125 | -175 | 0 | 0 | 0 | 0 | 0 | -565.625 | -843.75 | -437.5 | -506.25 | -878.125 | -406.25 | -703.125 | -584.375 | -500 | -478.125 | -915.625 | -603.125 | -287.5 | -553.125 | -343.75 | 0
Weekly interest (16.86% APR) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -91.573 | -91.573 | -91.573 | -91.573 | -91.573 | -91.573 | -91.573 | -91.573 | -91.573 | -144.5337 | -144.5337 | -144.5337
Module purchases (OUT) | [21 empty] | -115.33 |  | -345.99
Creditors
Total credit for loans | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28243.1471 | 28243.1471 | 28243.1471 | 28243.1471 | 28243.1471 | 28243.1471 | 28243.1471 | 28243.1471 | 28243.1471 | 44577.4268 | 44577.4268 | 44577.4268
Total credit recieved for modules | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 345.99 | 345.99 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total credit given for modules | [21 empty] | 790.58 | 790.58 | 0
Opening Balance | 0 | 0 | 0 | 0 | -2618.2692 | -2721.3942 | -3724.5192 | -5728.8462 | -5825.7212 | -6078.8462 | -8751.9231 | -8751.9231 | -8751.9231 | -8751.9231 | -8751.9231 | -8751.9231 | -9317.5481 | -10161.2981 | -15660.3365 | -16166.5865 | 9606.8626 | 7210.9627 | 6564.4648 | 5888.5168 | 3243.4569 | 2673.7589 | 1666.5609 | 971.863 | 592.79 | 16229.4109 | 15741.1272
OUT total | 0 | 0 | 0 | -2618.2692 | -103.125 | -1003.125 | -2004.3269 | -96.875 | -253.125 | -2673.0769 | 0 | 0 | 0 | 0 | 0 | -565.625 | -843.75 | -5499.0385 | -506.25 | -2469.698 | -2395.8999 | -910.028 | -675.948 | -3435.6399 | -569.698 | -1007.198 | -694.698 | -379.073 | -697.6587 | -488.2837 | -144.5337
IN total | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28243.1471 | 0 | 263.53 | 0 | 790.58 | 0 | 0 | 0 | 0 | 16334.2796 | 0 | 0
Closing Balance | 0 | 0 | 0 | -2618.2692 | -2721.3942 | -3724.5192 | -5728.8462 | -5825.7212 | -6078.8462 | -8751.9231 | -8751.9231 | -8751.9231 | -8751.9231 | -8751.9231 | -8751.9231 | -9317.5481 | -10161.2981 | -15660.3365 | -16166.5865 | 9606.8626 | 7210.9627 | 6564.4648 | 5888.5168 | 3243.4569 | 2673.7589 | 1666.5609 | 971.863 | 592.79 | 16229.4109 | 15741.1272 | 15596.5934
Difference to prediction | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 90.625 | -50 | 275 | 351.325 | 341.95 | 952.165 | 1064.665 | 583.415 | 336.54 | 592.79 | 583.415 | 705.29
Estimated time - Week 23
Role | Name | Software | Design | Testing | Meetings | Finance | Administration | Total
Project Manager | James Pearson |  |  |  | 1 |  | 2 | 3
Finance Manager | Louis Newman | 8 |  |  | 1 | 2 |  | 11
Design & Specification Manager | Joe Butler |  | 3.5 |  | 1 |  |  | 4.5
Lead Software Developer | James Clawley | 17 |  |  | 1 |  |  | 18
Testing & Integration Manager | Nathan Billis |  |  | 3.5 | 1 |  |  | 4.5
Marketing Manager | Becky Anderson | 3 |  |  | 1 |  |  | 4
XML & Server Manager | Jun Ma |  |  |  | 1 |  |  | 1
[7 empty] | Total: | 46
Reason for predicted hour distribution: | Hours assigned to team member taking lead on story to delegate as they see fit.
Actual timesheet - Week 23
Project | User | 03/02/2020 | 03/03/2020 | 03/04/2020 | 03/05/2020 | 03/06/2020 | 03/07/2020 | 03/08/2020 | Total | Billable total
Finance - SWEng Group 4 |  | 00:00:00 | 01:00:00 | 00:00:00 | 00:30:00 | 00:00:00 | 00:00:00 | 00:00:00 | 01:30:00 | 01:30:00
| Louis Newman | 00:00:00 | 01:00:00 | 00:00:00 | 00:30:00 | 00:00:00 | 00:00:00 | 00:00:00 | 01:30:00 | 01:30:00
Meetings - SWEng Group 4 |  | 03:30:00 | 01:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 04:30:00 | 04:30:00
| James Pearson | 00:30:00 | 00:30:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 01:00:00 | 01:00:00
| Louis Newman | 00:30:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:30:00 | 00:30:00
| Rebecca Anderson | 00:30:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:30:00 | 00:30:00
| Nathan Billis | 00:30:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:30:00 | 00:30:00
| Jun Ma | 00:30:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:30:00 | 00:30:00
| Joe Butler | 00:30:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:30:00 | 00:30:00
| James Clawley | 00:30:00 | 00:30:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 01:00:00 | 01:00:00
Software - SWEng Group 4 |  | 01:00:00 | 01:00:00 | 02:00:00 | 15:15:00 | 04:30:00 | 04:30:00 | 03:00:00 | 31:15:00 | 31:15:00
| Louis Newman | 01:00:00 | 00:00:00 | 00:00:00 | 03:30:00 | 00:00:00 | 03:00:00 | 02:00:00 | 09:30:00 | 09:30:00
| Rebecca Anderson | 00:00:00 | 00:00:00 | 00:00:00 | 02:45:00 | 00:00:00 | 01:00:00 | 00:00:00 | 03:45:00 | 03:45:00
| Nathan Billis | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:30:00 | 00:30:00 | 00:30:00
| Jun Ma | 00:00:00 | 00:00:00 | 02:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 02:00:00 | 02:00:00
| Joe Butler | 00:00:00 | 00:00:00 | 00:00:00 | 07:00:00 | 02:30:00 | 00:30:00 | 00:30:00 | 10:30:00 | 10:30:00
| James Clawley | 00:00:00 | 01:00:00 | 00:00:00 | 02:00:00 | 02:00:00 | 00:00:00 | 00:00:00 | 05:00:00 | 05:00:00
Testing - SWEng Group 4 |  | 00:00:00 | 00:00:00 | 00:00:00 | 00:15:00 | 00:00:00 | 00:00:00 | 00:30:00 | 00:45:00 | 00:45:00
| Nathan Billis | 00:00:00 | 00:00:00 | 00:00:00 | 00:15:00 | 00:00:00 | 00:00:00 | 00:30:00 | 00:45:00 | 00:45:00
Administration - SWEng Group 4 |  | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 01:30:00 | 00:00:00 | 00:15:00 | 01:45:00 | 01:45:00
| James Pearson | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:15:00 | 00:15:00 | 00:15:00
| James Clawley | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 01:30:00 | 00:00:00 | 00:00:00 | 01:30:00 | 01:30:00
User Stories - SWEng Group 4 |  | 00:00:00 | 00:30:00 | 00:00:00 | 02:00:00 | 00:00:00 | 01:30:00 | 00:00:00 | 04:00:00 | 04:00:00
| James Pearson | 00:00:00 | 00:30:00 | 00:00:00 | 02:00:00 | 00:00:00 | 01:30:00 | 00:00:00 | 04:00:00 | 04:00:00
Test and integration plan - SWEng Group 4 |  | 00:00:00 | 00:00:00 | 01:00:00 | 01:30:00 | 00:30:00 | 00:00:00 | 00:00:00 | 03:00:00 | 03:00:00
| Nathan Billis | 00:00:00 | 00:00:00 | 01:00:00 | 01:30:00 | 00:30:00 | 00:00:00 | 00:00:00 | 03:00:00 | 03:00:00
TOTAL |  | 04:30:00 | 03:30:00 | 03:00:00 | 19:30:00 | 06:30:00 | 06:00:00 | 03:45:00 | 46:45:00 | 46:45:00 | Difference to predicted: | -0.75
[9 empty] | Billable total: | 46.75
Notes on labour for week 23:
| Finance manager comment from weekly timesheet: | Over by 0.75 hours this week with an estimated hours of 46, we are ahead overall with 7.5 hours more than we have used. We are about where we should be with user stories with the meal planner pushed back to Iteration 2 but with us using the time we had allocated to these user stories we are mildly behind schedule in terms of hours used. No hours seem out of place in this weeks timesheet.
| Team lead comment from weekly timesheet: | N/A
Other comments for week 23: | N/A
Estimated time - Week 24
Role | Name | Software | Design | Testing | Meetings | Finance | Administration | Total
Project Manager | James Pearson | 4 |  |  | 1 |  | 2 | 7
Finance Manager | Louis Newman |  |  |  | 1 | 2 |  | 3
Design & Specification Manager | Joe Butler | 2 | 1.75 |  | 1 |  |  | 4.75
Lead Software Developer | James Clawley | 8 |  |  | 1 |  |  | 9
Testing & Integration Manager | Nathan Billis |  |  | 1.75 | 1 |  |  | 2.75
Marketing Manager | Becky Anderson |  |  |  | 1 |  |  | 1
XML & Server Manager | Jun Ma |  |  |  | 1 |  |  | 1
[7 empty] | Total: | 28.5
Reason for predicted hour distribution: | Hours assigned to team member taking lead on story to delegate as they see fit.
Actual timesheet - Week 24
Project | User | 03/09/2020 | 03/10/2020 | 03/11/2020 | 03/12/2020 | 03/13/2020 | 03/14/2020 | 03/15/2020 | Total | Billable total
Finance - SWEng Group 4 |  | 00:00:00 | 00:15:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:15:00 | 00:15:00
| Louis Newman | 00:00:00 | 00:15:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:15:00 | 00:15:00
Meetings - SWEng Group 4 |  | 03:15:00 | 00:00:00 | 00:30:00 | 00:00:00 | 01:00:00 | 00:00:00 | 00:00:00 | 04:45:00 | 04:45:00
| James Pearson | 00:30:00 | 00:00:00 | 00:30:00 | 00:00:00 | 00:15:00 | 00:00:00 | 00:00:00 | 01:15:00 | 01:15:00
| Louis Newman | 00:30:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:15:00 | 00:00:00 | 00:00:00 | 00:45:00 | 00:45:00
| Rebecca Anderson | 00:30:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:30:00 | 00:30:00
| Nathan Billis | 00:30:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:15:00 | 00:00:00 | 00:00:00 | 00:45:00 | 00:45:00
| Jun Ma | 00:30:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:30:00 | 00:30:00
| James Clawley | 00:45:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:15:00 | 00:00:00 | 00:00:00 | 01:00:00 | 01:00:00
Quality Manual - SWEng Group 4 |  | 00:00:00 | 00:00:00 | 00:15:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:15:00 | 00:15:00
| James Pearson | 00:00:00 | 00:00:00 | 00:15:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:15:00 | 00:15:00
Software - SWEng Group 4 |  | 02:45:00 | 03:15:00 | 00:00:00 | 04:00:00 | 02:30:00 | 00:00:00 | 00:00:00 | 12:30:00 | 12:30:00
| Louis Newman | 02:00:00 | 00:00:00 | 00:00:00 | 02:00:00 | 00:30:00 | 00:00:00 | 00:00:00 | 04:30:00 | 04:30:00
| Rebecca Anderson | 00:00:00 | 00:45:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:45:00 | 00:45:00
| Joe Butler | 00:45:00 | 01:30:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 02:15:00 | 02:15:00
| James Clawley | 00:00:00 | 01:00:00 | 00:00:00 | 02:00:00 | 02:00:00 | 00:00:00 | 00:00:00 | 05:00:00 | 05:00:00
Testing - SWEng Group 4 |  | 00:00:00 | 02:00:00 | 00:00:00 | 01:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 03:00:00 | 03:00:00
| Rebecca Anderson | 00:00:00 | 02:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 02:00:00 | 02:00:00
| Nathan Billis | 00:00:00 | 00:00:00 | 00:00:00 | 01:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 01:00:00 | 01:00:00
Marketing - SWEng Group 4 |  | 00:00:00 | 00:45:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:15:00 | 01:00:00 | 01:00:00
| Rebecca Anderson | 00:00:00 | 00:45:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:15:00 | 01:00:00 | 01:00:00
Administration - SWEng Group 4 |  | 00:15:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:15:00 | 00:15:00
| Rebecca Anderson | 00:15:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:15:00 | 00:15:00
Design - SWEng Group 4 |  | 00:00:00 | 00:00:00 | 00:00:00 | 01:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 01:00:00 | 01:00:00
| James Pearson | 00:00:00 | 00:00:00 | 00:00:00 | 01:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 01:00:00 | 01:00:00
Test and integration plan - SWEng Group 4 |  | 00:00:00 | 01:30:00 | 05:00:00 | 10:00:00 | 00:30:00 | 00:00:00 | 00:00:00 | 17:00:00 | 17:00:00
| James Pearson | 00:00:00 | 00:00:00 | 00:45:00 | 02:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 02:45:00 | 02:45:00
| Louis Newman | 00:00:00 | 00:00:00 | 01:00:00 | 02:30:00 | 00:00:00 | 00:00:00 | 00:00:00 | 03:30:00 | 03:30:00
| Rebecca Anderson | 00:00:00 | 00:00:00 | 00:45:00 | 01:30:00 | 00:00:00 | 00:00:00 | 00:00:00 | 02:15:00 | 02:15:00
| Nathan Billis | 00:00:00 | 01:30:00 | 01:00:00 | 01:00:00 | 00:30:00 | 00:00:00 | 00:00:00 | 04:00:00 | 04:00:00
| Jun Ma | 00:00:00 | 00:00:00 | 00:00:00 | 03:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 03:00:00 | 03:00:00
| Joe Butler | 00:00:00 | 00:00:00 | 01:30:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 01:30:00 | 01:30:00
TOTAL |  | 06:15:00 | 07:45:00 | 05:45:00 | 16:00:00 | 04:00:00 | 00:00:00 | 00:15:00 | 40:00:00 | 40:00:00
[9 empty] | Total billable | 40 | Difference to predicted: | -11.5
Notes on labour for week 24:
| Finance manager comment from weekly timesheet: | The team had predicted 29.25 hours for this week, finishing iteration 1. It was found however that a team oversight had lead to no time allocation for the Test and Iteration plan. We have had 25 % of user stories given to testing in general, but nothing had gone into the Test and Iteration plan. During this week, 17 hours has gone into the Test and Iteration plan, last week 3 hours went into it. When asked during the predition phase of the project, the test team had not brought up this deliverable and thus was missed. Due to this oversight we are over budget this week, taking from the balance of time the team have built up over Iteration 1, the team is now 3.25 hours over going into Iteration 2. Looking at the current financial situation of the group as a whole this week however, we can identify that, due to excellent sales of Modules, we have £952.17 more in the bank than predicted. This will enable to team to put in extra hours where necessary during this iteration to finish in a strong position, with all necessary features completed.
| Team lead comment from weekly timesheet: | As project leader I take full responsibility for the oversight that has led to extra hours needing to be worked for this week. My initial assumptions on what was required for the Testing and Integration plan were greatly underestimated when originally put forward to the group in our initial predictions. This then led to the needing of extra hours from other members of the development team. All in all, finances are healthy and having the financial buffer to cover for any problems that may arise going forward is a great asset.
Other comments for week 24: | Second instalment of module sales came into the accounts along with second installment of module purchases leaving the accounts, this aligned with agreed timetable in contracts and boosted teams financial position dramatically.
Estimated time - Week 25
Role | Name | Software | Design | Testing | Meetings | Finance | Administration | Total
Project Manager | James Pearson |  |  |  | 1 |  | 2 | 3
Finance Manager | Louis Newman | 29 |  |  | 1 | 2 |  | 32
Design & Specification Manager | Joe Butler |  | 3.625 |  | 1 |  |  | 4.625
Lead Software Developer | James Clawley |  |  |  | 1 |  |  | 1
Testing & Integration Manager | Nathan Billis |  |  | 3.625 | 1 |  |  | 4.625
Marketing Manager | Becky Anderson |  |  |  | 1 |  |  | 1
XML & Server Manager | Jun Ma |  |  |  | 1 |  |  | 1
[7 empty] | Total: | 47.25
Reason for predicted hour distribution: | Hours assigned to team member taking lead on story to delegate as they see fit.
Actual timesheet - Week 25
Project | User | 03/16/2020 | 03/17/2020 | 03/18/2020 | 03/19/2020 | 03/20/2020 | 03/21/2020 | 03/22/2020 | Total | Billable total
Finance - SWEng Group 4 |  | 00:30:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:30:00 | 00:30:00
| Louis Newman | 00:30:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:30:00 | 00:30:00
Software - SWEng Group 4 |  | 01:00:00 | 11:45:00 | 10:00:00 | 03:15:00 | 03:00:00 | 05:00:00 | 02:00:00 | 36:00:00 | 36:00:00
| James Pearson | 00:00:00 | 00:00:00 | 04:00:00 | 03:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 07:00:00 | 07:00:00
| Louis Newman | 00:00:00 | 05:00:00 | 04:00:00 | 00:15:00 | 00:00:00 | 00:00:00 | 00:00:00 | 09:15:00 | 09:15:00
| Rebecca Anderson | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 02:00:00 | 02:00:00 | 02:00:00
| Nathan Billis | 00:00:00 | 01:30:00 | 02:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 03:30:00 | 03:30:00
| Jun Ma | 01:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 01:00:00 | 01:00:00
| Joe Butler | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 03:00:00 | 05:00:00 | 00:00:00 | 08:00:00 | 08:00:00
| James Clawley | 00:00:00 | 05:15:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 05:15:00 | 05:15:00
Testing - SWEng Group 4 |  | 00:00:00 | 00:30:00 | 00:30:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:30:00 | 01:30:00 | 01:30:00
| Nathan Billis | 00:00:00 | 00:30:00 | 00:30:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:30:00 | 01:30:00 | 01:30:00
Administration - SWEng Group 4 |  | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:15:00 | 00:15:00 | 00:15:00
| James Pearson | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:15:00 | 00:15:00 | 00:15:00
TOTAL |  | 01:30:00 | 12:15:00 | 10:30:00 | 03:15:00 | 03:00:00 | 05:00:00 | 02:45:00 | 38:15:00 | 38:15:00
[9 empty] | Total billable | 38.25 | Difference to predicted: | 9
Notes on labour for week 25:
| Finance manager comment from weekly timesheet: | The team had predicted 47.25 hours for this week, starting Iteration 2. Taking our previous weeks balance into account, the team is now under our predicted hours by 5.75 hours. Compared with our total predicted location, the team has an extra £1,064.67 in the bank. Again this is mainly due to the team selling modules at an excellent price and this retains the buffer to enable extra labour hours as and where we require them in order to deliver the product envisioned in the tender presentation. Analysing the teams position with respect to the Financial Business Plan, we are behind in our expected position as we should be well under way with the social aspect of the application. However as the team has pushed the meal planner back to iteration 2, we are where we should be taking this into account. The strong financial position of the team should enable the team to catch up to our predicted position as members are able to put in the extra hours required to get to this position.
| Team lead comment from weekly timesheet: | Observations made by the Financial Manager are accurate and with big features like the meal planner and the social aspect being done now or coming up, The extra funds will cover any problems that arise in the coming development time.
Other comments for week 25: | N/A
Estimated time - Week 26
Role | Name | Software | Design | Testing | Meetings | Finance | Administration | Total
Project Manager | James Pearson |  |  |  | 1 |  | 2 | 3
Finance Manager | Louis Newman | 19 |  |  | 1 | 2 |  | 22
Design & Specification Manager | Joe Butler |  | 2.25 |  | 1 |  |  | 3.25
Lead Software Developer | James Clawley |  |  |  | 1 |  |  | 1
Testing & Integration Manager | Nathan Billis |  |  | 2.5 | 1 |  |  | 3.5
Marketing Manager | Becky Anderson |  |  |  | 1 |  |  | 1
XML & Server Manager | Jun Ma |  |  |  | 1 |  |  | 1
[7 empty] | Total: | 34.75
Reason for predicted hour distribution: | Hours assigned to team member taking lead on story to delegate as they see fit.
Actual timesheet - Week 26
Project | User | 03/23/2020 | 03/24/2020 | 03/25/2020 | 03/26/2020 | 03/27/2020 | 03/28/2020 | 03/29/2020 | Total | Total billable
Finance - SWEng Group 4 |  | 00:45:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:45:00 | 00:45:00
| Louis Newman | 00:45:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:45:00 | 00:45:00
Meetings - SWEng Group 4 |  | 02:00:00 | 05:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 07:00:00 | 07:00:00
| James Pearson | 00:00:00 | 01:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 01:00:00 | 01:00:00
| Louis Newman | 00:00:00 | 01:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 01:00:00 | 01:00:00
| Rebecca Anderson | 01:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 01:00:00 | 01:00:00
| Nathan Billis | 00:00:00 | 01:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 01:00:00 | 01:00:00
| Jun Ma | 00:00:00 | 01:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 01:00:00 | 01:00:00
| Joe Butler | 00:00:00 | 01:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 01:00:00 | 01:00:00
| James Clawley | 01:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 01:00:00 | 01:00:00
Software - SWEng Group 4 |  | 03:00:00 | 07:30:00 | 10:00:00 | 12:00:00 | 07:00:00 | 02:00:00 | 15:30:00 | 57:00:00 | 57:00:00
| James Pearson | 03:00:00 | 04:00:00 | 00:00:00 | 01:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 08:00:00 | 08:00:00
| Louis Newman | 00:00:00 | 01:30:00 | 03:00:00 | 03:00:00 | 02:00:00 | 00:00:00 | 07:30:00 | 17:00:00 | 17:00:00
| Rebecca Anderson | 00:00:00 | 00:00:00 | 01:00:00 | 00:00:00 | 00:00:00 | 02:00:00 | 03:00:00 | 06:00:00 | 06:00:00
| Nathan Billis | 00:00:00 | 00:00:00 | 01:00:00 | 00:00:00 | 02:00:00 | 00:00:00 | 00:00:00 | 03:00:00 | 03:00:00
| Jun Ma | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 01:00:00 | 01:00:00 | 01:00:00
| Joe Butler | 00:00:00 | 00:00:00 | 02:00:00 | 06:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 08:00:00 | 08:00:00
| James Clawley | 00:00:00 | 02:00:00 | 03:00:00 | 02:00:00 | 03:00:00 | 00:00:00 | 04:00:00 | 14:00:00 | 14:00:00
Testing - SWEng Group 4 |  | 00:00:00 | 00:00:00 | 03:00:00 | 02:30:00 | 00:00:00 | 00:00:00 | 00:00:00 | 05:30:00 | 05:30:00
| Nathan Billis | 00:00:00 | 00:00:00 | 02:00:00 | 02:30:00 | 00:00:00 | 00:00:00 | 00:00:00 | 04:30:00 | 04:30:00
| Jun Ma | 00:00:00 | 00:00:00 | 01:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 01:00:00 | 01:00:00
Administration - SWEng Group 4 |  | 00:30:00 | 00:00:00 | 00:15:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:15:00 | 01:00:00 | 01:00:00
| James Pearson | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:15:00 | 00:15:00 | 00:15:00
| Rebecca Anderson | 00:30:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:30:00 | 00:30:00
| Nathan Billis | 00:00:00 | 00:00:00 | 00:15:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:15:00 | 00:15:00
Design - SWEng Group 4 |  | 00:00:00 | 00:00:00 | 00:00:00 | 01:00:00 | 01:00:00 | 00:00:00 | 00:00:00 | 02:00:00 | 02:00:00
| Jun Ma | 00:00:00 | 00:00:00 | 00:00:00 | 01:00:00 | 01:00:00 | 00:00:00 | 00:00:00 | 02:00:00 | 02:00:00
TOTAL |  | 06:15:00 | 12:30:00 | 13:15:00 | 15:30:00 | 08:00:00 | 02:00:00 | 15:45:00 | 73:15:00 | 73:15:00
[9 empty] | Total billable | 73.25 | Difference to predicted: | -38.5
Notes on labour for week 26:
| Finance manager comment from weekly timesheet: | The team had predicted 34.75 hours for this week, week 2 of iteration 2. We have gone over on estimated hours in total of 32.75 for the entire project. At then end of last week, the team had an extra £1,064.67, this week we are still in the positive but from the extra work that has gone in this week we are at £583.42 extra in the pot, using up some of this redundancy. The reason for this this over time is due to the team attempting to catch up with our estimated plan location. Along with this our 30 minute meeting slot is being stretched as we now have to meet in a virtual domain, meeting are being elongated with this domain. The presentation is nearly all together and the meal planner has been completed. Along with this, the social stories planned for weeks 1 & 2, iteration 2, are nearly where they should be. Overall Corona-Virus is having an impact on the operation of the team, however we are nearly where we estimated we should be with user stories and financially. Having this extra money in the bank should enable to team to completely catch up with our previously estimated location before the end of iteration 2.
| Team lead comment from weekly timesheet: | COVID-19 impact - Pair programming is out the window, getting people to ask for help when needed is top priority and delegating that help to a member of the development team with the correct skills is imperative to make sure that there is no extra time wasted going round in circles looking for fix. Weekly meetings online aren't as streamlined as one would hope but they are doing a job keeping everyone in the loop as to what is going on. Bugs with the presentation and Louis working on the Social Aspect is taking a chunk of extra time but when these and the user created recipes is done, everything else should be relatively straight forward. Building on what we already have.
Other comments for week 26: | N/A
Estimated time - Week 26
Role | Name | Software | Design | Testing | Meetings | Finance | Administration | Total
Project Manager | James Pearson |  |  |  | 1 |  | 2 | 3
Finance Manager | Louis Newman |  |  |  | 1 | 2 |  | 3
Design & Specification Manager | Joe Butler |  | 1.75 |  | 1 |  |  | 2.75
Lead Software Developer | James Clawley |  |  |  | 1 |  |  | 1
Testing & Integration Manager | Nathan Billis | 14 |  | 1.75 | 1 |  |  | 16.75
Marketing Manager | Becky Anderson |  |  |  | 1 |  |  | 1
XML & Server Manager | Jun Ma |  |  |  | 1 |  |  | 1
[7 empty] | Total: | 28.5
Reason for predicted hour distribution: | Hours assigned to team member taking lead on story to delegate as they see fit.
Actual timesheet - Week 27
Project | User | 03/30/2020 | 03/31/2020 | 04/01/2020 | 04/02/2020 | 04/03/2020 | 04/04/2020 | 04/05/2020 | Total | Billable hours
Finance - SWEng Group 4 |  | 00:30:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:30:00 | 00:30:00
| Louis Newman | 00:30:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:30:00 | 00:30:00
Meetings - SWEng Group 4 |  | 04:15:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 04:15:00 | 04:15:00
| James Pearson | 00:30:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:30:00 | 00:30:00
| Louis Newman | 00:30:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:30:00 | 00:30:00
| Rebecca Anderson | 00:30:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:30:00 | 00:30:00
| Nathan Billis | 00:30:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:30:00 | 00:30:00
| Jun Ma | 00:45:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:45:00 | 00:45:00
| Joe Butler | 00:45:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:45:00 | 00:45:00
| James Clawley | 00:45:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:45:00 | 00:45:00
Software - SWEng Group 4 |  | 08:00:00 | 07:00:00 | 09:00:00 | 09:00:00 | 09:00:00 | 01:00:00 | 00:00:00 | 43:00:00 | 43:00:00
| James Pearson | 00:00:00 | 00:00:00 | 02:00:00 | 02:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 04:00:00 | 04:00:00
| Louis Newman | 00:00:00 | 02:00:00 | 02:00:00 | 01:00:00 | 01:00:00 | 01:00:00 | 00:00:00 | 07:00:00 | 07:00:00
| Rebecca Anderson | 00:00:00 | 02:00:00 | 00:00:00 | 01:00:00 | 02:00:00 | 00:00:00 | 00:00:00 | 05:00:00 | 05:00:00
| Nathan Billis | 00:00:00 | 00:00:00 | 01:00:00 | 02:00:00 | 04:00:00 | 00:00:00 | 00:00:00 | 07:00:00 | 07:00:00
| Jun Ma | 00:00:00 | 00:00:00 | 00:00:00 | 01:00:00 | 01:00:00 | 00:00:00 | 00:00:00 | 02:00:00 | 02:00:00
| Joe Butler | 08:00:00 | 00:00:00 | 01:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 09:00:00 | 09:00:00
| James Clawley | 00:00:00 | 03:00:00 | 03:00:00 | 02:00:00 | 01:00:00 | 00:00:00 | 00:00:00 | 09:00:00 | 09:00:00
Administration - SWEng Group 4 |  | 00:30:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:30:00 | 00:30:00
| Rebecca Anderson | 00:30:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:30:00 | 00:30:00
TOTAL |  | 13:15:00 | 07:00:00 | 09:00:00 | 09:00:00 | 09:00:00 | 01:00:00 | 00:00:00 | 48:15:00 | 48:15:00
[9 empty] | Total billable | 48.25 | Difference to predicted: | -19.75
Notes on labour for week 27:
| Finance manager comment from weekly timesheet: | The team had predicted 28.5 hours for this week, week 3 of iteration 2. We have gone over on estimated hours in total of 52.5 for the entire project. At then end of last week, the team had an extra £583.42, this week we are still in the positive but from the extra work that has gone in this week we are at £336.54 extra in the pot, using up some of this redundancy. The reason for this this over time is due to the team spending extra time on the most crutial parts of the application. These include adding recipes, building a strong searching capability and building the social feature that will work and promote repeat customers within our userbase. With these features holding the key selling points of the application it is crutial to get these correct, moreover as these key feature develop the team is uncovering new challenges and new solutions which will make the application not only functional but bring relish to these aspects. As a result of this, the team has gone over estimations for these stories, along with previous stories needing to be revisited to function with these stories. With active financial management I am allowing for this overtime with the spare capacity the team currently holds.
| Team lead comment from weekly timesheet: | N/A
Other comments for week 27: | N/A
Estimated time - Week 28
Role | Name | Software | Design | Testing | Meetings | Finance | Administration | Total | stories not assigned
Project Manager | James Pearson |  |  |  | 1 |  | 2 | 3 | C13 & C32
Finance Manager | Louis Newman |  |  |  | 1 | 2 |  | 3
Design & Specification Manager | Joe Butler |  | 1.25 |  | 1 |  |  | 2.25
Lead Software Developer | James Clawley |  |  |  | 1 |  |  | 1
Testing & Integration Manager | Nathan Billis | 10 |  | 1.25 | 1 |  |  | 12.25
Marketing Manager | Becky Anderson |  |  |  | 1 |  |  | 1
XML & Server Manager | Jun Ma |  |  |  | 1 |  |  | 1
[7 empty] | Total: | 23.5
Reason for predicted hour distribution: | Hours assigned to team member taking lead on story to delegate as they see fit. | [5 empty] | Not assigned | 20
Actual timesheet - Week 28
Project | User | 04/06/2020 | 04/07/2020 | 04/08/2020 | 04/09/2020 | 04/10/2020 | 04/11/2020 | 04/12/2020 | Total | Billable total
Finance - SWEng Group 4 |  | 00:15:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:15:00 | 00:15:00
| Louis Newman | 00:15:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:15:00 | 00:15:00
Meetings - SWEng Group 4 |  | 04:30:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 04:30:00 | 04:30:00
| James Pearson | 00:45:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:45:00 | 00:45:00
| Louis Newman | 00:45:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:45:00 | 00:45:00
| Rebecca Anderson | 00:45:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:45:00 | 00:45:00
| Nathan Billis | 00:45:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:45:00 | 00:45:00
| Jun Ma | 00:45:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:45:00 | 00:45:00
| James Clawley | 00:45:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:45:00 | 00:45:00
Quality Manual - SWEng Group 4 |  | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:15:00 | 00:00:00 | 00:15:00 | 00:15:00
| James Pearson | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:15:00 | 00:00:00 | 00:15:00 | 00:15:00
Software - SWEng Group 4 |  | 05:00:00 | 02:00:00 | 06:30:00 | 02:00:00 | 00:30:00 | 00:00:00 | 00:00:00 | 16:00:00 | 16:00:00
| James Pearson | 00:00:00 | 00:00:00 | 01:00:00 | 02:00:00 | 00:30:00 | 00:00:00 | 00:00:00 | 03:30:00 | 03:30:00
| Louis Newman | 00:00:00 | 02:00:00 | 02:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 04:00:00 | 04:00:00
| Jun Ma | 01:00:00 | 00:00:00 | 01:45:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 02:45:00 | 02:45:00
| Joe Butler | 00:00:00 | 00:00:00 | 01:45:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 01:45:00 | 01:45:00
| James Clawley | 04:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 04:00:00 | 04:00:00
Marketing - SWEng Group 4 |  | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 02:00:00 | 00:00:00 | 00:00:00 | 02:00:00 | 02:00:00
| Rebecca Anderson | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 02:00:00 | 00:00:00 | 00:00:00 | 02:00:00 | 02:00:00
TOTAL |  | 09:45:00 | 02:00:00 | 06:30:00 | 02:00:00 | 02:30:00 | 00:15:00 | 00:00:00 | 23:00:00 | 23:00:00
[9 empty] | Total billable | 23 | Difference to predicted: | 0.5
Notes on labour for week 28: | Alterations from this prediction: | Two stories not picked up and assosiated time altered in change log.
| Finance manager comment from weekly timesheet: | The team had predicted 43.5 hours for this week, week 4 of iteration 2. We have gone under this week by 20.5 hours but in total is over on estimated hours by 32 for the entire project. At then end of last week, the team had an extra £336.54, this week we are still in the positive but from the extra work that has gone in this week we are at £592.79 extra in the pot, adding to our redundancy. The reason the team has gone under this week is due to the entire team effort being direrted to another module assignment brought about by Covid-19. This was unexpected and unforeseen in our estimations. However the team now has this redundancy in hours, where stories not completed this week must be pushed and made up in either the last week of this Iteration or the first weeks of Iteration 3. Some progress has been made this week but nothing substantial. The team has the hours available to catch up to where is should be but story estimates are going over in several areas. Specifics on this will be left to the team lead.
| Team lead comment from weekly timesheet: | Currently we are behind in our estimations on where we should be in the development of the application. The decision has been made to move the Healthy Living feature to the bottom of the plan as our idea of what the application is has changed since first conception. The change log has been updated to reflect these changes. Due to this, more hours from the second iteration should be available to put in to catching up. More pressure will need to be applied in areas to try and speed up development while not impacting the quality of the application and the ability for members of the team to focus in other areas of study. With some of the best developers tied up in big features, moving resources around to try and move things along will be tricky.
Other comments for week 28: | N/A
Estimated time - Week 29
Role | Name | Software | Design | Testing | Meetings | Finance | Administration | Total | stories not assigned
Project Manager | James Pearson |  |  |  | 1 |  | 2 | 3 | A13
Finance Manager | Louis Newman |  |  |  | 1 | 2 |  | 3
Design & Specification Manager | Joe Butler |  | 1.75 |  | 1 |  |  | 2.75
Lead Software Developer | James Clawley | 14 |  |  | 1 |  |  | 15
Testing & Integration Manager | Nathan Billis |  |  | 1.75 | 1 |  |  | 2.75
Marketing Manager | Becky Anderson |  |  |  | 1 |  |  | 1
XML & Server Manager | Jun Ma |  |  |  | 1 |  |  | 1
[7 empty] | Total: | 28.5
Reason for predicted hour distribution: | Hours assigned to team member taking lead on story to delegate as they see fit. | [5 empty] | Not assigned | 15
Actual timesheet - Week 29
Project | User | 04/13/2020 | 04/14/2020 | 04/15/2020 | 04/16/2020 | 04/17/2020 | 04/18/2020 | 04/19/2020 | Total | Billable total
Finance - SWEng Group 4 |  | 00:00:00 | 00:00:00 | 00:15:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:15:00 | 00:15:00
| Louis Newman | 00:00:00 | 00:00:00 | 00:15:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:15:00 | 00:15:00
Meetings - SWEng Group 4 |  | 03:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 03:00:00 | 03:00:00
| James Pearson | 00:30:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:30:00 | 00:30:00
| Louis Newman | 00:30:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:30:00 | 00:30:00
| Rebecca Anderson | 00:30:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:30:00 | 00:30:00
| Nathan Billis | 00:30:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:30:00 | 00:30:00
| Joe Butler | 00:30:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:30:00 | 00:30:00
| James Clawley | 00:30:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:30:00 | 00:30:00
Quality Manual - SWEng Group 4 |  | 00:30:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:30:00 | 00:30:00
| Rebecca Anderson | 00:15:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:15:00 | 00:15:00
| Nathan Billis | 00:15:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:15:00 | 00:15:00
Software - SWEng Group 4 |  | 00:00:00 | 03:00:00 | 00:30:14 | 02:00:00 | 03:00:00 | 05:00:00 | 18:30:00 | 32:00:14 | 32:00:14
| James Pearson | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 03:00:00 | 02:00:00 | 05:00:00 | 05:00:00
| Louis Newman | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 10:00:00 | 10:00:00 | 10:00:00
| Rebecca Anderson | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 01:30:00 | 01:30:00 | 01:30:00
| Nathan Billis | 00:00:00 | 00:00:00 | 00:00:00 | 02:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 02:00:00 | 02:00:00
| Joe Butler | 00:00:00 | 03:00:00 | 00:30:14 | 00:00:00 | 03:00:00 | 00:00:00 | 01:00:00 | 07:30:14 | 07:30:14
| James Clawley | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 02:00:00 | 04:00:00 | 06:00:00 | 06:00:00
Testing - SWEng Group 4 |  | 00:00:00 | 00:00:00 | 00:30:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:30:00 | 00:30:00
| Nathan Billis | 00:00:00 | 00:00:00 | 00:30:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:30:00 | 00:30:00
Marketing - SWEng Group 4 |  | 00:00:00 | 03:00:00 | 00:00:00 | 01:45:00 | 00:00:00 | 01:00:00 | 00:00:00 | 05:45:00 | 05:45:00
| Rebecca Anderson | 00:00:00 | 03:00:00 | 00:00:00 | 01:45:00 | 00:00:00 | 01:00:00 | 00:00:00 | 05:45:00 | 05:45:00
Administration - SWEng Group 4 |  | 00:15:00 | 00:00:00 | 00:00:00 | 00:15:00 | 00:00:00 | 00:30:00 | 00:15:00 | 01:15:00 | 01:15:00
| James Pearson | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:30:00 | 00:15:00 | 00:45:00 | 00:45:00
| Rebecca Anderson | 00:15:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:15:00 | 00:15:00
| Nathan Billis | 00:00:00 | 00:00:00 | 00:00:00 | 00:15:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:15:00 | 00:15:00
Design - SWEng Group 4 |  | 00:00:00 | 01:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 01:00:00 | 01:00:00
| Joe Butler | 00:00:00 | 01:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 01:00:00 | 01:00:00
TOTAL |  | 03:45:00 | 07:00:00 | 01:15:14 | 04:00:00 | 03:00:00 | 06:30:00 | 18:45:00 | 44:15:14 | 44:15:14
[9 empty] | Total billable | 44.25 | Difference to predicted: | -15.75
Notes on labour for week 29: | Alterations from this prediction: | One story not picked up and assosiated time altered in change log.
| Finance manager comment from weekly timesheet: | The team had predicted 43.5 hours for this week, week 5 of iteration 2. We have gone over on estimated hours in total of 32.75 for the entire project. We have only gone over on hours by 0.75 so have used up a very small amount of the company redundancy and so still have £583.41 extra in the pot. The company remains in a comfortable place financially. Timings have been close to expected with regards to the financial business plan, some stories have gone over so story progress is not entirely accurate. This time over in stories is mainly due to ensuring the product retains the quality envisioned. The financial redundancy should get the team through to completion however some stores have been dropped and recorded in the change log, however the team lead will elaborate on this aspect.
| Team lead comment from weekly timesheet: | Financially the company is on track but overall we are behind on feature development. Some features have had to be cut or pushed back depending on their overall importance to the companies vision of the application. The change log is updated with all these plan alterations. Overall the company is in a healthy position and if we stay on track with the revised plan we will hit our targets for an application that has unique features to bring value to the customers.
Other comments for week 29: | N/A
Estimated time - Week 30
Role | Name | Software | Design | Testing | Meetings | Finance | Administration | Total | stories not assigned
Project Manager | James Pearson | 12 |  |  | 1 |  | 2 | 15 | C10
Finance Manager | Louis Newman | 6 |  |  | 1 | 2 |  | 9
Design & Specification Manager | Joe Butler |  | 2.25 |  | 1 |  |  | 3.25
Lead Software Developer | James Clawley |  |  |  | 1 |  |  | 1
Testing & Integration Manager | Nathan Billis |  |  | 2.25 | 1 |  |  | 3.25
Marketing Manager | Becky Anderson |  |  |  | 1 |  |  | 1
XML & Server Manager | Jun Ma |  |  |  | 1 |  |  | 1
[7 empty] | Total: | 33.5
Reason for predicted hour distribution: | Hours assigned to team member taking lead on story to delegate as they see fit. | [5 empty] | Not assigned | 3.75
Actual timesheet - Week 30
Project | User | 04/20/2020 | 04/21/2020 | 04/22/2020 | 04/23/2020 | 04/24/2020 | 04/25/2020 | 04/26/2020 | Total | Billable total
Finance - SWEng Group 4 |  | 00:00:00 | 00:00:00 | 00:15:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:15:00 | 00:15:00
| Louis Newman | 00:00:00 | 00:00:00 | 00:15:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:15:00 | 00:15:00
Meetings - SWEng Group 4 |  | 03:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 03:00:00 | 03:00:00
| James Pearson | 00:30:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:30:00 | 00:30:00
| Louis Newman | 00:30:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:30:00 | 00:30:00
| Rebecca Anderson | 00:30:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:30:00 | 00:30:00
| Nathan Billis | 00:30:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:30:00 | 00:30:00
| Joe Butler | 00:30:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:30:00 | 00:30:00
| James Clawley | 00:30:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:30:00 | 00:30:00
Software - SWEng Group 4 |  | 02:00:00 | 02:00:00 | 02:00:00 | 05:00:00 | 05:00:00 | 03:30:00 | 03:00:00 | 22:30:00 | 22:30:00
| James Pearson | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 02:00:00 | 02:30:00 | 00:00:00 | 04:30:00 | 04:30:00
| Louis Newman | 00:00:00 | 00:00:00 | 00:00:00 | 03:00:00 | 00:00:00 | 00:00:00 | 03:00:00 | 06:00:00 | 06:00:00
| Rebecca Anderson | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 03:00:00 | 01:00:00 | 00:00:00 | 04:00:00 | 04:00:00
| Jun Ma | 00:00:00 | 02:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 02:00:00 | 02:00:00
| James Clawley | 02:00:00 | 00:00:00 | 02:00:00 | 02:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 06:00:00 | 06:00:00
Testing - SWEng Group 4 |  | 00:15:00 | 00:00:00 | 00:00:00 | 00:30:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:45:00 | 00:45:00
| Nathan Billis | 00:15:00 | 00:00:00 | 00:00:00 | 00:30:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:45:00 | 00:45:00
Administration - SWEng Group 4 |  | 00:30:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:30:00 | 00:30:00
| Rebecca Anderson | 00:30:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:30:00 | 00:30:00
HTML Tour - SWEng Group 4 |  | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:30:00 | 00:00:00 | 00:00:00 | 00:30:00 | 00:30:00
| Nathan Billis | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:30:00 | 00:00:00 | 00:00:00 | 00:30:00 | 00:30:00
TOTAL |  | 05:45:00 | 02:00:00 | 02:15:00 | 05:30:00 | 05:30:00 | 03:30:00 | 03:00:00 | 27:30:00 | 27:30:00
[9 empty] | Total billable | 27.5 | Difference to predicted: | 6
Notes on labour for week 30: | Alterations from this prediction: | One story not picked up and assosiated time altered in change log.
| Finance manager comment from weekly timesheet: | The team had predicted 37.25 hours for this week, week 1 of iteration 3. We have gone over on estimated hours in total of 23 hours for the entire project. This week alone we have gone under by 9.75 hours so have added to the company redundancy and so now have £705.41 extra in the pot. The company remains in a comfortable place financially. With the team having exams and assignment due dates coming up, some are focusing on these which has lead to the miscalculation is user time this week. We have not missed this mark by too much as a lot of the other members are still on task. As the team enters iteration 3, the application is all starting to come together nicely. Final usability is being added and in reference to the financial business plan, taking the change log into account, the team is on track to finish on time and in a comfortable financial position.
| Team lead comment from weekly timesheet: | With the reshuffling of the plan to focus on the more important aspects of the application, more hours can be assigned to the main features to flesh them out and make sure a quality product will be delivered in the coming weeks. Progress is coming along well on our main features. Overall, progress is good. Two members of the development team have been paired up on a problem to get that rectified this coming week which will put us in a good position coming towards the end of the project.
Other comments for week 30: | N/A
Financial updates from reporting period: | During this reporting period there have been a number of financial changes that are either a direct consequence of COVID-19 or due to development of the application requiring specific features. These features are required in order to bring increased capabilities to the application with the aim to increase user retention and usability.
Marteking update: | In light of COVID-19, our marketing strategy has to change. Getting rid of all face to face advertising. This however is not a bad thing, our marketing surveys tell us that 89% of people find out about a new app online. Focusing on this will reduce our overall marketing cost.
Author: Marketing Manager |  |  |  | Type of marketing | Price
|  |  |  | Social media ads & People working | 1500
|  |  |  | Influencers pay | 800
|  |  |  | Total | 2300
These figures come from 8 influencers with 10,000 mainly on Instagram and Facebook and the social media ads and people working covers the wage of someone who is in charge of the social media sites and the paid ads on different platforms I will need a total of 15 hours for the 3rd iteration to complete what is set out in the marketing plan
In-app search capability update: | Algolia Searching Finance Details
Author: Testing Manager | Pricing | Records | Operations | Additional Usage
| $29/mo | 50K | 250K | 100k operations: $10/month
20k records: $10/month
| $499/mo | 1M | 5M | 100k operations: $5/month
20k records: $5/month
https://www.algolia.com/pricing/
Benefits:
Search analytics
Abilities to roll out search updates without having to change the codebase
Used by industry leaders
99.999% uptime
We retain owners of our data at all times
Searching scales as the company scales
Our Analytics from the past 30 days (16/4/20)
Comments on update:
Initially Algolia will cost $29/month, once we reach 250k operations and 50k records. For every 100k operations over that it will cost $10/mo additional and for every 20k records it will also add $10/mo.
Team lead comments from reporting period: | Heading into iteration 3, changes have been made to the plan to increase the focus on the more important features of the application. The company’s vision of a cooking application with a social media aspect has taken priority over the healthy living system feature that was to implement calorie tracking and healthy diet options. These changes are reflected in the company’s change log with some user stories being removed from the plan completely or pushed to the end with the aim to implement if time allows. Hours for the stories moved off plan have been redistributed to newer stories that focus on the social media side of the app. This is with the aim of fully fleshing out our niche market feature and making sure that quality is delivered to the customer. Progress on the plan is going ok with some great strides being made. Some issues arose that slowed some progression but overall the company is in a healthy position and should deliver a quality application on time.
Final comments from Finance Manager: | The company remains in a strong and stable financial position. Where not all time estimations were correct and stories have over run in several places. Active financial management and strong negotiation during module sales has allowed the team to be slightly more flexible with the key stories to attain the quality level desired by the project. While there have been these under estimations in time and some over estimations in programmer capabilities, the majority of stories have aligned with predictions and the team is on course to complete all key stories for main application and USP with minor alterations within the change log. Even with the alterations brought on with COVID-19, the team is financially on track for a successful project.

## Financal Summary
Version control: 1.0 - Date: 20/05/2020
Financial Summary | Date: 20/05/2020 | SWEng Group 4
Author: | Codev Financial Manager | Louis Newman
Week number | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38
Week dates | Sep. 30, 2019-Oct. 6, 2019 | Oct. 7, 2019-Oct. 13, 2019 | Oct. 14, 2019-Oct. 20, 2019 | Oct. 21, 2019-Oct. 27, 2019 | Oct. 28, 2019-Nov. 3, 2019 | Nov. 4, 2019-Nov. 10, 2019 | Nov. 11, 2019-Nov. 17, 2019 | Nov. 18, 2019-Nov. 24, 2019 | Nov. 25, 2019-Dec. 1, 2019 | Dec. 2, 2019-Dec. 8, 2019 | Dec. 9, 2019-Dec. 15, 2019 | Dec. 16, 2019-Dec. 22, 2019 | Dec. 23, 2019-Dec. 29, 2019 | Dec. 30, 2019-Jan. 5, 2020 | Jan. 6, 2020-Jan. 12, 2020 | Jan. 13, 2020-Jan. 19, 2020 | Jan. 20, 2020-Jan. 26, 2020 | Jan. 27, 2020-Feb. 2, 2020 | Feb. 3, 2020-Feb. 9, 2020 | Feb. 10, 2020-Feb. 16, 2020 | Feb. 17, 2020-Feb. 23, 2020 | Feb. 24, 2020-Mar. 1, 2020 | Mar. 2, 2020-Mar. 8, 2020 | Mar. 9, 2020-Mar. 15, 2020 | Mar. 16, 2020-Mar. 22, 2020 | Mar. 23, 2020-Mar. 29, 2020 | Mar. 30, 2020-Apr. 5, 2020 | Apr. 6, 2020-Apr. 12, 2020 | Apr. 13, 2020-Apr. 19, 2020 | Apr. 20, 2020-Apr. 26, 2020 | Apr. 27, 2020-May 3, 2020 | May 4, 2020-May 10, 2020 | May 11, 2020-May 17, 2020 | May 18, 2020-May 24, 2020 | May 25, 2020-May 31, 2020 | June 1, 2020-June 7, 2020 | June 8, 2020-June 14, 2020 | June 15, 2020-June 21, 2020
Term week | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | Christmas | Christmas | Christmas | Christmas | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | Easter | Easter | Easter | Easter | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10
Project Iteration Stage | Preparation | Preparation | Preparation | Preparation | Preparation | Preparation | Preparation | Preparation | Preparation | Preparation | Preparation | Preparation | Preparation | Preparation | Preparation | Preparation | Preparation | Preparation | Iteration 1, week 1 | Iteration 1, week 2 | Iteration 1, week 3 | Iteration 1, week 4 | Iteration 1, week 5 | Iteration 1, week 6 | Iteration 2, week 1 | Iteration 2, week 2 | Iteration 2, week 3 | Iteration 2, week 4 | Iteration 2, week 5 | Iteration 3, week 1 | Iteration 3, week 2 | Iteration 3, week 3 | Iteration 3, week 4 | Iteration 3, week 5 | Presentation preparation | Presentation & hand in
Predicted
Predicted Module sales (IN)
Predicted Module purchases (OUT) | [21 empty] | -100 |  | -300
Predicted weekly hours | 0 | 0 | 0 | 7 | 8.25 | 8.25 | 8.5 | 7.75 | 20.25 | 14 | 0 | 0 | 0 | 0 | 0 | 45.25 | 67.5 | 35 | 47.75 | 59 | 58.5 | 42.5 | 46 | 29.25 | 47.25 | 34.75 | 28.5 | 43.5 | 43.5 | 37.25 | 47.25 | 29.75 | 31 | 43.5 | 75.25 | 7 | 0 | 0
Closing Balance | 0 | 0 | 0 | -2618.2692 | -2721.3942 | -3724.5192 | -5728.8462 | -5825.7212 | -6078.8462 | -8751.9231 | -8751.9231 | -8751.9231 | -8751.9231 | -8751.9231 | -8751.9231 | -9317.5481 | -10161.2981 | -15660.3365 | -16257.2115 | 9656.8626 | 6935.9627 | 6213.1398 | 5546.5668 | 2291.2919 | 1609.0939 | 1083.1459 | 635.323 | -1.9327e-12 | 15645.9959 | 15035.8372 | 14300.6784 | 14300.6784 | 8722.7312 | 8190.6975 | 6002.4138 | 3019.1781 | 2787.1444 | 2642.6107
Actual
Actual hours | 0 | 0 | 0 | 7 | 8.25 | 8.25 | 8.5 | 7.75 | 20.25 | 14 | 0 | 0 | 0 | 0 | 0 | 45.25 | 67.5 | 35 | 40.5 | 70.25 | 32.5 | 56.25 | 46.75 | 40 | 38.25 | 73.25 | 48.25 | 23 | 44.25 | 27.5 | 32.25 | 23.25 | 50.75
IN
Loans (IN) | [19 empty] | 28243.1471 | [8 empty] | 16334.2796
Module sales (IN) | [21 empty] | 263.53 |  | 790.58
OUT
Premises Rent |  |  |  | -2530.7692 |  |  | -1898.0769 |  |  | -1898.0769 | [7 empty] | -5061.5385 |  |  | -1898.0769 |  |  | -1898.0769 | [7 empty] | -5061.5385 |  |  | -1898.0769 |  |  | -1898.0769
Utilities Rent | [5 empty] | -300 |  |  |  | -200 | [9 empty] | -500 |  |  |  | -200 | [9 empty] | -500 |  |  |  | -200
IT infrastructure | [5 empty] | -600 |  |  |  | -400 | [9 empty] | -1000 |  |  |  | -400 | [9 empty] | -1000 |  |  |  | -400
Cost of Labour (12.5 GBP per hour) | 0 | 0 | 0 | -87.5 | -103.125 | -103.125 | -106.25 | -96.875 | -253.125 | -175 | 0 | 0 | 0 | 0 | 0 | -565.625 | -843.75 | -437.5 | -506.25 | -878.125 | -406.25 | -703.125 | -584.375 | -500 | -478.125 | -915.625 | -603.125 | -287.5 | -553.125 | -343.75 | -403.125 | -290.625 | -634.375 | 0 | 0 | 0 | 0 | 0
Weekly interest (16.86% APR) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -91.573 | -91.573 | -91.573 | -91.573 | -91.573 | -91.573 | -91.573 | -91.573 | -91.573 | -144.5337 | -144.5337 | -144.5337 | -144.5337 | -144.5337 | -144.5337 | -144.5337 | -144.5337 | -144.5337 | -144.5337
Module purchases (OUT) | [21 empty] | -115.33 |  | -345.99
Creditors
Total credit for loans | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28243.1471 | 28243.1471 | 28243.1471 | 28243.1471 | 28243.1471 | 28243.1471 | 28243.1471 | 28243.1471 | 28243.1471 | 44577.4268 | 44577.4268 | 44577.4268 | 44577.4268 | 44577.4268 | 44577.4268 | 44577.4268 | 44577.4268 | 44577.4268 | 44577.4268
Total credit recieved for modules | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 345.99 | 345.99 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total credit given for modules | [21 empty] | 790.58 | 790.58 | 0
Opening Balance | 0 | 0 | 0 | 0 | -2618.2692 | -2721.3942 | -3724.5192 | -5728.8462 | -5825.7212 | -6078.8462 | -8751.9231 | -8751.9231 | -8751.9231 | -8751.9231 | -8751.9231 | -8751.9231 | -9317.5481 | -10161.2981 | -15660.3365 | -16166.5865 | 9606.8626 | 7210.9627 | 6564.4648 | 5888.5168 | 3243.4569 | 2673.7589 | 1666.5609 | 971.863 | 592.79 | 16229.4109 | 15741.1272 | 15193.4684 | 9696.7712 | 8917.8625 | 7273.3288 | 5230.7181 | 5086.1844 | 4941.6507
OUT total | 0 | 0 | 0 | -2618.2692 | -103.125 | -1003.125 | -2004.3269 | -96.875 | -253.125 | -2673.0769 | 0 | 0 | 0 | 0 | 0 | -565.625 | -843.75 | -5499.0385 | -506.25 | -2469.698 | -2395.8999 | -910.028 | -675.948 | -3435.6399 | -569.698 | -1007.198 | -694.698 | -379.073 | -697.6587 | -488.2837 | -547.6587 | -5496.6972 | -778.9087 | -1644.5337 | -2042.6107 | -144.5337 | -144.5337 | -2642.6107
IN total | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28243.1471 | 0 | 263.53 | 0 | 790.58 | 0 | 0 | 0 | 0 | 16334.2796 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Closing Balance | 0 | 0 | 0 | -2618.2692 | -2721.3942 | -3724.5192 | -5728.8462 | -5825.7212 | -6078.8462 | -8751.9231 | -8751.9231 | -8751.9231 | -8751.9231 | -8751.9231 | -8751.9231 | -9317.5481 | -10161.2981 | -15660.3365 | -16166.5865 | 9606.8626 | 7210.9627 | 6564.4648 | 5888.5168 | 3243.4569 | 2673.7589 | 1666.5609 | 971.863 | 592.79 | 16229.4109 | 15741.1272 | 15193.4684 | 9696.7712 | 8917.8625 | 7273.3288 | 5230.7181 | 5086.1844 | 4941.6507 | 2299.04
Difference to prediction | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 90.625 | -50 | 275 | 351.325 | 341.95 | 952.165 | 1064.665 | 583.415 | 336.54 | 592.79 | 583.415 | 705.29 | 892.79 | 974.04 | 727.165 | 1270.915 | 2211.54 | 2299.04 | 2299.04 | 2299.04
Financial Reporting week 31-33
Estimated time - Week 31
Role | Name | Software | Design | Testing | Meetings | Finance | Administration | Total
Project Manager | James Pearson | 6 |  |  | 1 |  | 2 | 9 | Stories not taken | Type | Hours | [23 empty] | -632.6923
Finance Manager | Louis Newman |  |  |  | 1 | 2 |  | 3 | C25 | reccomended recipes | 10 | [21 empty] | rent 1 week
Design & Specification Manager | Joe Butler |  | 1.625 |  | 1 |  |  | 2.625 | C30 | recipe questions | 6 | [21 empty] | 450 util
Lead Software Developer | James Clawley |  |  |  | 1 |  |  | 1 | total not used: | (with design & testing) | 20 | [21 empty] | 900 IT
Testing & Integration Manager | Nathan Billis |  |  | 1.625 | 1 |  |  | 2.625
Marketing Manager | Becky Anderson | 7 |  |  | 1 |  |  | 8
XML & Server Manager | Jun Ma |  |  |  | 1 |  |  | 1 | [24 empty] | 632.6923
[7 empty] | Total: | 27.25 | [24 empty] | 450
Reason for predicted hour distribution: | Hours assigned to team member taking lead on story to delegate as they see fit. | [31 empty] | 900
1982.6923
Actual timesheet - Week 31
Project | User | 04/27/2020 | 04/28/2020 | 04/29/2020 | 04/30/2020 | 05/01/2020 | 05/02/2020 | 05/03/2020 | Total | Total billable
Finance - SWEng Group 4 |  | 00:00:00 | 00:00:00 | 02:45:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 02:45:00 | 02:45:00
| Louis Newman | 00:00:00 | 00:00:00 | 02:45:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 02:45:00 | 02:45:00
Meetings - SWEng Group 4 |  | 03:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 03:00:00 | 03:00:00
| James Pearson | 00:30:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:30:00 | 00:30:00
| Louis Newman | 00:30:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:30:00 | 00:30:00
| Rebecca Anderson | 00:30:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:30:00 | 00:30:00
| Nathan Billis | 00:30:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:30:00 | 00:30:00
| Jun Ma | 00:30:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:30:00 | 00:30:00
| James Clawley | 00:30:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:30:00 | 00:30:00
Software - SWEng Group 4 |  | 01:30:00 | 06:00:00 | 00:00:00 | 01:30:00 | 03:00:00 | 05:00:00 | 00:00:00 | 17:00:00 | 17:00:00
| James Pearson | 00:00:00 | 03:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 03:00:00 | 03:00:00
| Louis Newman | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 05:00:00 | 00:00:00 | 05:00:00 | 05:00:00
| Rebecca Anderson | 00:00:00 | 03:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 03:00:00 | 03:00:00
| Joe Butler | 01:30:00 | 00:00:00 | 00:00:00 | 01:30:00 | 03:00:00 | 00:00:00 | 00:00:00 | 06:00:00 | 06:00:00
Testing - SWEng Group 4 |  | 02:00:00 | 00:00:00 | 01:30:00 | 01:15:00 | 00:00:00 | 00:00:00 | 00:00:00 | 04:45:00 | 04:45:00
| Nathan Billis | 02:00:00 | 00:00:00 | 01:30:00 | 01:15:00 | 00:00:00 | 00:00:00 | 00:00:00 | 04:45:00 | 04:45:00
Administration - SWEng Group 4 |  | 00:45:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:15:00 | 01:00:00 | 01:00:00
| James Pearson | 00:15:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:15:00 | 00:30:00 | 00:30:00
| Rebecca Anderson | 00:30:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:30:00 | 00:30:00
Design - SWEng Group 4 |  | 00:00:00 | 00:00:00 | 00:00:00 | 02:30:00 | 00:00:00 | 00:00:00 | 00:00:00 | 02:30:00 | 02:30:00
| James Pearson | 00:00:00 | 00:00:00 | 00:00:00 | 02:30:00 | 00:00:00 | 00:00:00 | 00:00:00 | 02:30:00 | 02:30:00
HTML Tour - SWEng Group 4 |  | 01:15:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 01:15:00 | 01:15:00
| Joe Butler | 01:15:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 01:15:00 | 01:15:00
TOTAL |  | 08:30:00 | 06:00:00 | 04:15:00 | 05:15:00 | 03:00:00 | 05:00:00 | 00:15:00 | 32:15:00 | 32:15:00
[9 empty] | Billable total: | 32.25 | Difference to predicted: | -5
Notes on labour for week 31:
| Finance manager comment from weekly timesheet: | The team had predicted 47.25 hours for this week, week 2 of iteration 3. We have gone over on estimated hours in total of 8 for the entire project. We have gone under on hours this week by 15 so have added to the company redundancy which now stands at £892.79 extra in the pot. The company remains in a comfortable place financially. Due to deadlines and exams fast approaching, not all team members have been fully involved this week. With all change log items in place, the team is where is expected to be with regards to the Financial Business Plan. The team has the finances and hours required to finish the application. One item of note is that there was a mistake on C34 offering 5 hours of programming time when only 2 hours was budgeted. This mistake can be rectified with the company financial redundancy. Even with this extra time, the story is now finished but again went over this 5 hour limit coming out at 9.25 hours. Design manager leading this story may require some remedial training to stay on a specific task.
| Team lead comment from weekly timesheet: | Financially we're are in a good position but more alterations to the plan need to be made. Due to exams and other assignments production is down so focus needs to be on delivering our main features that have been backed up by the recent survey. This features are looking to be finished before the release in good time.
Other comments for week 31: | N/A
Estimated time - Week 32
Role | Name | Software | Design | Testing | Meetings | Finance | Administration | Total | Stories not taken | Type | Hours
Project Manager | James Pearson | 6 |  |  | 1 |  | 2 | 9 | A14 | recipe icons | 3
Finance Manager | Louis Newman |  |  |  | 1 | 2 |  | 3
Design & Specification Manager | Joe Butler | 6 | 1.5 |  | 1 |  |  | 8.5 | total not used: | (with design & testing) | 3.75
Lead Software Developer | James Clawley |  |  |  | 1 |  |  | 1
Testing & Integration Manager | Nathan Billis |  |  | 1.5 | 1 |  |  | 2.5
Marketing Manager | Becky Anderson |  |  |  | 1 |  |  | 1
XML & Server Manager | Jun Ma |  |  |  | 1 |  |  | 1
[7 empty] | Total: | 26
Reason for predicted hour distribution: | Hours assigned to team member taking lead on story to delegate as they see fit.
Actual timesheet - Week 32
Project | User | 05/04/2020 | 05/05/2020 | 05/06/2020 | 05/07/2020 | 05/08/2020 | 05/09/2020 | 05/10/2020 | Total | Billable total
Finance - SWEng Group 4 |  | 00:00:00 | 00:00:00 | 00:15:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:15:00 | 00:15:00
| Louis Newman | 00:00:00 | 00:00:00 | 00:15:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:15:00 | 00:15:00
Meetings - SWEng Group 4 |  | 03:30:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 03:30:00 | 03:30:00
| James Pearson | 00:30:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:30:00 | 00:30:00
| Louis Newman | 00:30:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:30:00 | 00:30:00
| Rebecca Anderson | 00:30:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:30:00 | 00:30:00
| Nathan Billis | 00:30:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:30:00 | 00:30:00
| Jun Ma | 00:30:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:30:00 | 00:30:00
| Joe Butler | 00:30:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:30:00 | 00:30:00
| James Clawley | 00:30:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:30:00 | 00:30:00
Software - SWEng Group 4 |  | 00:00:00 | 02:00:00 | 00:00:00 | 05:00:00 | 08:00:00 | 01:30:00 | 00:00:00 | 16:30:00 | 16:30:00
| James Pearson | 00:00:00 | 00:00:00 | 00:00:00 | 02:00:00 | 03:00:00 | 00:00:00 | 00:00:00 | 05:00:00 | 05:00:00
| Louis Newman | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 03:00:00 | 00:00:00 | 00:00:00 | 03:00:00 | 03:00:00
| Nathan Billis | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 01:30:00 | 00:00:00 | 01:30:00 | 01:30:00
| James Clawley | 00:00:00 | 02:00:00 | 00:00:00 | 03:00:00 | 02:00:00 | 00:00:00 | 00:00:00 | 07:00:00 | 07:00:00
Design - SWEng Group 4 |  | 01:30:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 01:30:00 | 01:30:00
| Joe Butler | 01:30:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 01:30:00 | 01:30:00
HTML Tour - SWEng Group 4 |  | 01:30:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 01:30:00 | 01:30:00
| Joe Butler | 01:30:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 01:30:00 | 01:30:00
TOTAL |  | 06:30:00 | 02:00:00 | 00:15:00 | 05:00:00 | 08:00:00 | 01:30:00 | 00:00:00 | 23:15:00 | 23:15:00
[9 empty] | Total billable | 23.25 | Difference to predicted: | 2.75
Notes on labour for week 32:
| Finance manager comment from weekly timesheet: | The team had predicted 29.75 hours for this week, week 3 of iteration 3. We have gone over on estimated hours in total of 1.5 for the entire project. We have gone under on hours this week by 6.5 so have added to the company redundancy which now stands at £974.04 extra in the pot. The company remains in a comfortable place financially. Team members have been preoccupied by other commitments recently due to other deadlines and exams, however this period is coming to a close and the company having a large financial redundancy due to the sale of modules still, some of the hourly restrictions and being slightly loosened in order to allow team members to finish the project to the high standard we have come to expect. Hours will remain closely watched, but members are no longer required to request extra hours and instead, trust is in place that all extra hours used during this period are going toward perfecting all aspects of the application ready for the completion of iteration 3.
| Team lead comment from weekly timesheet: | Final push to get everything done we can. I have diverted some of our resources to the development of the HTML tour and to the start of the Presentation to allow us some breathing room towards the end. Main features are looking polished and are near completion. Financially, in a very solid position giving us the ability to have a strong push before release to make sure that all features work as intended and that we have the quality of product that we strive for.
Other comments for week 32:
Estimated time - Week 33
Role | Name | Software | Design | Testing | Meetings | Finance | Administration | Total | Stories not taken | Type | Hours
Project Manager | James Pearson |  |  |  | 1 |  | 2 | 3 | C15 | disliked recipes | 3
Finance Manager | Louis Newman | 6 |  |  | 1 | 2 |  | 9
Design & Specification Manager | Joe Butler |  | 1.625 |  | 1 |  |  | 2.625 | total not used: | (with design & testing) | 3.75
Lead Software Developer | James Clawley |  |  |  | 1 |  |  | 1
Testing & Integration Manager | Nathan Billis |  |  | 1.625 | 1 |  |  | 2.625
Marketing Manager | Becky Anderson |  |  |  | 1 |  |  | 1
XML & Server Manager | Jun Ma | 7 |  |  | 1 |  |  | 8
[7 empty] | Total: | 27.25
Reason for predicted hour distribution: | Hours assigned to team member taking lead on story to delegate as they see fit.
Actual timesheet - Week 33
Project | User | 05/11/2020 | 05/12/2020 | 05/13/2020 | 05/14/2020 | 05/15/2020 | 05/16/2020 | 05/17/2020 | Total | total billable
Finance - SWEng Group 4 |  | 00:00:00 | 00:00:00 | 00:15:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:15:00 | 00:15:00
| Louis Newman | 00:00:00 | 00:00:00 | 00:15:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:15:00 | 00:15:00
Meetings - SWEng Group 4 |  | 01:45:00 | 03:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 04:45:00 | 04:45:00
| James Pearson | 00:00:00 | 00:45:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:45:00 | 00:45:00
| Louis Newman | 00:00:00 | 00:45:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:45:00 | 00:45:00
| Rebecca Anderson | 00:00:00 | 00:45:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:45:00 | 00:45:00
| Nathan Billis | 00:00:00 | 00:45:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:45:00 | 00:45:00
| Jun Ma | 00:30:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:30:00 | 00:30:00
| Joe Butler | 00:45:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:45:00 | 00:45:00
| James Clawley | 00:30:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:30:00 | 00:30:00
Software - SWEng Group 4 |  | 06:00:00 | 03:00:00 | 00:00:00 | 05:00:00 | 10:30:00 | 13:30:00 | 03:00:00 | 41:00:00 | 41:00:00
| James Pearson | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 03:00:00 | 04:00:00 | 00:00:00 | 07:00:00 | 07:00:00
| Louis Newman | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 05:00:00 | 06:00:00 | 03:00:00 | 14:00:00 | 14:00:00
| Rebecca Anderson | 00:00:00 | 02:30:00 | 00:00:00 | 03:00:00 | 01:30:00 | 02:00:00 | 00:00:00 | 09:00:00 | 09:00:00
| Nathan Billis | 03:00:00 | 00:30:00 | 00:00:00 | 00:00:00 | 01:00:00 | 00:00:00 | 00:00:00 | 04:30:00 | 04:30:00
| Jun Ma | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 01:30:00 | 00:00:00 | 01:30:00 | 01:30:00
| James Clawley | 03:00:00 | 00:00:00 | 00:00:00 | 02:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 05:00:00 | 05:00:00
Testing - SWEng Group 4 |  | 00:00:00 | 00:00:00 | 00:00:00 | 00:15:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:15:00 | 00:15:00
| Nathan Billis | 00:00:00 | 00:00:00 | 00:00:00 | 00:15:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:15:00 | 00:15:00
Marketing - SWEng Group 4 |  | 00:00:00 | 01:00:00 | 00:00:00 | 00:30:00 | 00:00:00 | 00:00:00 | 00:00:00 | 01:30:00 | 01:30:00
| Rebecca Anderson | 00:00:00 | 01:00:00 | 00:00:00 | 00:30:00 | 00:00:00 | 00:00:00 | 00:00:00 | 01:30:00 | 01:30:00
Administration - SWEng Group 4 |  | 00:15:00 | 00:30:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:15:00 | 01:00:00 | 01:00:00
| James Pearson | 00:15:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:15:00 | 00:30:00 | 00:30:00
| Rebecca Anderson | 00:00:00 | 00:30:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:30:00 | 00:30:00
Design - SWEng Group 4 |  | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 01:30:00 | 00:00:00 | 00:00:00 | 01:30:00 | 01:30:00
| Joe Butler | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 01:30:00 | 00:00:00 | 00:00:00 | 01:30:00 | 01:30:00
HTML Tour - SWEng Group 4 |  | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:30:00 | 00:00:00 | 00:00:00 | 00:30:00 | 00:30:00
| Nathan Billis | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:30:00 | 00:00:00 | 00:00:00 | 00:30:00 | 00:30:00
TOTAL |  | 08:00:00 | 07:30:00 | 00:15:00 | 05:45:00 | 12:30:00 | 13:30:00 | 03:15:00 | 50:45:00 | 50:45:00
[9 empty] | Total billable | 50.75 | Difference to predicted: | -23.5
Notes on labour for week 33:
| Finance manager comment from weekly timesheet: | The team had predicted 31 hours for this week, week 4 of iteration 3. We have gone over on estimated hours in total of 21.25 for the entire project. We have gone over on hours this week by 19.75 so have reduced the company redundancy which now stands at £727.17 extra in the pot. The company remains in a comfortable place financially. From going under last week, some of the team still have some exams left but the team is starting to return concentration to the SWEng effort in order to bring iteration 3 to a strong ending. To that end the team has gone over in hours but we have the redundancy to do so and since lifting hour restrictions last week the team has taken that into play with this week of labour. The team remains in a strong place financially and the restriction will remain off until the team has finished with a product we can be proud of.
| Team lead comment from weekly timesheet: | Echoing the Financial Manager, The company looks to be in a healthy position right up until the release date of the application. With maximum focus being brought back onto the project, we will be looking at ramping up the hours in development to make sure the application is as polished as possible and that any changes that need to be made as per the Design Survey results, can be made.
Other comments for week 33: | N/A
Financial updates from reporting period: | A better estimate of Firebase pricing is now avaliable due to usage data across several months with 7 developers. Particularly paying close attention to the last month of data, the application now hosts the majority of initial lauch expected capabilities giving a clearer picture of what costs may look like upon release.
Team lead comments on story alterations | Due to re-evaluating the plan the following user stories have been removed and will no longer be flagged for development. C25 has been removed due its complexity. The story is to produce recipes based on categories of recipes the user has made before. This requires a machine learning algorithm to implement and with the potential of having an incredible number of categories due to user created recipes, this is a little out of reach for the time we have available. C30 has been removed as a story as its very similar to another user story that was a part of the social side. Users are able to leave comments and reviews, so this story has effectively already been done. A14 has been removed as the time it would take to implement icons for every recipe and ingredient properly would be too long. This also adds no real value to application so spending critical development time on something that adds nothing it terms of functionality is a waste of the precious time we have left. C15 was removed completely as users can remove meals from the plan at any time, they like so it is now irrelevant. Due to these changes in the plan, 27.5 hours in total have been accrued. This time has already been reassigned to other areas of development.
Team lead comments from reporting period: | In the last few weeks development has slowed due to external factors such as exams and assignments. Within this time good progress has been made in some of key areas. The social aspect has made great strides and is very near completion. The team have also implemented a new search function that allows for a more robust searching. Coming towards the end of the third iteration and having the development team back at full capacity, we can make a final push to make sure that everything is polished and in fully working order. Due to the slowdown in development and the reorganising of the plan we have enough hours and financial strength to divert all resources to the tasks at hand.
Financial Project Summary
Team lead comments on financial status from project | Over the course of the project the company has been financially solid. There are numerous factors to consider why this has been the case. During Iteration 2, the decision was made to lower the time the group spent in meetings and to lower the time allocated to design after the first Iteration and design phase to allow more financial flexibility. This would allow us more funds to assign to features that would develop issues and take longer to implement. A big factor in the financial stability the company has had throughout the project is down to the contract negotiations and selling of our modules. Due to the successful negotiations the company accrued a large redundancy pot that could be allocated to the features that were very important and time consuming. For example, the social media side of the application was larger than originally estimated and the redundancy allowed the development to proceed as planned and for however long it took to get right. As we approach the end of the development phase and towards the release of the application, the company remains in a healthy financial position.
Breakdown of team labour over project-(30/09/19 - 10/05/20)
Project Labour Summary | Labour estimations have been mostly accurate throughout the project. We have gone over our estimate several times but the spare capacity from module sales allowed us this leeway. This over time allowed stories to be completed to the required standard and will pay dividends upon release.
Project overall financial summary | The team has remained in a strong place financially. All financial matters were directed though myself and I have been firm but fair with the team with labour and extra costs. I took the decision following the sale of modules to keep this money within the company instead of paying the bank back a small sum in order to relieve some of the interest we will pay in later months. I still believe this was the correct decision as it allowed the team to go over allocated hours in some stories to maintain our standards. All other costs have been set via contracts so predicted costs have matched up as expected. Estimating user time via hours allocated to contracts has worked well, where not completely accurate at times, the rough estimates have rounded out to expected costs.
Lessons learnt | All estimates should be made carefully, with significant research and group deliberation. The team should be firm with estimates and push to come in on time and target, however the team should also remember that these were purely estimates and in some cases leeway is sometimes required.
30/09/19 - 10/05/20 totals
|  | Premises Rent | 22144.2308
|  | Utilities Rent | 1700
|  | IT infrastructure | 3400
|  | Labour | 10859.375
|  | Weekly interest | 1835.8929
|  | Module purchases | 461.32
| CoDev Profit & Loss (30/09/19 - 10/05/20) |  |  | CoDev Balance sheet (10/05/20)
| Sales Revenue | 1054.11 |  | Fixed Assets
| Cost of Sales | 184.38 |  |  | Tangible fixed assets |  | 0
| Gross Profit | 869.73 |  |  | Financial fixed assets |  | 0
| Overheads | 24307.47
| Net Profit (PBIT) | -23437.74 |  | Current Assets
| Interest | 1546.83 |  |  | Cash in hand & at bank |  | 8917.86
| Profit Before Taxation | -24984.57 |  |  | Stock |  | 0
[5 empty] | Debtors |  | 0
Current Liabilities
Creditors
[5 empty] | Rent | -632.6923
[5 empty] | IT Infastructure | -900
[5 empty] | Utilities | -450
[5 empty] | Total: |  | -1982.6923
|  |  |  | Long term liabilities |  |  | -43030.6
|  |  |  | Net Assets |  |  | -36095.4323
Financial Performance over project | From the outset it was evident that learning the mechanics of the team, letting everyone work in their own best method while still attempting to hold the team to estimations of time would be difficult. Together as a team we estimated how long each story would take to program, at the beginning these estimations were slightly out due to must of the team overestimating their programming capabilities. As the project progressed, abilities caught up with projections and estimation got more accurate. For the most part, the team adhered to my guidelines, although some members still put in significantly more work than others, targets were met for the most part. A strong negotiation during the module sales enabled the team to have significantly extra money in the bank that allowed some restrictions on time to be relieved. This enabled the team to put extra time into key selling features and has led to a better product. The financial platform for the company has been solid throughout the project. Moving forward into deployment, we hope this solid financial platform gives investors reassurance that the company has what it takes to take Scran Plan to market for a strong return on investment.

## Business Plan going forward
| Each marketting campaign cost: | 2300
Marketting estimates
Following the first ad campaign - hope to generate 500 daily active users.
Following the second ad campaign - hope to have 2000 daily active users.
Following the third ad campaign - hope to have 5000 daily active users.
Following the fourth ad campaign - hope to generate 11,000daily active users.
Following the fifth ad campaign - hope to have 23,000 daily active users.
Following the sixth ad campaign - hope to have 47,000 daily active users.
If we run one ad campaign every 2 months in the first 6 months we can reach our 5000 DAU goal
Evenly splitting added users over each two month period gives the following results
[14 empty] | 1 | 1.5972
[14 empty] | 100 | 159.725
Revised Product Pricing | [13 empty] | 500 | 798.625
| Estimating that 10% of userbase opt for gold membership | [12 empty] | 1000 | 1597.25
| Time Frame | Value | Estimated user % | Averaged over 1 month/User | [9 empty] | 2000 | 3194.5
| Monthly | 1.99 | 50% | 0.995 | [9 empty] | 5000 | 7986.25
| Quarterly | 4.55 | 20% | 0.2275 | [9 empty] | 10000 | 15972.5
| Yearly | 14.99 | 30% | 0.37475 | [9 empty] | 50000 | 79862.5
|  |  | Average monthly per gold user | 1.5972 | [9 empty] | 100000 | 159725
| Free users will have access to the full application without the meal planner and with advetisments | [12 empty] | 1000000 | 1597250
Admob income is very difficult to estimate. As we are working with an application that is available in every country in the world and we need to rely on daily active users making impressions and clicks with the advertising. As we are aiming at students in the UK, we shall make a simplification here and specify that our average daily user is more likely to be from a tier 1 country (i.e. US, UK, Canada and Australia). Due to this we will estimate the average cost per click (CPC) to be around £0.27, we will estimate the click through rate (CTR) of our users to be around 1.1%. We will then estimate that our users will see roughly 4 pages of the application on each visit. This will give us an average Cost Per Thousand (CPM), which means the cost per 1000 pageviews, of £2.94. Using these assumptions, we can estimate potential revenue produced with free daily active users from ADMOB:
|  | Daily Users | Daily Income
|  | 1 | 0.0154 | 1 | 0.462
|  | 100 | 1.54 | 100 | 46.2
|  | 500 | 5.87 | 500 | 176.1
|  | 1000 | 11.75 | 1000 | 352.5
|  | 2000 | 23.5 | 2000 | 705
|  | 5000 | 58.74 | 5000 | 1762.2
|  | 10000 | 117.48 | 10000 | 3524.4
|  | 50000 | 587.41 | 50000 | 17622.3
|  | 100000 | 1174.83 | 100000 | 35244.9
|  | 1000000 | 11748.27 | 1000000 | 352448.1
Current loan | 44577.4268
Costs
Agolia (monthly) | 23.72
Google play store (one off) | 20.43
Labour | Monthly
Developers x 2 | 2500 | (25 HORUS)
Chef x 2 | 1920 | (20 HOURS)
Marketing | 1142.64 | (6 HOURS)
Bookkeeper | 150
5712.64
Month | July | August | September | October | November | December | January | February | March | April | May | June | July
Daily Active Users (start of month) | 0 | 250 | 500 | 1250 | 2000 | 3500 | 5000 | 8000 | 11000 | 17000 | 23000 | 35000 | 47000
Credit
Long term loan | 84577.4268 | 84577.4268 | 84577.4268 | 84577.4268 | 84577.4268 | 101577.4268 | 101577.4268 | 101577.4268 | 101577.4268 | 101577.4268 | 101577.4268 | 101577.4268 | 101577.4268
IN
Loans | 40000 |  |  |  |  | 17000
Montly free user Revenue | 0 | 103.95 | 207.9 | 519.75 | 831.6 | 1455.3 | 2079 | 3326.4 | 4573.8 | 7068.6 | 9563.4 | 14553 | 19542.6
Monthly gold user Revenue | 0 | 39.9312 | 79.8625 | 199.6562 | 319.45 | 559.0375 | 798.625 | 1277.8 | 1756.975 | 2715.325 | 3673.675 | 5590.375 | 7507.075
OUT
Labour
Developers labour | 2500 | 2500 | 2500 | 2500 | 2500 | 2500 | 2500 | 2500 | 2500 | 2500 | 2500 | 2500 | 2500
Chef labour | 1920 | 1920 | 1920 | 1920 | 1920 | 1920 | 1920 | 1920 | 1920 | 1920 | 1920 | 1920 | 1920
Marketing labour | 1142.64 | 1142.64 | 1142.64 | 1142.64 | 1142.64 | 1142.64 | 1142.64 | 1142.64 | 1142.64 | 1142.64 | 1142.64 | 1142.64 | 1142.64
Bookkeeper | 150 | 150 | 150 | 150 | 150 | 150 | 150 | 150 | 150 | 150 | 150 | 150 | 150
Other Overheads
Marketing Campaign | 1150 | 1150 | 1150 | 1150 | 1150 | 1150 | 1150 | 1150 | 1150 | 1150 | 1150 | 1150 | 1150
Adding to Google Play Store | 20.43 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Agolia | 23.72 | 23.72 | 23.72 | 23.72 | 23.72 | 23.72 | 23.72 | 23.72 | 23.72 | 23.72 | 23.72 | 23.72 | 23.72
Firebase hosting | 0.5945 | 0.5945 | 2.4928 | 8.7002 | 15.047 | 27.6504 | 40.5326 | 65.928 | 91.881 | 142.8522 | 194.9468 | 297.0778 | 401.431
Weekly interest (16.86% APR) | 1188.3128 | 1188.3128 | 1188.3128 | 1188.3128 | 1188.3128 | 1427.1628 | 1427.1628 | 1427.1628 | 1427.1628 | 1427.1628 | 1427.1628 | 1427.1628 | 1427.1628
Totals
Opening Balance | 0 | 31904.3027 | 23972.9166 | 16183.5134 | 8819.5466 | 1880.8768 | 12554.041 | 7077.6106 | 3302.3597 | 1227.7309 | 2555.2808 | 7283.8862 | 18816.6605
Total cash in | 40000 | 143.8812 | 287.7625 | 719.4062 | 1151.05 | 19014.3375 | 2877.625 | 4604.2 | 6330.775 | 9783.925 | 13237.075 | 20143.375 | 27049.675
Total cash out | 8095.6973 | 8075.2673 | 8077.1656 | 8083.373 | 8089.7198 | 8341.1732 | 8354.0554 | 8379.4508 | 8405.4038 | 8456.375 | 8508.4696 | 8610.6006 | 8714.9538
Net cash flow | 31904.3027 | -7931.3861 | -7789.4031 | -7363.9668 | -6938.6698 | 10673.1643 | -5476.4304 | -3775.2508 | -2074.6288 | 1327.55 | 4728.6054 | 11532.7744 | 18334.7212
Closing balance | 31904.3027 | 23972.9166 | 16183.5134 | 8819.5466 | 1880.8768 | 12554.041 | 7077.6106 | 3302.3597 | 1227.7309 | 2555.2808 | 7283.8862 | 18816.6605 | 37151.3817
CoDev Profit & Loss (July 2020 - July 2021) |  |  | CoDev Balance sheet July 2021
Sales Revenue | 88343.0875 |  | Fixed Assets
Cost of Sales | 0 |  |  | Tangible fixed assets |  | 0
Gross Profit | 88343.0875 |  |  | Financial fixed assets |  | 0
Overheads | 90832.8388
Net Profit (PBIT) | -2489.7513 |  | Current Assets
Interest | 17358.867 |  |  | Cash in hand & at bank |  | 37151.3817
Profit Before Taxation | -19848.6183 |  |  | Stock |  | 0
|  |  |  | Debtors |  | 0
|  |  | Current Liabilities |  |  | 0
|  |  | Long term liabilities |  |  | -101577.4268
|  |  | Net Assets |  |  | -64426.0451
| July | August | September | October | November | December | January | February | March | April | May | June | July
Monthly Revenue | 0 | 143.8812 | 287.7625 | 719.4062 | 1151.05 | 2014.3375 | 2877.625 | 4604.2 | 6330.775 | 9783.925 | 13237.075 | 20143.375 | 27049.675
Monthly Costs | 8095.6973 | 8075.2673 | 8077.1656 | 8083.373 | 8089.7198 | 8341.1732 | 8354.0554 | 8379.4508 | 8405.4038 | 8456.375 | 8508.4696 | 8610.6006 | 8714.9538
CoDev Balance sheet July 2021
Fixed Assets
[15 empty] | Tangible fixed assets | 0
[15 empty] | Financial fixed assets | 0
Current Assets
[15 empty] | Cash in hand & at bank | 37151.3817
[15 empty] | Stock | 0
[15 empty] | Debtors | 0
[14 empty] | Current Liabilities |  | 0
[14 empty] | Long term liabilities |  | -101577.4268
[14 empty] | Net Assets |  | -64426.0451
[14 empty] | 1 | 1.5972
[14 empty] | 100 | 159.725
Revised Product Pricing | [13 empty] | 500 | 798.625
| Estimating that 10% of userbase opt for gold membership | [12 empty] | 1000 | 1597.25
| Time Frame | Value | Estimated user % | Averaged over 1 year/User | [9 empty] | 2000 | 3194.5
| Monthly | 1.99 | 50% | 11.94 | [9 empty] | 5000 | 7986.25
| Quarterly | 4.99 | 20% | 3.992 | [9 empty] | 10000 | 15972.5
| Yearly | 14.99 | 30% | 4.497 | [9 empty] | 50000 | 79862.5
|  |  | Average monthly per gold user | 20.429 | [9 empty] | 100000 | 159725
| Free users will have access to the full application without the meal planner and with advetisments | [12 empty] | 1000000 | 1597250
Admob income is very difficult to estimate. As we are working with an application that is available in every country in the world and we need to rely on daily active users making impressions and clicks with the advertising. As we are aiming at students in the UK, we shall make a simplification here and specify that our average daily user is more likely to be from a tier 1 country (i.e. US, UK, Canada and Australia). Due to this we will estimate the average cost per click (CPC) to be around £0.27, we will estimate the click through rate (CTR) of our users to be around 1.1%. We will then estimate that our users will see roughly 4 pages of the application on each visit. This will give us an average Cost Per Thousand (CPM), which means the cost per 1000 pageviews, of £2.94. Using these assumptions, we can estimate potential revenue produced with free daily active users from ADMOB:
|  | Daily Users | Daily Income |  | Yearly income
|  | 1 | 0.0154 | 1 | 5.621
|  | 100 | 1.54 | 100 | 562.1
|  | 500 | 5.87 | 500 | 2142.55
|  | 1000 | 11.75 | 1000 | 4288.75
|  | 2000 | 23.5 | 2000 | 8577.5
|  | 5000 | 58.74 | 5000 | 21440.1
|  | 10000 | 117.48 | 10000 | 42880.2
|  | 50000 | 587.41 | 50000 | 214404.65
|  | 100000 | 1174.83 | 100000 | 428812.95
|  | 1000000 | 11748.27 | 1000000 | 4288118.55
Current loan | 44577.4268
Costs
Agolia (monthly) | 23.72
Google play store (one off) | 20.43
Labour | Monthly
Developers x 2 | 2500 | (25 HORUS)
Chef x 2 | 1920 | (20 HOURS)
Marketing | 1142.64 | (6 HOURS)
Bookkeeper | 150
5712.64

## Week 4 labour
Project | User | 10/21/2019 | 10/22/2019 | 10/23/2019 | 10/24/2019 | 10/25/2019 | 10/26/2019 | 10/27/2019 | Total | Project | Client | Description | Task | User | Email | Tags | Billable | Start Date | Start Time | End Date | End Time | Duration (h) | Duration (decimal) | Hourly Rate (GBP) | Amount (GBP)
Finance - SWEng Group 4 |  | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 01:00:00 | 00:00:00 | 00:00:00 | 01:00:00 | Meetings | SWEng Group 4 | Team meeting |  | Jb2200 | jb2200@york.ac.uk |  | Yes | 10/21/2019 | 9:00 | 10/21/2019 | 10:00 | 1:00 | 1 | 12.5 | 12.5
| Louis Newman | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 01:00:00 | 00:00:00 | 00:00:00 | 01:00:00 | Meetings | SWEng Group 4 | Team meeting |  | Jm2285 | jm2285@york.ac.uk |  | Yes | 10/21/2019 | 9:00 | 10/21/2019 | 10:00 | 1:00 | 1 | 12.5 | 12.5
Meetings - SWEng Group 4 |  | 06:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 06:00:00 | Meetings | SWEng Group 4 | Team meeting |  | Louis Newman | lifn501@york.ac.uk |  | Yes | 10/21/2019 | 10:00 | 10/21/2019 | 11:00 | 1:00 | 1 | 13.5 | 13.5
| Jp1439 | 01:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 01:00:00 | Meetings | SWEng Group 4 | Team meeting |  | Rea524 | rea524@york.ac.uk |  | Yes | 10/21/2019 | 10:00 | 10/21/2019 | 11:00 | 1:00 | 1 | 12.5 | 12.5
| Louis Newman | 01:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 01:00:00 | Meetings | SWEng Group 4 | Team meeting |  | James Clawley | jc2421@york.ac.uk |  | Yes | 10/21/2019 | 10:00 | 10/21/2019 | 11:00 | 1:00 | 1 | 12.5 | 12.5
| Rea524 | 01:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 01:00:00 | Meetings | SWEng Group 4 | Roles assigned, talking through ideas |  | Jp1439 | jp1439@york.ac.uk |  | Yes | 10/21/2019 | 10:00 | 10/21/2019 | 11:00 | 1:00 | 1 | 12.5 | 12.5
| Jm2285 | 01:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 01:00:00 | Finance | SWEng Group 4 | Basic outline of Financial Business Plan |  | Louis Newman | lifn501@york.ac.uk |  | Yes | 10/25/2019 | 11:00 | 10/25/2019 | 12:00 | 1:00 | 1 | 12.5 | 12.5
| Jb2200 | 01:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 01:00:00
| James Clawley | 01:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 01:00:00
TOTAL |  | 06:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 01:00:00 | 00:00:00 | 00:00:00 | 07:00:00
per hour £12.5
[8 empty] | total (£): | 7

## Week 5 Labour
Project | User | 10/28/2019 | 10/29/2019 | 10/30/2019 | 10/31/2019 | 11/01/2019 | 11/02/2019 | 11/03/2019 | Total |  | Project | Client | Description | Task | User | Email | Tags | Billable | Start Date | Start Time | End Date | End Time | Duration (h) | Duration (decimal) | Hourly Rate (GBP) | Amount (GBP)
Finance - SWEng Group 4 |  | 01:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 01:00:00 | 01:00:00 | Finance | SWEng Group 4 | Put together a basic outline of all current expenses |  | Louis Newman | lifn501@york.ac.uk |  | Yes | 10/28/2019 | 7:00 | 10/28/2019 | 8:00 | 1:00 | 1 | 12.5 | 12.5
| Louis Newman | 01:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 01:00:00 |  | Meetings | SWEng Group 4 | Team meeting |  | Louis Newman | lifn501@york.ac.uk |  | Yes | 10/28/2019 | 8:00 | 10/28/2019 | 9:00 | 1:00 | 1 | 13.5 | 13.5
Meetings - SWEng Group 4 |  | 06:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 06:00:00 | 06:00:00 | Meetings | SWEng Group 4 | Team meeting |  | Rea524 | rea524@york.ac.uk |  | Yes | 10/28/2019 | 9:00 | 10/28/2019 | 10:00 | 1:00 | 1 | 12.5 | 12.5
| Jp1439 | 01:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 01:00:00 |  | Meetings | SWEng Group 4 | Team meeting |  | Jb2200 | jb2200@york.ac.uk |  | Yes | 10/28/2019 | 9:00 | 10/28/2019 | 10:00 | 1:00 | 1 | 12.5 | 12.5
| Louis Newman | 01:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 01:00:00 |  | Meetings | SWEng Group 4 | Team meeting |  | James Clawley | jc2421@york.ac.uk |  | Yes | 10/28/2019 | 9:00 | 10/28/2019 | 10:00 | 1:00 | 1 | 12.5 | 12.5
| Rea524 | 01:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 01:00:00 |  | Meetings | SWEng Group 4 | Team meeting |  | Jm2285 | jm2285@york.ac.uk |  | Yes | 10/28/2019 | 9:00 | 10/28/2019 | 10:00 | 1:00 | 1 | 12.5 | 12.5
| Jm2285 | 01:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 01:00:00 |  | Meetings | SWEng Group 4 | Narrowed down ideas and talked through how we will operate |  | Jp1439 | jp1439@york.ac.uk |  | Yes | 10/28/2019 | 10:00 | 10/28/2019 | 11:00 | 1:00 | 1 | 12.5 | 12.5
| Jb2200 | 01:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 01:00:00 |  | Administration | SWEng Group 4 | Completing minutes after the meeting |  | Jp1439 | jp1439@york.ac.uk |  | Yes | 10/28/2019 | 11:00 | 10/28/2019 | 11:20 | 0:20 | 0.33333 | 12.5 | 4.17
| James Clawley | 01:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 01:00:00 |  | Software General | SWEng Group 4 | Created first android studio project and researched github stuff. |  | Jb2200 | jb2200@york.ac.uk |  | Yes | 10/29/2019 | 9:00 | 10/29/2019 | 9:10 | 0:10 | 0.16667 | 12.5 | 2.08
Software General - SWEng Group 4 |  | 00:00:00 | 00:10:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:10:00 | 0:00 | Research | SWEng Group 4 | Reached out to MOB Kitchen and BBC Good Food, also researched time sheets and costs |  | Louis Newman | lifn501@york.ac.uk |  | Yes | 10/29/2019 | 13:00 | 10/29/2019 | 14:00 | 1:00 | 1 | 12.5 | 12.5
| Jb2200 | 00:00:00 | 00:10:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:10:00 | 0:00
Administration - SWEng Group 4 |  | 00:20:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:20:00 | 0:15
| Jp1439 | 00:20:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:20:00 | 0:15
Research - SWEng Group 4 |  | 00:00:00 | 01:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 01:00:00 | 01:00:00
| Louis Newman | 00:00:00 | 01:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 01:00:00
TOTAL |  | 07:20:00 | 01:10:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 08:30:00 | 8:15
wages at £12.50
[8 empty] | weekly total: | 8.25
rounded down to nearest 15 mins

## Week 6 Labour
Project | User | 11/04/2019 | 11/05/2019 | 11/06/2019 | 11/07/2019 | 11/08/2019 | 11/09/2019 | 11/10/2019 | Total | Billable total | Project | Client | Description | Task | User | Email | Tags | Billable | Start Date | Start Time | End Date | End Time | Duration (h) | Duration (decimal) | Hourly Rate (GBP) | Amount (GBP)
Meetings - SWEng Group 4 |  | 05:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 01:00:00 | 06:00:00 | 4:00 | Meetings | SWEng Group 4 | Assign roles for the week |  | Louis Newman | lifn501@york.ac.uk |  | Yes | 11/04/2019 | 09:00:00 AM | 11/04/2019 | 09:40:00 AM | 00:40:00 | 0.66667 | 12.5 | 8.33
| Jp1439 | 00:40:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 01:00:00 | 01:40:00 | 1:30 | Meetings | SWEng Group 4 | Assign roles for the week |  | Jb2200 | jb2200@york.ac.uk |  | Yes | 11/04/2019 | 09:00:00 AM | 11/04/2019 | 09:40:00 AM | 00:40:00 | 0.66667 | 12.5 | 8.33
| Louis Newman | 00:40:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:40:00 | 0:30 | Meetings | SWEng Group 4 | Team meeting |  | James Clawley | jc2421@york.ac.uk |  | Yes | 11/04/2019 | 09:00:00 AM | 11/04/2019 | 10:00:00 AM | 01:00:00 | 1 | 12.5 | 12.5
| Rea524 | 00:40:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:40:00 | 0:30 | Meetings | SWEng Group 4 | Team meeting |  | Rea524 | rea524@york.ac.uk |  | Yes | 11/04/2019 | 10:00:00 AM | 11/04/2019 | 10:40:00 AM | 00:40:00 | 0.66667 | 12.5 | 8.33
| nathanbillis | 00:40:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:40:00 | 0:30 | Meetings | SWEng Group 4 | Team meeting |  | nathanbillis | ncab500@york.ac.uk |  | Yes | 11/04/2019 | 10:00:00 AM | 11/04/2019 | 10:40:00 AM | 00:40:00 | 0.66667 | 12.5 | 8.33
| Jm2285 | 00:40:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:40:00 | 0:30 | Meetings | SWEng Group 4 | Team meeting |  | Jm2285 | jm2285@york.ac.uk |  | Yes | 11/04/2019 | 10:00:00 AM | 11/04/2019 | 10:40:00 AM | 00:40:00 | 0.66667 | 12.5 | 8.33
| Jb2200 | 00:40:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:40:00 | 0:30 | Meetings | SWEng Group 4 | Team meeting |  | Jp1439 | jp1439@york.ac.uk |  | Yes | 11/04/2019 | 10:00:00 AM | 11/04/2019 | 10:40:00 AM | 00:40:00 | 0.66667 | 12.5 | 8.33
| James Clawley | 01:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 01:00:00 | 01:00:00 | Research | SWEng Group 4 | Listed android design requirements and best/worst case scenarios from existing apps. |  | Jb2200 | jb2200@york.ac.uk |  | Yes | 11/05/2019 | 02:09:12 PM | 11/05/2019 | 04:19:12 PM | 02:10:00 | 2.1667 | 12.5 | 27.08
Research - SWEng Group 4 |  | 00:00:00 | 02:51:35 | 00:00:00 | 01:00:00 | 01:30:00 | 00:00:00 | 01:55:46 | 07:17:21 | 4:15 | Research | SWEng Group 4 | Flashcard Design idea and implementation |  | Jb2200 | jb2200@york.ac.uk |  | Yes | 11/05/2019 | 04:43:02 PM | 11/05/2019 | 04:58:02 PM | 00:15:00 | 0.25 | 12.5 | 3.13
| Jp1439 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:55:46 | 00:55:46 | 0:45 | Research | SWEng Group 4 | Researching Apps in the current market |  | nathanbillis | ncab500@york.ac.uk |  | Yes | 11/05/2019 | 08:36:45 PM | 11/05/2019 | 09:03:20 PM | 00:26:35 | 0.44306 | 12.5 | 5.54
| Louis Newman | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 01:00:00 | 01:00:00 | 01:00:00 | Research | SWEng Group 4 | Collate Scranplan ideas with android and general design restrictions/ best practices |  | Jb2200 | jb2200@york.ac.uk |  | Yes | 11/07/2019 | 03:00:00 AM | 11/07/2019 | 04:00:00 AM | 01:00:00 | 1 | 12.5 | 12.5
| Rea524 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 01:30:00 | 00:00:00 | 00:00:00 | 01:30:00 | 01:30:00 | Research | SWEng Group 4 | Marketing research |  | Rea524 | rea524@york.ac.uk |  | Yes | 11/08/2019 | 10:00:00 PM | 11/08/2019 | 11:30:00 PM | 01:30:00 | 1.5 | 12.5 | 18.75
| nathanbillis | 00:00:00 | 00:26:35 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:26:35 | 0:15 | Research | SWEng Group 4 | Researched names, ways to make money and got all ideas down on the google drive |  | Louis Newman | lifn501@york.ac.uk |  | Yes | 11/10/2019 | 12:00:00 PM | 11/10/2019 | 01:00:00 PM | 01:00:00 | 1 | 12.5 | 12.5
| Jb2200 | 00:00:00 | 02:25:00 | 00:00:00 | 01:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 03:25:00 | 3:15 | Meetings | SWEng Group 4 | Setting up Monday agenda |  | Jp1439 | jp1439@york.ac.uk |  | Yes | 11/10/2019 | 12:00:00 PM | 11/10/2019 | 01:00:00 PM | 01:00:00 | 1 | 12.5 | 12.5
TOTAL |  | 05:00:00 | 02:51:35 | 00:00:00 | 01:00:00 | 01:30:00 | 00:00:00 | 02:55:46 | 13:17:21 | 8:15 | Research | SWEng Group 4 | Looking into online databases |  | Jp1439 | jp1439@york.ac.uk |  | Yes | 11/10/2019 | 02:14:25 PM | 11/10/2019 | 03:10:11 PM | 00:55:46 | 0.92944 | 12.5 | 11.62
wages at £12.5
[8 empty] | weekly total: | 8.25
all rounded down to nearest 15 mins

## Week 7 Labour
Project | User | 11/11/2019 | 11/12/2019 | 11/13/2019 | 11/14/2019 | 11/15/2019 | 11/16/2019 | 11/17/2019 | Total | Project | Client | Description | Task | User | Email | Tags | Billable | Start Date | Start Time | End Date | End Time | Duration (h) | Duration (decimal) | Hourly Rate (GBP) | Amount (GBP)
Meetings - SWEng Group 4 |  | 05:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:15:00 | 00:00:00 | 00:00:00 | 05:15:00 | Meetings | SWEng Group 4 | Team meeting |  | Rea524 | rea524@york.ac.uk |  | Yes | 11/11/2019 | 09:00:00 AM | 11/11/2019 | 10:00:00 AM | 01:00:00 | 1 | 12.5 | 12.5
| Jp1439 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:15:00 | 00:00:00 | 00:00:00 | 00:15:00 | Meetings | SWEng Group 4 | Team meeting |  | nathanbillis | ncab500@york.ac.uk |  | Yes | 11/11/2019 | 09:00:00 AM | 11/11/2019 | 10:00:00 AM | 01:00:00 | 1 | 12.5 | 12.5
| Louis Newman | 01:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 01:00:00 | Meetings | SWEng Group 4 | Team meeting |  | James Clawley | jc2421@york.ac.uk |  | Yes | 11/11/2019 | 09:00:00 AM | 11/11/2019 | 10:00:00 AM | 01:00:00 | 1 | 12.5 | 12.5
| Rea524 | 01:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 01:00:00 | Meetings | SWEng Group 4 | Team meeting |  | Louis Newman | lifn501@york.ac.uk |  | Yes | 11/11/2019 | 10:00:00 AM | 11/11/2019 | 11:00:00 AM | 01:00:00 | 1 | 12.5 | 12.5
| nathanbillis | 01:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 01:00:00 | Meetings | SWEng Group 4 | Team meeting |  | Jm2285 | jm2285@york.ac.uk |  | Yes | 11/11/2019 | 10:00:00 AM | 11/11/2019 | 11:00:00 AM | 01:00:00 | 1 | 12.5 | 12.5
| Jm2285 | 01:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 01:00:00 | Research | SWEng Group 4 | Marketing research |  | Rea524 | rea524@york.ac.uk |  | Yes | 11/13/2019 | 09:00:00 AM | 11/13/2019 | 09:45:00 AM | 00:45:00 | 0.75 | 12.5 | 9.38
| James Clawley | 01:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 01:00:00 | Quality Manual | SWEng Group 4 | Created QA Manual template |  | Jp1439 | jp1439@york.ac.uk |  | Yes | 11/15/2019 | 09:00:00 AM | 11/15/2019 | 10:30:00 AM | 01:30:00 | 1.5 | 12.5 | 18.75
Quality Manual - SWEng Group 4 |  | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 02:30:00 | 00:00:00 | 00:00:00 | 02:30:00 | Meetings | SWEng Group 4 | Finishing off minutes and writing agenda for next meeting |  | Jp1439 | jp1439@york.ac.uk |  | Yes | 11/15/2019 | 10:30:00 AM | 11/15/2019 | 10:45:00 AM | 00:15:00 | 0.25 | 12.5 | 3.13
| Jp1439 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 01:30:00 | 00:00:00 | 00:00:00 | 01:30:00 | Quality Manual | SWEng Group 4 | Started financial section of QA draft |  | Louis Newman | lifn501@york.ac.uk |  | Yes | 11/15/2019 | 07:00:00 PM | 11/15/2019 | 08:00:00 PM | 01:00:00 | 1 | 12.5 | 12.5
| Louis Newman | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 01:00:00 | 00:00:00 | 00:00:00 | 01:00:00
Research - SWEng Group 4 |  | 00:00:00 | 00:00:00 | 00:45:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:45:00
| Rea524 | 00:00:00 | 00:00:00 | 00:45:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:45:00
TOTAL |  | 05:00:00 | 00:00:00 | 00:45:00 | 00:00:00 | 02:45:00 | 00:00:00 | 00:00:00 | 08:30:00
12.5
[8 empty] | total: | 8.5

## Week 8 labour
Project | User | 11/18/2019 | 11/19/2019 | 11/20/2019 | 11/21/2019 | 11/22/2019 | 11/23/2019 | 11/24/2019 | Total | Project | Client | Description | Task | User | Email | Tags | Billable | Start Date | Start Time | End Date | End Time | Duration (h) | Duration (decimal) | Hourly Rate (GBP) | Amount (GBP)
Meetings - SWEng Group 4 |  | 05:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 05:00:00 | Meetings | SWEng Group 4 | Team meeting |  | Louis Newman | lifn501@york.ac.uk |  | Yes | 11/18/2019 | 09:00:00 AM | 11/18/2019 | 10:00:00 AM | 01:00:00 | 1 | 12.5 | 12.5
| Jp1439 | 01:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 01:00:00 | Meetings | SWEng Group 4 | Team meeting |  | Rea524 | rea524@york.ac.uk |  | Yes | 11/18/2019 | 09:00:00 AM | 11/18/2019 | 10:00:00 AM | 01:00:00 | 1 | 12.5 | 12.5
| Louis Newman | 01:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 01:00:00 | Meetings | SWEng Group 4 | Team meeting |  | James Clawley | jc2421@york.ac.uk |  | Yes | 11/18/2019 | 09:00:00 AM | 11/18/2019 | 10:00:00 AM | 01:00:00 | 1 | 12.5 | 12.5
| Rea524 | 01:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 01:00:00 | Meetings | SWEng Group 4 | Team meeting |  | Jp1439 | jp1439@york.ac.uk |  | Yes | 11/18/2019 | 09:00:00 AM | 11/18/2019 | 10:00:00 AM | 01:00:00 | 1 | 12.5 | 12.5
| Jm2285 | 01:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 01:00:00 | Meetings | SWEng Group 4 | Team meeting |  | Jm2285 | jm2285@york.ac.uk |  | Yes | 11/18/2019 | 10:00:00 AM | 11/18/2019 | 11:00:00 AM | 01:00:00 | 1 | 12.5 | 12.5
| James Clawley | 01:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 01:00:00 | Quality Manual | SWEng Group 4 | Completing marketing role |  | Rea524 | rea524@york.ac.uk |  | Yes | 11/23/2019 | 09:00:00 AM | 11/23/2019 | 09:30:00 AM | 00:30:00 | 0.5 | 12.5 | 6.25
Quality Manual - SWEng Group 4 |  | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 02:45:00 | 00:00:00 | 02:45:00 | Quality Manual | SWEng Group 4 | QA manual - Role |  | James Clawley | jc2421@york.ac.uk |  | Yes | 11/23/2019 | 09:00:00 AM | 11/23/2019 | 10:30:00 AM | 01:30:00 | 1.5 | 12.5 | 18.75
| Jp1439 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:45:00 | 00:00:00 | 00:45:00 | Quality Manual | SWEng Group 4 | QA Manual - Putting doc together |  | Jp1439 | jp1439@york.ac.uk |  | Yes | 11/23/2019 | 11:00:00 AM | 11/23/2019 | 11:45:00 AM | 00:45:00 | 0.75 | 12.5 | 9.38
| Rea524 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:30:00 | 00:00:00 | 00:30:00
| James Clawley | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 01:30:00 | 00:00:00 | 01:30:00
TOTAL |  | 05:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 02:45:00 | 00:00:00 | 07:45:00
12.5
[8 empty] | total: | 7.75

## Week 9 Labour
Project | User | 11/25/2019 | 11/26/2019 | 11/27/2019 | 11/28/2019 | 11/29/2019 | 11/30/2019 | 12/01/2019 | Total | Project | Client | Description | Task | User | Email | Tags | Billable | Start Date | Start Time | End Date | End Time | Duration (h) | Duration (decimal) | Hourly Rate (GBP) | Amount (GBP)
Finance - SWEng Group 4 |  | 01:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 01:00:00 | Quality Manual | SWEng Group 4 | Updated Design role QA description |  | Jb2200 | jb2200@york.ac.uk |  | Yes | 11/25/2019 | 12:00:00 AM | 11/25/2019 | 03:00:00 AM | 03:00:00 | 3 | 12.5 | 37.5
| Louis Newman | 01:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 01:00:00 | Meetings | SWEng Group 4 | Team meeting |  | Louis Newman | lifn501@york.ac.uk |  | Yes | 11/25/2019 | 09:00:00 AM | 11/25/2019 | 10:00:00 AM | 01:00:00 | 1 | 12.5 | 12.5
Meetings - SWEng Group 4 |  | 06:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:15:00 | 00:00:00 | 06:15:00 | Meetings | SWEng Group 4 | Team meeting |  | Rea524 | rea524@york.ac.uk |  | Yes | 11/25/2019 | 09:00:00 AM | 11/25/2019 | 10:00:00 AM | 01:00:00 | 1 | 12.5 | 12.5
| Jp1439 | 01:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:15:00 | 00:00:00 | 01:15:00 | Meetings | SWEng Group 4 | Team meeting |  | James Clawley | jc2421@york.ac.uk |  | Yes | 11/25/2019 | 09:00:00 AM | 11/25/2019 | 10:00:00 AM | 01:00:00 | 1 | 12.5 | 12.5
| Louis Newman | 01:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 01:00:00 | Meetings | SWEng Group 4 | Team meeting |  | Jp1439 | jp1439@york.ac.uk |  | Yes | 11/25/2019 | 09:00:00 AM | 11/25/2019 | 10:00:00 AM | 01:00:00 | 1 | 12.5 | 12.5
| Rea524 | 01:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 01:00:00 | Finance | SWEng Group 4 | Finances spreadsheet |  | Louis Newman | lifn501@york.ac.uk |  | Yes | 11/25/2019 | 10:00:00 AM | 11/25/2019 | 11:00:00 AM | 01:00:00 | 1 | 12.5 | 12.5
| nathanbillis | 01:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 01:00:00 | Meetings | SWEng Group 4 | Team meeting |  | nathanbillis | ncab500@york.ac.uk |  | Yes | 11/25/2019 | 10:00:00 AM | 11/25/2019 | 11:00:00 AM | 01:00:00 | 1 | 12.5 | 12.5
| Jm2285 | 01:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 01:00:00 | Meetings | SWEng Group 4 | Team meeting |  | Jm2285 | jm2285@york.ac.uk |  | Yes | 11/25/2019 | 10:00:00 AM | 11/25/2019 | 11:00:00 AM | 01:00:00 | 1 | 12.5 | 12.5
| James Clawley | 01:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 01:00:00 | Quality Manual | SWEng Group 4 | Work on QA manual |  | nathanbillis | ncab500@york.ac.uk |  | Yes | 11/26/2019 | 12:00:00 PM | 11/26/2019 | 01:15:00 PM | 01:15:00 | 1.25 | 12.5 | 15.63
Quality Manual - SWEng Group 4 |  | 03:00:00 | 01:15:00 | 02:00:00 | 04:00:00 | 00:30:00 | 01:45:00 | 00:30:00 | 13:00:00 | Quality Manual | SWEng Group 4 | Specifications and requirements |  | Louis Newman | lifn501@york.ac.uk |  | Yes | 11/27/2019 | 12:00:00 PM | 11/27/2019 | 02:00:00 PM | 02:00:00 | 2 | 12.5 | 25
| Jp1439 | 00:00:00 | 00:00:00 | 00:00:00 | 02:00:00 | 00:00:00 | 01:45:00 | 00:30:00 | 04:15:00 | Quality Manual | SWEng Group 4 | QA manual |  | James Clawley | jc2421@york.ac.uk |  | Yes | 11/28/2019 | 09:00:00 AM | 11/28/2019 | 11:00:00 AM | 02:00:00 | 2 | 12.5 | 25
| Louis Newman | 00:00:00 | 00:00:00 | 02:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 02:00:00 | Quality Manual | SWEng Group 4 | QA Manual |  | Jp1439 | jp1439@york.ac.uk |  | Yes | 11/28/2019 | 11:30:00 AM | 11/28/2019 | 01:30:00 PM | 02:00:00 | 2 | 12.5 | 25
| Rea524 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:30:00 | 00:00:00 | 00:00:00 | 00:30:00 | Quality Manual | SWEng Group 4 | QA Manual - Role and testing sections |  | Rea524 | rea524@york.ac.uk |  | Yes | 11/29/2019 | 09:00:00 AM | 11/29/2019 | 09:30:00 AM | 00:30:00 | 0.5 | 12.5 | 6.25
| nathanbillis | 00:00:00 | 01:15:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 01:15:00 | Meetings | SWEng Group 4 | Setting up agenda for meeting |  | Jp1439 | jp1439@york.ac.uk |  | Yes | 11/30/2019 | 03:15:00 PM | 11/30/2019 | 03:30:00 PM | 00:15:00 | 0.25 | 12.5 | 3.13
| Jb2200 | 03:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 03:00:00 | Quality Manual | SWEng Group 4 | QA Manual |  | Jp1439 | jp1439@york.ac.uk |  | Yes | 11/30/2019 | 03:30:00 PM | 11/30/2019 | 05:15:00 PM | 01:45:00 | 1.75 | 12.5 | 21.88
| James Clawley | 00:00:00 | 00:00:00 | 00:00:00 | 02:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 02:00:00 | Quality Manual | SWEng Group 4 | QA Manual |  | Jp1439 | jp1439@york.ac.uk |  | Yes | 12/01/2019 | 03:00:00 PM | 12/01/2019 | 03:30:00 PM | 00:30:00 | 0.5 | 12.5 | 6.25
TOTAL |  | 10:00:00 | 01:15:00 | 02:00:00 | 04:00:00 | 00:30:00 | 02:00:00 | 00:30:00 | 20:15:00
[8 empty] | total | 20.25

## Week 10 labour
Project | User | 12/02/2019 | 12/03/2019 | 12/04/2019 | 12/05/2019 | 12/06/2019 | 12/07/2019 | 12/08/2019 | Total | BillableTotal | Project | Client | Description | Task | User | Email | Tags | Billable | Start Date | Start Time | End Date | End Time | Duration (h) | Duration (decimal) | Hourly Rate (GBP) | Amount (GBP)
Meetings - SWEng Group 4 |  | 07:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 07:00:00 | 07:00:00 | Meetings | SWEng Group 4 | Team meeting |  | Rea524 | rea524@york.ac.uk |  | Yes | 2019-02-12 | 9:00 | 2019-02-12 | 10:00 | 1:00 | 1 | 12.5 | 12.5
| Jp1439 | 01:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 01:00:00 | 01:00:00 | Meetings | SWEng Group 4 | Team meeting |  | James Clawley | jc2421@york.ac.uk |  | Yes | 2019-02-12 | 9:00 | 2019-02-12 | 10:00 | 1:00 | 1 | 12.5 | 12.5
| Louis Newman | 01:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 01:00:00 | 01:00:00 | Meetings | SWEng Group 4 | Team meeting |  | Jp1439 | jp1439@york.ac.uk |  | Yes | 2019-02-12 | 9:00 | 2019-02-12 | 10:00 | 1:00 | 1 | 12.5 | 12.5
| Rea524 | 01:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 01:00:00 | 01:00:00 | Meetings | SWEng Group 4 | Team meeting |  | Louis Newman | lifn501@york.ac.uk |  | Yes | 2019-02-12 | 10:00 | 2019-02-12 | 11:00 | 1:00 | 1 | 12.5 | 12.5
| nathanbillis | 01:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 01:00:00 | 01:00:00 | Meetings | SWEng Group 4 | Team meeting |  | nathanbillis | ncab500@york.ac.uk |  | Yes | 2019-02-12 | 10:00 | 2019-02-12 | 11:00 | 1:00 | 1 | 12.5 | 12.5
| Jm2285 | 01:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 01:00:00 | 01:00:00 | Meetings | SWEng Group 4 | Team meeting |  | Jb2200 | jb2200@york.ac.uk |  | Yes | 2019-02-12 | 10:00 | 2019-02-12 | 11:00 | 1:00 | 1 | 12.5 | 12.5
| Jb2200 | 01:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 01:00:00 | 01:00:00 | Meetings | SWEng Group 4 | Team meeting |  | Jm2285 | jm2285@york.ac.uk |  | Yes | 2019-02-12 | 10:00 | 2019-02-12 | 11:00 | 1:00 | 1 | 12.5 | 12.5
| James Clawley | 01:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 01:00:00 | 01:00:00 | Quality Manual | SWEng Group 4 | Created Design specification QA description, integrated github with Trello and edited specification .drawio flow diagram to fit requirements. |  | Jb2200 | jb2200@york.ac.uk |  | Yes | 2019-02-12 | 18:20 | 2019-02-12 | 21:20 | 3:00 | 3 | 12.5 | 37.5
Quality Manual - SWEng Group 4 |  | 03:00:00 | 02:00:49 | 02:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 07:00:49 | 7:00 | Quality Manual | SWEng Group 4 | Time sheet information |  | Louis Newman | lifn501@york.ac.uk |  | Yes | 2019-03-12 | 9:00 | 2019-03-12 | 10:00 | 1:00 | 1 | 12.5 | 12.5
| Louis Newman | 00:00:00 | 01:00:00 | 02:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 03:00:00 | 03:00:00 | Quality Manual | SWEng Group 4 | working on QA |  | nathanbillis | ncab500@york.ac.uk |  | Yes | 2019-03-12 | 13:29 | 2019-03-12 | 14:30 | 1:01 | 1.0136 | 12.5 | 12.67
| nathanbillis | 00:00:00 | 01:00:49 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 01:00:49 | 1:00 | Quality Manual | SWEng Group 4 | Editing layout, adding time sheet details |  | Louis Newman | lifn501@york.ac.uk |  | Yes | 2019-04-12 | 8:00 | 2019-04-12 | 9:00 | 1:00 | 1 | 12.5 | 12.5
| Jb2200 | 03:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 03:00:00 | 03:00:00 | Quality Manual | SWEng Group 4 | Adding pair programming deatils |  | Louis Newman | lifn501@york.ac.uk |  | Yes | 2019-04-12 | 16:26 | 2019-04-12 | 17:26 | 1:00 | 1 | 12.5 | 12.5
TOTAL |  | 10:00:00 | 02:00:49 | 02:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 14:00:49 | 14:00
[8 empty] | total: | 14

## Week 16 labour
Project | User | 01/13/2020 | 01/14/2020 | 01/15/2020 | 01/16/2020 | 01/17/2020 | 01/18/2020 | 01/19/2020 | Total | Billable Total | Project | Client | Description | Task | User | Email | Tags | Billable | Start Date | Start Time | End Date | End Time | Duration (h) | Duration (decimal) | Hourly Rate (GBP) | Amount (GBP)
Meetings - SWEng Group 4 |  | 03:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 03:00:00 | 03:00:00 | Meetings | SWEng Group 4 | Team meeting |  | Rea524 | rea524@york.ac.uk |  | Yes | 01/13/2020 | 09:00:00 AM | 01/13/2020 | 09:30:00 AM | 00:30:00 | 0.5 | 12.5 | 6.25
| Jp1439 | 00:30:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:30:00 | 00:30:00 | Meetings | SWEng Group 4 | Team meeting -> welcome back and set tasks for financial business plan. Also set everyone to write user stories to begin road map. |  | Louis Newman | lifn501@york.ac.uk |  | Yes | 01/13/2020 | 11:00:00 AM | 01/13/2020 | 11:30:00 AM | 00:30:00 | 0.5 | 12.5 | 6.25
| Louis Newman | 00:30:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:30:00 | 00:30:00 | Meetings | SWEng Group 4 | Team Meeting |  | nathanbillis | ncab500@york.ac.uk |  | Yes | 01/13/2020 | 11:00:00 AM | 01/13/2020 | 11:30:00 AM | 00:30:00 | 0.5 | 12.5 | 6.25
| Rea524 | 00:30:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:30:00 | 00:30:00 | Meetings | SWEng Group 4 | Team meeting |  | Jb2200 | jb2200@york.ac.uk |  | Yes | 01/13/2020 | 11:00:00 AM | 01/13/2020 | 11:30:00 AM | 00:30:00 | 0.5 | 12.5 | 6.25
| nathanbillis | 00:30:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:30:00 | 00:30:00 | Meetings | SWEng Group 4 | Team meeting |  | Jm2285 | jm2285@york.ac.uk |  | Yes | 01/13/2020 | 11:00:00 AM | 01/13/2020 | 11:30:00 AM | 00:30:00 | 0.5 | 12.5 | 6.25
| Jm2285 | 00:30:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:30:00 | 00:30:00 | Meetings | SWEng Group 4 | Team Meeting |  | Jp1439 | jp1439@york.ac.uk |  | Yes | 01/13/2020 | 11:00:00 AM | 01/13/2020 | 11:30:00 AM | 00:30:00 | 0.5 | 12.5 | 6.25
| Jb2200 | 00:30:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:30:00 | 00:30:00 | Administration | SWEng Group 4 | started Functional Spec document formatting |  | Jp1439 | jp1439@york.ac.uk |  | Yes | 01/14/2020 | 01:00:00 PM | 01/14/2020 | 02:30:00 PM | 01:30:00 | 1.5 | 12.5 | 18.75
Administration - SWEng Group 4 |  | 00:00:00 | 01:30:00 | 00:00:00 | 07:45:00 | 06:30:00 | 00:00:00 | 04:00:00 | 19:45:00 | 19:45:00 | User Stories | SWEng Group 4 | Wrote user stories |  | Jp1439 | jp1439@york.ac.uk |  | Yes | 01/14/2020 | 02:30:00 PM | 01/14/2020 | 03:15:00 PM | 00:45:00 | 0.75 | 12.5 | 9.38
| Jp1439 | 00:00:00 | 01:30:00 | 00:00:00 | 03:45:00 | 05:00:00 | 00:00:00 | 00:00:00 | 10:15:00 | 10:15:00 | User Stories | SWEng Group 4 | Writing up user stories |  | Rea524 | rea524@york.ac.uk |  | Yes | 01/15/2020 | 09:00:00 AM | 01/15/2020 | 10:00:00 AM | 01:00:00 | 1 | 12.5 | 12.5
| nathanbillis | 00:00:00 | 00:00:00 | 00:00:00 | 02:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 02:00:00 | 02:00:00 | User Stories | SWEng Group 4 |  |  | James Clawley | jc2421@york.ac.uk |  | Yes | 01/15/2020 | 09:00:00 AM | 01/15/2020 | 11:00:00 AM | 02:00:00 | 2 | 12.5 | 25
| Jb2200 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 04:00:00 | 04:00:00 | 04:00:00 | User Stories | SWEng Group 4 | Writing up features as user stories |  | Louis Newman | lifn501@york.ac.uk |  | Yes | 01/15/2020 | 01:00:00 PM | 01/15/2020 | 02:30:00 PM | 01:30:00 | 1.5 | 12.5 | 18.75
| James Clawley | 00:00:00 | 00:00:00 | 00:00:00 | 02:00:00 | 01:30:00 | 00:00:00 | 00:00:00 | 03:30:00 | 03:30:00 | User Stories | SWEng Group 4 | User Stories - creation of user stories |  | nathanbillis | ncab500@york.ac.uk |  | Yes | 01/15/2020 | 08:00:00 PM | 01/15/2020 | 08:30:00 PM | 00:30:00 | 0.5 | 12.5 | 6.25
Research - SWEng Group 4 |  | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 02:45:00 | 02:45:00 | 02:45:00 | User Stories | SWEng Group 4 | writing up user stories, formatting correctly and sorting through |  | Rea524 | rea524@york.ac.uk |  | Yes | 01/16/2020 | 09:00:00 AM | 01/16/2020 | 12:00:00 PM | 03:00:00 | 3 | 12.5 | 37.5
| Louis Newman | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 02:00:00 | 02:00:00 | 02:00:00 | Administration | SWEng Group 4 | Functional Spec |  | James Clawley | jc2421@york.ac.uk |  | Yes | 01/16/2020 | 09:00:00 AM | 01/16/2020 | 11:00:00 AM | 02:00:00 | 2 | 12.5 | 25
| nathanbillis | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:45:00 | 00:45:00 | 00:45:00 | User Stories | SWEng Group 4 | Reformatting all user stories to have requirements and tests |  | Louis Newman | lifn501@york.ac.uk |  | Yes | 01/16/2020 | 01:00:00 PM | 01/16/2020 | 03:00:00 PM | 02:00:00 | 2 | 12.5 | 25
User Stories - SWEng Group 4 |  | 00:00:00 | 00:45:00 | 05:00:00 | 12:10:50 | 00:00:00 | 00:00:00 | 02:00:00 | 19:55:50 | 19:45 | Administration | SWEng Group 4 | Functional User Spec - Research into existing Functional User Specs and working on the configuration section of the spec. |  | nathanbillis | ncab500@york.ac.uk |  | Yes | 01/16/2020 | 01:00:00 PM | 01/16/2020 | 03:00:00 PM | 02:00:00 | 2 | 12.5 | 25
| Jp1439 | 00:00:00 | 00:45:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:45:00 | 00:45:00 | User Stories | SWEng Group 4 | User stories (Server related only) |  | Jb2200 | jb2200@york.ac.uk |  | Yes | 01/16/2020 | 01:00:00 PM | 01/16/2020 | 04:30:00 PM | 03:30:00 | 3.5 | 12.5 | 43.75
| Louis Newman | 00:00:00 | 00:00:00 | 01:30:00 | 03:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 04:30:00 | 04:30:00 | User Stories | SWEng Group 4 | teamwork |  | Jm2285 | jm2285@york.ac.uk |  | Yes | 01/16/2020 | 01:00:00 PM | 01/16/2020 | 03:40:50 PM | 02:40:50 | 2.6806 | 12.5 | 33.51
| Rea524 | 00:00:00 | 00:00:00 | 01:00:00 | 03:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 04:00:00 | 04:00:00 | Administration | SWEng Group 4 | Working on Functional Specification |  | Jp1439 | jp1439@york.ac.uk |  | Yes | 01/16/2020 | 01:00:00 PM | 01/16/2020 | 04:45:00 PM | 03:45:00 | 3.75 | 12.5 | 46.88
| nathanbillis | 00:00:00 | 00:00:00 | 00:30:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:30:00 | 00:30:00 | User Stories | SWEng Group 4 | Finished writing up user stories |  | Louis Newman | lifn501@york.ac.uk |  | Yes | 01/16/2020 | 07:00:00 PM | 01/16/2020 | 08:00:00 PM | 01:00:00 | 1 | 12.5 | 12.5
| Jm2285 | 00:00:00 | 00:00:00 | 00:00:00 | 02:40:50 | 00:00:00 | 00:00:00 | 00:00:00 | 02:40:50 | 2:30 | Administration | SWEng Group 4 | Functional spec |  | James Clawley | jc2421@york.ac.uk |  | Yes | 01/17/2020 | 09:00:00 AM | 01/17/2020 | 10:30:00 AM | 01:30:00 | 1.5 | 12.5 | 18.75
| Jb2200 | 00:00:00 | 00:00:00 | 00:00:00 | 03:30:00 | 00:00:00 | 00:00:00 | 02:00:00 | 05:30:00 | 05:30:00 | Administration | SWEng Group 4 | Setting up project Gantt chart. Problem with Uni comps and had to restart in Project manager. Excel Gantt not good enough |  | Jp1439 | jp1439@york.ac.uk |  | Yes | 01/17/2020 | 10:30:00 AM | 01/17/2020 | 12:30:00 PM | 02:00:00 | 2 | 12.5 | 25
| James Clawley | 00:00:00 | 00:00:00 | 02:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 02:00:00 | 02:00:00 | Administration | SWEng Group 4 | Setting up project roadmap and correcting iterations in func spec |  | Jp1439 | jp1439@york.ac.uk |  | Yes | 01/17/2020 | 02:00:00 PM | 01/17/2020 | 05:00:00 PM | 03:00:00 | 3 | 12.5 | 37.5
TOTAL |  | 03:00:00 | 02:15:00 | 05:00:00 | 19:55:50 | 06:30:00 | 00:00:00 | 08:45:00 | 45:25:50 | 45:15 | Research | SWEng Group 4 | Researched Firestore duplication for social feed and build the risks section of the functional specification and added 4 risks for: (Server data structure), (Server document limits), (Feature creep) and (Star rating system in conjunction with number of reviews). Also found an excellent course through Fireship.io for data modelling and cloud functions. |  | Louis Newman | lifn501@york.ac.uk |  | Yes | 01/19/2020 | 04:00:00 PM | 01/19/2020 | 06:00:00 PM | 02:00:00 | 2 | 12.5 | 25
[8 empty] | hours paid: | 45.15 |  | Research | SWEng Group 4 | Premium Features - Researched and added a list of ideas for premium features to the team drive |  | nathanbillis | ncab500@york.ac.uk |  | Yes | 01/19/2020 | 06:15:00 PM | 01/19/2020 | 07:00:00 PM | 00:45:00 | 0.75 | 12.5 | 9.38
[8 empty] | total: | 565.625 |  | User Stories | SWEng Group 4 | Finalising initial user stories for server compatibility. Also adding vital privacy policy user story to user interaction section. |  | Jb2200 | jb2200@york.ac.uk |  | Yes | 01/19/2020 | 08:30:00 PM | 01/19/2020 | 10:30:00 PM | 02:00:00 | 2 | 12.5 | 25
[11 empty] | Administration | SWEng Group 4 | Added 4 risks (server host limits), (capacity), (hardware implementation and testing) and (versioning) in the functional specification |  | Jb2200 | jb2200@york.ac.uk |  | Yes | 01/19/2020 | 11:00:00 PM | 01/20/2020 | 03:00:00 AM | 04:00:00 | 4 | 12.5 | 50

## Week 17 labour
Project | User | 01/20/2020 | 01/21/2020 | 01/22/2020 | 01/23/2020 | 01/24/2020 | 01/25/2020 | 01/26/2020 | Total | Billable Total | Project | Client | Description | Task | User | Email | Tags | Billable | Start Date | Start Time | End Date | End Time | Duration (h) | Duration (decimal) | Hourly Rate (GBP) | Amount (GBP)
Finance - SWEng Group 4 |  | 01:00:00 | 00:00:00 | 00:00:00 | 03:30:00 | 00:00:00 | 00:00:00 | 01:00:00 | 05:30:00 | 05:30:00 | Finance | SWEng Group 4 | Updated weekly finance, paying for previous week, checked functional specification and added all stories as tasks to software |  | Louis Newman | lifn501@york.ac.uk |  | Yes | 01/20/2020 | 10:00:00 AM | 01/20/2020 | 11:00:00 AM | 01:00:00 | 1 | 12.5 | 12.5
| Louis Newman | 01:00:00 | 00:00:00 | 00:00:00 | 01:30:00 | 00:00:00 | 00:00:00 | 01:00:00 | 03:30:00 | 03:30:00 | Meetings | SWEng Group 4 | Team meeting |  | Rea524 | rea524@york.ac.uk |  | Yes | 01/20/2020 | 10:00:00 AM | 01/20/2020 | 10:45:00 AM | 00:45:00 | 0.75 | 12.5 | 9.38
| Jm2285 | 00:00:00 | 00:00:00 | 00:00:00 | 02:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 02:00:00 | 02:00:00 | Meetings | SWEng Group 4 | Booked session for Friday and talked about functional specification |  | Louis Newman | lifn501@york.ac.uk |  | Yes | 01/20/2020 | 11:00:00 AM | 01/20/2020 | 12:00:00 PM | 01:00:00 | 1 | 12.5 | 12.5
Meetings - SWEng Group 4 |  | 05:55:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:15:00 | 06:10:00 | 6:00 | Meetings | SWEng Group 4 | Team Meeting |  | nathanbillis | ncab500@york.ac.uk |  | Yes | 01/20/2020 | 11:00:00 AM | 01/20/2020 | 11:30:00 AM | 00:30:00 | 0.5 | 12.5 | 6.25
| Jp1439 | 01:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:15:00 | 01:15:00 | 01:15:00 | Meetings | SWEng Group 4 | Meeting |  | Jb2200 | jb2200@york.ac.uk |  | Yes | 01/20/2020 | 11:00:00 AM | 01/20/2020 | 12:00:00 PM | 01:00:00 | 1 | 12.5 | 12.5
| Louis Newman | 01:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 01:00:00 | 01:00:00 | Meetings | SWEng Group 4 | Team Meeting |  | James Clawley | jc2421@york.ac.uk |  | Yes | 01/20/2020 | 11:00:00 AM | 01/20/2020 | 12:00:00 PM | 01:00:00 | 1 | 12.5 | 12.5
| Rea524 | 00:45:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:45:00 | 00:45:00 | Meetings | SWEng Group 4 | team meeting |  | Jm2285 | jm2285@york.ac.uk |  | Yes | 01/20/2020 | 11:00:00 AM | 01/20/2020 | 11:40:00 AM | 00:40:00 | 0.66667 | 12.5 | 8.33
| nathanbillis | 00:30:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:30:00 | 00:30:00 | Meetings | SWEng Group 4 | Monday morning meeting |  | Jp1439 | jp1439@york.ac.uk |  | Yes | 01/20/2020 | 11:00:00 AM | 01/20/2020 | 12:00:00 PM | 01:00:00 | 1 | 12.5 | 12.5
| Jm2285 | 00:40:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:40:00 | 0:30 | Design | SWEng Group 4 | Designed mock UI |  | James Clawley | jc2421@york.ac.uk |  | Yes | 01/20/2020 | 02:00:00 PM | 01/20/2020 | 03:00:00 PM | 01:00:00 | 1 | 12.5 | 12.5
| Jb2200 | 01:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 01:00:00 | 01:00:00 | Design | SWEng Group 4 | Created mockup recipe design in Xcode (iOS) whilst using android icons + design principles |  | Jb2200 | jb2200@york.ac.uk |  | Yes | 01/21/2020 | 10:30:00 PM | 01/22/2020 | 02:30:00 AM | 04:00:00 | 4 | 12.5 | 50
| James Clawley | 01:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 01:00:00 | 01:00:00 | Administration | SWEng Group 4 | Adding user stories on Trello ready for organizing after user story rating session. Stories available now for development |  | Jp1439 | jp1439@york.ac.uk |  | Yes | 01/22/2020 | 08:30:00 AM | 01/22/2020 | 10:30:00 AM | 02:00:00 | 2 | 12.5 | 25
Software - SWEng Group 4 |  | 00:00:00 | 00:00:00 | 00:00:00 | 09:00:00 | 00:00:00 | 03:45:00 | 00:00:00 | 12:45:00 | 12:45:00 | Design | SWEng Group 4 | Added timeline design (from Xcode mockup design using android image elements) |  | Jb2200 | jb2200@york.ac.uk |  | Yes | 01/22/2020 | 11:00:00 PM | 01/23/2020 | 12:00:00 AM | 01:00:00 | 1 | 12.5 | 12.5
| Louis Newman | 00:00:00 | 00:00:00 | 00:00:00 | 02:00:00 | 00:00:00 | 03:45:00 | 00:00:00 | 05:45:00 | 05:45:00 | Marketing | SWEng Group 4 | making a finance marketing plan. researching different marketing techniques and trying to reduce money spent. |  | Rea524 | rea524@york.ac.uk |  | Yes | 01/23/2020 | 09:00:00 AM | 01/23/2020 | 11:00:00 AM | 02:00:00 | 2 | 12.5 | 25
| nathanbillis | 00:00:00 | 00:00:00 | 00:00:00 | 02:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 02:00:00 | 02:00:00 | Software | SWEng Group 4 | Started programming - Working on side menu |  | James Clawley | jc2421@york.ac.uk |  | Yes | 01/23/2020 | 09:00:00 AM | 01/23/2020 | 12:00:00 PM | 03:00:00 | 3 | 12.5 | 37.5
| Jb2200 | 00:00:00 | 00:00:00 | 00:00:00 | 02:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 02:00:00 | 02:00:00 | Software | SWEng Group 4 | Attached project to firebase and made sure project was ready to go |  | Louis Newman | lifn501@york.ac.uk |  | Yes | 01/23/2020 | 01:00:00 PM | 01/23/2020 | 03:00:00 PM | 02:00:00 | 2 | 12.5 | 25
| James Clawley | 00:00:00 | 00:00:00 | 00:00:00 | 03:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 03:00:00 | 03:00:00 | Software | SWEng Group 4 | Working on side menus and learning about android studio. |  | nathanbillis | ncab500@york.ac.uk |  | Yes | 01/23/2020 | 01:00:00 PM | 01/23/2020 | 03:00:00 PM | 02:00:00 | 2 | 12.5 | 25
Marketing - SWEng Group 4 |  | 00:00:00 | 00:00:00 | 00:00:00 | 02:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 02:00:00 | 02:00:00 | Software | SWEng Group 4 | Created Firebase and setup github with Louis |  | Jb2200 | jb2200@york.ac.uk |  | Yes | 01/23/2020 | 01:00:00 PM | 01/23/2020 | 03:00:00 PM | 02:00:00 | 2 | 12.5 | 25
| Rea524 | 00:00:00 | 00:00:00 | 00:00:00 | 02:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 02:00:00 | 02:00:00 | Finance | SWEng Group 4 | Focus on the cost of firebase and list the needed products of firebase |  | Jm2285 | jm2285@york.ac.uk |  | Yes | 01/23/2020 | 01:00:00 PM | 01/23/2020 | 03:00:00 PM | 02:00:00 | 2 | 12.5 | 25
Administration - SWEng Group 4 |  | 00:00:00 | 00:00:00 | 02:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 02:00:00 | 04:00:00 | 04:00:00 | Finance | SWEng Group 4 | Built revenue model |  | Louis Newman | lifn501@york.ac.uk |  | Yes | 01/23/2020 | 04:00:00 PM | 01/23/2020 | 05:00:00 PM | 01:00:00 | 1 | 12.5 | 12.5
| Jp1439 | 00:00:00 | 00:00:00 | 02:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 02:00:00 | 04:00:00 | 04:00:00 | Finance | SWEng Group 4 | Continued building revenue model and researched attaching an android project to firebase for authentication |  | Louis Newman | lifn501@york.ac.uk |  | Yes | 01/23/2020 | 07:00:00 PM | 01/23/2020 | 07:30:00 PM | 00:30:00 | 0.5 | 12.5 | 6.25
Research - SWEng Group 4 |  | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 03:00:00 | 00:00:00 | 03:00:00 | 03:00:00 | User Stories | SWEng Group 4 | Going though the users stories and establishing agreed values for value,risk and time to complete |  | Rea524 | rea524@york.ac.uk |  | Yes | 01/24/2020 | 09:00:00 AM | 01/24/2020 | 01:00:00 PM | 04:00:00 | 4 | 12.5 | 50
| Jb2200 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 03:00:00 | 00:00:00 | 03:00:00 | 03:00:00 | User Stories | SWEng Group 4 | User stories |  | James Clawley | jc2421@york.ac.uk |  | Yes | 01/24/2020 | 09:00:00 AM | 01/24/2020 | 01:00:00 PM | 04:00:00 | 4 | 12.5 | 50
User Stories - SWEng Group 4 |  | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 28:00:00 | 00:15:00 | 00:00:00 | 28:15:00 | 28:15:00 | User Stories | SWEng Group 4 | Rated all user stories as a full team |  | Louis Newman | lifn501@york.ac.uk |  | Yes | 01/24/2020 | 12:00:00 PM | 01/24/2020 | 04:00:00 PM | 04:00:00 | 4 | 12.5 | 50
| Jp1439 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 04:00:00 | 00:15:00 | 00:00:00 | 04:15:00 | 04:15:00 | User Stories | SWEng Group 4 | User story classification |  | nathanbillis | ncab500@york.ac.uk |  | Yes | 01/24/2020 | 12:00:00 PM | 01/24/2020 | 04:00:00 PM | 04:00:00 | 4 | 12.5 | 50
| Louis Newman | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 04:00:00 | 00:00:00 | 00:00:00 | 04:00:00 | 04:00:00 | User Stories | SWEng Group 4 | Assessed user stories value and risks |  | Jb2200 | jb2200@york.ac.uk |  | Yes | 01/24/2020 | 12:00:00 PM | 01/24/2020 | 04:00:00 PM | 04:00:00 | 4 | 12.5 | 50
| Rea524 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 04:00:00 | 00:00:00 | 00:00:00 | 04:00:00 | 04:00:00 | User Stories | SWEng Group 4 | team discussion about user stories |  | Jm2285 | jm2285@york.ac.uk |  | Yes | 01/24/2020 | 12:00:00 PM | 01/24/2020 | 04:00:00 PM | 04:00:00 | 4 | 12.5 | 50
| nathanbillis | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 04:00:00 | 00:00:00 | 00:00:00 | 04:00:00 | 04:00:00 | User Stories | SWEng Group 4 | Ranking user stories |  | Jp1439 | jp1439@york.ac.uk |  | Yes | 01/24/2020 | 12:00:00 PM | 01/24/2020 | 04:00:00 PM | 04:00:00 | 4 | 12.5 | 50
| Jm2285 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 04:00:00 | 00:00:00 | 00:00:00 | 04:00:00 | 04:00:00 | Research | SWEng Group 4 | Created notes from Bucky Roberts (newboston) java android development tutorials for the first 1/4 of his series. Mainly UI stuff. Also updated everyone on next weeks meeting agenda and design/QA alternations fro QA metrics that need to be made before the QA deadline |  | Jb2200 | jb2200@york.ac.uk |  | Yes | 01/25/2020 | 01:30:00 PM | 01/25/2020 | 03:30:00 PM | 02:00:00 | 2 | 12.5 | 25
| Jb2200 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 04:00:00 | 00:00:00 | 00:00:00 | 04:00:00 | 04:00:00 | Software | SWEng Group 4 | Researching how java uses the firebase and looked into preparation of sign in and register pages |  | Louis Newman | lifn501@york.ac.uk |  | Yes | 01/25/2020 | 03:30:00 PM | 01/25/2020 | 07:15:00 PM | 03:45:00 | 3.75 | 12.5 | 46.88
| James Clawley | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 04:00:00 | 00:00:00 | 00:00:00 | 04:00:00 | 04:00:00 | User Stories | SWEng Group 4 | Creating high risk high reward graph for further planning |  | Jp1439 | jp1439@york.ac.uk |  | Yes | 01/25/2020 | 03:30:00 PM | 01/25/2020 | 03:45:00 PM | 00:15:00 | 0.25 | 12.5 | 3.13
Design - SWEng Group 4 |  | 01:00:00 | 04:00:00 | 01:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 06:00:00 | 06:00:00 | Research | SWEng Group 4 | Research into junit testing |  | Jb2200 | jb2200@york.ac.uk |  | Yes | 01/25/2020 | 04:00:00 PM | 01/25/2020 | 05:00:00 PM | 01:00:00 | 1 | 12.5 | 12.5
| Jb2200 | 00:00:00 | 04:00:00 | 01:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 05:00:00 | 05:00:00 | Finance | SWEng Group 4 | Prep for finance meeting with Tony |  | Louis Newman | lifn501@york.ac.uk |  | Yes | 01/26/2020 | 10:00:00 AM | 01/26/2020 | 11:00:00 AM | 01:00:00 | 1 | 12.5 | 12.5
| James Clawley | 01:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 01:00:00 | 01:00:00 | Administration | SWEng Group 4 | Created doc for risk reward graph and iterations. Assigned user stories to iterations |  | Jp1439 | jp1439@york.ac.uk |  | Yes | 01/26/2020 | 11:30:00 AM | 01/26/2020 | 01:30:00 PM | 02:00:00 | 2 | 12.5 | 25
TOTAL |  | 07:55:00 | 04:00:00 | 03:00:00 | 14:30:00 | 28:00:00 | 07:00:00 | 03:15:00 | 67:40:00 | 67:30 | Meetings | SWEng Group 4 | Agenda and Minutes prep |  | Jp1439 | jp1439@york.ac.uk |  | Yes | 01/26/2020 | 03:00:00 PM | 01/26/2020 | 03:15:00 PM | 00:15:00 | 0.25 | 12.5 | 3.13
[8 empty] | total: | 67.5

## Week 18 labour
Project | User | 01/27/2020 | 01/28/2020 | 01/29/2020 | 01/30/2020 | 01/31/2020 | 02/01/2020 | 02/02/2020 | Total | Total Billable | Project | Client | Description | Task | User | Email | Tags | Billable | Start Date | Start Time | End Date | End Time | Duration (h) | Duration (decimal) | Hourly Rate (GBP) | Amount (GBP)
Finance - SWEng Group 4 |  | 00:50:00 | 00:00:00 | 00:30:00 | 03:00:00 | 00:00:00 | 01:00:00 | 02:30:00 | 07:50:00 | 7:45 | Meetings | SWEng Group 4 | group team meeting |  | Rea524 | rea524@york.ac.uk |  | Yes | 01/27/2020 | 9:00 | 01/27/2020 | 10:00 | 1:00 | 1 | 12.50 GBP | 12.50 GBP
| Louis Newman | 00:50:00 | 00:00:00 | 00:00:00 | 01:00:00 | 00:00:00 | 01:00:00 | 02:30:00 | 05:20:00 | 5:15 | Meetings | SWEng Group 4 | Team Meeting |  | James Clawley | jc2421@york.ac.uk |  | Yes | 01/27/2020 | 9:00 | 01/27/2020 | 10:00 | 1:00 | 1 | 12.50 GBP | 12.50 GBP
| Rea524 | 00:00:00 | 00:00:00 | 00:30:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:30:00 | 00:30:00 | Meetings | SWEng Group 4 | Team meeting |  | Jp1439 | jp1439@york.ac.uk |  | Yes | 01/27/2020 | 9:00 | 01/27/2020 | 10:00 | 1:00 | 1 | 12.50 GBP | 12.50 GBP
| Jm2285 | 00:00:00 | 00:00:00 | 00:00:00 | 02:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 02:00:00 | 02:00:00 | Software | SWEng Group 4 | Programming tab layout into appplication | User story C2 | James Clawley | jc2421@york.ac.uk |  | Yes | 01/27/2020 | 10:00 | 01/27/2020 | 10:45 | 0:45 | 0.75 | 12.50 GBP | 9.38 GBP
Meetings - SWEng Group 4 |  | 06:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 06:00:00 | 00:00:00 | 00:00:00 | 12:00:00 | 12:00:00 | Software | SWEng Group 4 | Programming recipe layouts on main screen | User story C1 | James Clawley | jc2421@york.ac.uk |  | Yes | 01/27/2020 | 10:45 | 01/27/2020 | 11:30 | 0:45 | 0.75 | 12.50 GBP | 9.38 GBP
| Jp1439 | 01:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 01:00:00 | 01:00:00 | Meetings | SWEng Group 4 | Team meeting |  | Louis Newman | lifn501@york.ac.uk |  | Yes | 01/27/2020 | 11:00 | 01/27/2020 | 12:00 | 1:00 | 1 | 12.50 GBP | 12.50 GBP
| Louis Newman | 01:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 01:30:00 | 00:00:00 | 00:00:00 | 02:30:00 | 02:30:00 | Meetings | SWEng Group 4 | Team Meeting |  | Jb2200 | jb2200@york.ac.uk |  | Yes | 01/27/2020 | 11:00 | 01/27/2020 | 12:00 | 1:00 | 1 | 12.50 GBP | 12.50 GBP
| Rea524 | 01:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 01:30:00 | 00:00:00 | 00:00:00 | 02:30:00 | 02:30:00 | Meetings | SWEng Group 4 | Team meeting |  | Jm2285 | jm2285@york.ac.uk |  | Yes | 01/27/2020 | 11:00 | 01/27/2020 | 12:00 | 1:00 | 1 | 12.50 GBP | 12.50 GBP
| nathanbillis | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 01:30:00 | 00:00:00 | 00:00:00 | 01:30:00 | 01:30:00 | Finance | SWEng Group 4 | Prep for meeting with Financial Advisor |  | Louis Newman | lifn501@york.ac.uk |  | Yes | 01/27/2020 | 13:00 | 01/27/2020 | 13:30 | 0:30 | 0.5 | 12.50 GBP | 6.25 GBP
| Jm2285 | 01:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 01:30:00 | 00:00:00 | 00:00:00 | 02:30:00 | 02:30:00 | Finance | SWEng Group 4 | Meeting with Financial Advisor |  | Louis Newman | lifn501@york.ac.uk |  | Yes | 01/27/2020 | 14:00 | 01/27/2020 | 14:20 | 0:20 | 0.33 | 12.50 GBP | 4.17 GBP
| Jb2200 | 01:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 01:00:00 | 01:00:00 | Software | SWEng Group 4 | Researched JUnit testing and implemented first JUnit 4 test example. Checks for an exception if an ‘@‘ symbol is within an input email string. |  | Jb2200 | jb2200@york.ac.uk |  | Yes | 01/29/2020 | 3:15 | 01/29/2020 | 3:45 | 0:30 | 0.5 | 12.50 GBP | 6.25 GBP
| James Clawley | 01:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 01:00:00 | 01:00:00 | Finance | SWEng Group 4 | Calculating finance for marketing and estimating users we expect to get |  | Rea524 | rea524@york.ac.uk |  | Yes | 01/29/2020 | 9:00 | 01/29/2020 | 9:30 | 0:30 | 0.5 | 12.50 GBP | 6.25 GBP
Quality Manual - SWEng Group 4 |  | 00:00:00 | 00:00:00 | 01:15:00 | 02:00:00 | 02:15:00 | 00:00:00 | 00:00:00 | 05:30:00 | 05:30:00 | Quality Manual | SWEng Group 4 | QA Manual adjustments |  | James Clawley | jc2421@york.ac.uk |  | Yes | 01/29/2020 | 9:00 | 01/29/2020 | 9:15 | 0:15 | 0.25 | 12.50 GBP | 3.13 GBP
| Jp1439 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 01:30:00 | 00:00:00 | 00:00:00 | 01:30:00 | 01:30:00 | Quality Manual | SWEng Group 4 | Updated QA manual to include information on how hours will be tracked, enable individual programming when pair programming is non-viable and updated metrics for myself the financial manager. Also spoke to team lead in reference to all changes and all recommendations communicated. |  | Louis Newman | lifn501@york.ac.uk |  | Yes | 01/29/2020 | 16:00 | 01/29/2020 | 17:00 | 1:00 | 1 | 12.50 GBP | 12.50 GBP
| Louis Newman | 00:00:00 | 00:00:00 | 01:00:00 | 01:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 02:00:00 | 02:00:00 | Quality Manual | SWEng Group 4 | Adapting QA manual for submission |  | Rea524 | rea524@york.ac.uk |  | Yes | 01/30/2020 | 9:00 | 01/30/2020 | 10:00 | 1:00 | 1 | 12.50 GBP | 12.50 GBP
| Rea524 | 00:00:00 | 00:00:00 | 00:00:00 | 01:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 01:00:00 | 01:00:00 | Administration | SWEng Group 4 | Rewriting parts of the functional spec following feedback |  | Rea524 | rea524@york.ac.uk |  | Yes | 01/30/2020 | 10:00 | 01/30/2020 | 11:00 | 1:00 | 1 | 12.50 GBP | 12.50 GBP
| James Clawley | 00:00:00 | 00:00:00 | 00:15:00 | 00:00:00 | 00:45:00 | 00:00:00 | 00:00:00 | 01:00:00 | 01:00:00 | Finance | SWEng Group 4 | Financial business plan layout construction |  | Louis Newman | lifn501@york.ac.uk |  | Yes | 01/30/2020 | 13:00 | 01/30/2020 | 14:00 | 1:00 | 1 | 12.50 GBP | 12.50 GBP
Software - SWEng Group 4 |  | 01:30:00 | 00:00:00 | 00:30:00 | 00:00:00 | 02:00:00 | 00:00:00 | 00:00:00 | 04:00:00 | 04:00:00 | User Stories | SWEng Group 4 | Working on side slider and qa metrics |  | nathanbillis | ncab500@york.ac.uk |  | Yes | 01/30/2020 | 13:00 | 01/30/2020 | 15:00 | 2:00 | 2 | 12.50 GBP | 25.00 GBP
| Louis Newman | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 02:00:00 | 00:00:00 | 00:00:00 | 02:00:00 | 02:00:00 | Finance | SWEng Group 4 | estimate the cost of firebase |  | Jm2285 | jm2285@york.ac.uk |  | Yes | 01/30/2020 | 13:00 | 01/30/2020 | 15:00 | 2:00 | 2 | 12.50 GBP | 25.00 GBP
| Jb2200 | 00:00:00 | 00:00:00 | 00:30:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:30:00 | 00:30:00 | Administration | SWEng Group 4 | Working on redoing functional specification and QA |  | Jp1439 | jp1439@york.ac.uk |  | Yes | 01/30/2020 | 13:00 | 01/30/2020 | 15:00 | 2:00 | 2 | 12.50 GBP | 25.00 GBP
| James Clawley | 01:30:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 01:30:00 | 01:30:00 | Quality Manual | SWEng Group 4 | Finance manager metrics modifications |  | Louis Newman | lifn501@york.ac.uk |  | Yes | 01/30/2020 | 14:00 | 01/30/2020 | 15:00 | 1:00 | 1 | 12.50 GBP | 12.50 GBP
Administration - SWEng Group 4 |  | 00:00:00 | 00:00:00 | 00:00:00 | 03:00:00 | 00:45:00 | 00:00:00 | 00:00:00 | 03:45:00 | 03:45:00 | Meetings | SWEng Group 4 | Meeting to check over functional spec and QA manual |  | Louis Newman | lifn501@york.ac.uk |  | Yes | 01/31/2020 | 9:00 | 01/31/2020 | 10:30 | 1:30 | 1.5 | 12.50 GBP | 18.75 GBP
| Jp1439 | 00:00:00 | 00:00:00 | 00:00:00 | 02:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 02:00:00 | 02:00:00 | Meetings | SWEng Group 4 | group discussion though the QA manual and functional spec |  | Rea524 | rea524@york.ac.uk |  | Yes | 01/31/2020 | 9:00 | 01/31/2020 | 10:30 | 1:30 | 1.5 | 12.50 GBP | 18.75 GBP
| Rea524 | 00:00:00 | 00:00:00 | 00:00:00 | 01:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 01:00:00 | 01:00:00 | Meetings | SWEng Group 4 | Meeting group - reviewing document and design |  | nathanbillis | ncab500@york.ac.uk |  | Yes | 01/31/2020 | 9:00 | 01/31/2020 | 10:30 | 1:30 | 1.5 | 12.50 GBP | 18.75 GBP
| James Clawley | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:45:00 | 00:00:00 | 00:00:00 | 00:45:00 | 00:45:00 | Administration | SWEng Group 4 | Functional Spec review |  | James Clawley | jc2421@york.ac.uk |  | Yes | 01/31/2020 | 9:00 | 01/31/2020 | 9:45 | 0:45 | 0.75 | 12.50 GBP | 9.38 GBP
User Stories - SWEng Group 4 |  | 00:00:00 | 00:00:00 | 00:00:00 | 02:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 02:00:00 | 02:00:00 | Meetings | SWEng Group 4 | team meeting about QA manual |  | Jm2285 | jm2285@york.ac.uk |  | Yes | 01/31/2020 | 9:00 | 01/31/2020 | 10:30 | 1:30 | 1.5 | 12.50 GBP | 18.75 GBP
| nathanbillis | 00:00:00 | 00:00:00 | 00:00:00 | 02:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 02:00:00 | 02:00:00 | Quality Manual | SWEng Group 4 | Updated QA and Functional Spec |  | Jp1439 | jp1439@york.ac.uk |  | Yes | 01/31/2020 | 9:00 | 01/31/2020 | 10:30 | 1:30 | 1.5 | 12.50 GBP | 18.75 GBP
TOTAL |  | 08:20:00 | 00:00:00 | 02:15:00 | 10:00:00 | 11:00:00 | 01:00:00 | 02:30:00 | 35:05:00 | 35:00 | Quality Manual | SWEng Group 4 | QA Manual review |  | James Clawley | jc2421@york.ac.uk |  | Yes | 01/31/2020 | 9:45 | 01/31/2020 | 10:30 | 0:45 | 0.75 | 12.50 GBP | 9.38 GBP
[11 empty] | Software | SWEng Group 4 | JUnit testing for A1 | User story A1 | Louis Newman | lifn501@york.ac.uk |  | Yes | 01/31/2020 | 11:00 | 01/31/2020 | 12:00 | 1:00 | 1 | 12.50 GBP | 12.50 GBP
[9 empty] | total | 35 | Software | SWEng Group 4 | JUnit testing for A2 | User story A2 | Louis Newman | lifn501@york.ac.uk |  | Yes | 01/31/2020 | 12:00 | 01/31/2020 | 13:00 | 1:00 | 1 | 12.50 GBP | 12.50 GBP
[11 empty] | Finance | SWEng Group 4 | Putting together financial Business Plan |  | Louis Newman | lifn501@york.ac.uk |  | Yes | 2020-01-02 | 21:00 | 2020-01-02 | 22:00 | 1:00 | 1 | 12.50 GBP | 12.50 GBP
[11 empty] | Finance | SWEng Group 4 | Constructing the documents and making sure i include all relevant parts of financial business plan |  | Louis Newman | lifn501@york.ac.uk |  | Yes | 2020-02-02 | 10:30 | 2020-02-02 | 13:00 | 2:30 | 2.5 | 12.50 GBP | 31.25 GBP

## Week 19 labour
Project | User | 02/03/2020 | 02/04/2020 | 02/05/2020 | 02/06/2020 | 02/07/2020 | 02/08/2020 | 02/09/2020 | Total | Billable total | Project | Client | Description | Task | User | Email | Tags | Billable | Start Date | Start Time | End Date | End Time | Duration (h) | Duration (decimal) | Hourly Rate (GBP) | Amount (GBP)
Finance - SWEng Group 4 |  | 06:00:00 | 02:00:00 | 04:15:00 | 00:00:00 | 01:00:00 | 00:00:00 | 00:00:00 | 13:15:00 | 13:15:00 | Meetings | SWEng Group 4 | Group weekly meeting |  | Rea524 | rea524@york.ac.uk |  | Yes | 02/03/2020 | 09:00:00 AM | 02/03/2020 | 10:00:00 AM | 01:00:00 | 1 | 12.5 | 12.5
| Louis Newman | 05:00:00 | 02:00:00 | 04:15:00 | 00:00:00 | 01:00:00 | 00:00:00 | 00:00:00 | 12:15:00 | 12:15:00 | Administration | SWEng Group 4 | writing up minutes and formatting |  | Rea524 | rea524@york.ac.uk |  | Yes | 02/03/2020 | 10:00:00 AM | 02/03/2020 | 10:30:00 AM | 00:30:00 | 0.5 | 12.5 | 6.25
| Jm2285 | 01:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 01:00:00 | 01:00:00 | Meetings | SWEng Group 4 | Team meeting |  | Louis Newman | lifn501@york.ac.uk |  | Yes | 02/03/2020 | 11:00:00 AM | 02/03/2020 | 12:00:00 PM | 01:00:00 | 1 | 12.5 | 12.5
Meetings - SWEng Group 4 |  | 07:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 01:00:00 | 00:00:00 | 00:15:00 | 08:15:00 | 08:15:00 | Meetings | SWEng Group 4 | Group meeting |  | nathanbillis | ncab500@york.ac.uk |  | Yes | 02/03/2020 | 11:00:00 AM | 02/03/2020 | 12:00:00 PM | 01:00:00 | 1 | 12.5 | 12.5
| Jp1439 | 01:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:15:00 | 01:15:00 | 01:15:00 | Meetings | SWEng Group 4 | Team meeting |  | Jb2200 | jb2200@york.ac.uk |  | Yes | 02/03/2020 | 11:00:00 AM | 02/03/2020 | 12:00:00 PM | 01:00:00 | 1 | 12.5 | 12.5
| Louis Newman | 01:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 01:00:00 | 01:00:00 | Meetings | SWEng Group 4 | Team meeting |  | James Clawley | jc2421@york.ac.uk |  | Yes | 02/03/2020 | 11:00:00 AM | 02/03/2020 | 12:00:00 PM | 01:00:00 | 1 | 12.5 | 12.5
| Rea524 | 01:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 01:00:00 | 01:00:00 | Meetings | SWEng Group 4 | Team meeting |  | Jm2285 | jm2285@york.ac.uk |  | Yes | 02/03/2020 | 11:00:00 AM | 02/03/2020 | 12:00:00 PM | 01:00:00 | 1 | 12.5 | 12.5
| nathanbillis | 01:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 01:00:00 | 01:00:00 | Meetings | SWEng Group 4 | General Meeting |  | Jp1439 | jp1439@york.ac.uk |  | Yes | 02/03/2020 | 11:00:00 AM | 02/03/2020 | 12:00:00 PM | 01:00:00 | 1 | 12.5 | 12.5
| Jm2285 | 01:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 01:00:00 | 01:00:00 | Finance | SWEng Group 4 | Financial business plan - put together all team estimates and build up a financial picture of the project so far |  | Louis Newman | lifn501@york.ac.uk |  | Yes | 02/03/2020 | 01:00:00 PM | 02/03/2020 | 06:00:00 PM | 05:00:00 | 5 | 12.5 | 62.5
| Jb2200 | 01:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 01:00:00 | 01:00:00 | Finance | SWEng Group 4 | Improve the estimation of cost of firebase |  | Jm2285 | jm2285@york.ac.uk |  | Yes | 02/03/2020 | 04:30:00 PM | 02/03/2020 | 05:30:00 PM | 01:00:00 | 1 | 12.5 | 12.5
| James Clawley | 01:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 01:00:00 | 00:00:00 | 00:00:00 | 02:00:00 | 02:00:00 | Software | SWEng Group 4 | Working on getting side menu to work. And learning more about android studio | User story C34 | nathanbillis | ncab500@york.ac.uk |  | Yes | 02/04/2020 | 04:00:00 PM | 02/04/2020 | 05:45:00 PM | 01:45:00 | 1.75 | 12.5 | 21.88
Software - SWEng Group 4 |  | 00:00:00 | 01:45:00 | 00:00:00 | 09:00:00 | 03:00:00 | 00:00:00 | 00:00:00 | 13:45:00 | 13:45:00 | Finance | SWEng Group 4 | Financial business plan - add marketing elements and help Jun with estimates and attempt to make his storage plan a viable addition |  | Louis Newman | lifn501@york.ac.uk |  | Yes | 02/04/2020 | 06:00:00 PM | 02/04/2020 | 08:00:00 PM | 02:00:00 | 2 | 12.5 | 25
| Jp1439 | 00:00:00 | 00:00:00 | 00:00:00 | 03:00:00 | 01:00:00 | 00:00:00 | 00:00:00 | 04:00:00 | 04:00:00 | Design | SWEng Group 4 | Design spec 2 intro + design guidelines |  | Jb2200 | jb2200@york.ac.uk |  | Yes | 02/05/2020 | 02:00:00 AM | 02/05/2020 | 02:30:00 AM | 00:30:00 | 0.5 | 12.5 | 6.25
| Louis Newman | 00:00:00 | 00:00:00 | 00:00:00 | 02:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 02:00:00 | 02:00:00 | Marketing | SWEng Group 4 | marketing finance sheet |  | Rea524 | rea524@york.ac.uk |  | Yes | 02/05/2020 | 09:00:00 AM | 02/05/2020 | 09:45:00 AM | 00:45:00 | 0.75 | 12.5 | 9.38
| Rea524 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 02:00:00 | 00:00:00 | 00:00:00 | 02:00:00 | 02:00:00 | Finance | SWEng Group 4 | Financial business plan - Last couple of sections and analysis of spreadsheet |  | Louis Newman | lifn501@york.ac.uk |  | Yes | 02/05/2020 | 11:45:00 AM | 02/05/2020 | 02:00:00 PM | 02:15:00 | 2.25 | 12.5 | 28.13
| nathanbillis | 00:00:00 | 01:45:00 | 00:00:00 | 02:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 03:45:00 | 03:45:00 | Finance | SWEng Group 4 | Financial business plan - finishing off |  | Louis Newman | lifn501@york.ac.uk |  | Yes | 02/05/2020 | 03:00:00 PM | 02/05/2020 | 05:00:00 PM | 02:00:00 | 2 | 12.5 | 25
| James Clawley | 00:00:00 | 00:00:00 | 00:00:00 | 02:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 02:00:00 | 02:00:00 | Design | SWEng Group 4 | UML class diagram (Recipes + Recipe Presentations) |  | Jb2200 | jb2200@york.ac.uk |  | Yes | 02/05/2020 | 10:00:00 PM | 02/05/2020 | 10:30:00 PM | 00:30:00 | 0.5 | 12.5 | 6.25
Marketing - SWEng Group 4 |  | 00:00:00 | 00:00:00 | 00:45:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:45:00 | 00:45:00 | Software | SWEng Group 4 | Developed and added sidebar | User story C35 | James Clawley | jc2421@york.ac.uk |  | Yes | 02/06/2020 | 12:00:00 PM | 02/06/2020 | 01:00:00 PM | 01:00:00 | 1 | 12.5 | 12.5
| Rea524 | 00:00:00 | 00:00:00 | 00:45:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:45:00 | 00:45:00 | Software | SWEng Group 4 | software - Helping team get up and running with their own user stories |  | Louis Newman | lifn501@york.ac.uk |  | Yes | 02/06/2020 | 01:00:00 PM | 02/06/2020 | 03:00:00 PM | 02:00:00 | 2 | 12.5 | 25
Administration - SWEng Group 4 |  | 00:30:00 | 00:00:00 | 00:00:00 | 00:00:00 | 01:00:00 | 00:00:00 | 00:00:00 | 01:30:00 | 01:30:00 | Software | SWEng Group 4 | Finish the user story and send pull request and start user story C2(?) | User story C34 | nathanbillis | ncab500@york.ac.uk |  | Yes | 02/06/2020 | 01:00:00 PM | 02/06/2020 | 03:00:00 PM | 02:00:00 | 2 | 12.5 | 25
| Louis Newman | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 01:00:00 | 00:00:00 | 00:00:00 | 01:00:00 | 01:00:00 | Software | SWEng Group 4 | Building layout basis for recipe images | User story C1 | James Clawley | jc2421@york.ac.uk |  | Yes | 02/06/2020 | 01:00:00 PM | 02/06/2020 | 02:00:00 PM | 01:00:00 | 1 | 12.5 | 12.5
| Rea524 | 00:30:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:30:00 | 00:30:00 | Design | SWEng Group 4 | Design the recipe xml schema |  | Jm2285 | jm2285@york.ac.uk |  | Yes | 02/06/2020 | 01:00:00 PM | 02/06/2020 | 02:00:00 PM | 01:00:00 | 1 | 12.5 | 12.5
Research - SWEng Group 4 |  | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 01:00:00 | 00:00:00 | 00:00:00 | 01:00:00 | 01:00:00 | Software | SWEng Group 4 | Writing functionality for C3. Getting used to android studio | User story C3 | Jp1439 | jp1439@york.ac.uk |  | Yes | 02/06/2020 | 01:00:00 PM | 02/06/2020 | 04:00:00 PM | 03:00:00 | 3 | 12.5 | 37.5
| Rea524 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 01:00:00 | 00:00:00 | 00:00:00 | 01:00:00 | 01:00:00 | Finance | SWEng Group 4 | Finish and hand in business plan |  | Louis Newman | lifn501@york.ac.uk |  | Yes | 02/07/2020 | 08:00:00 AM | 02/07/2020 | 09:00:00 AM | 01:00:00 | 1 | 12.5 | 12.5
Design - SWEng Group 4 |  | 00:00:00 | 00:00:00 | 01:00:00 | 01:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 02:00:00 | 02:00:00 | Software | SWEng Group 4 | working on user story C20. set up new section for initial user customisation. | User story C20 | Rea524 | rea524@york.ac.uk |  | Yes | 02/07/2020 | 09:00:00 AM | 02/07/2020 | 11:00:00 AM | 02:00:00 | 2 | 12.5 | 25
| Jm2285 | 00:00:00 | 00:00:00 | 00:00:00 | 01:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 01:00:00 | 01:00:00 | Administration | SWEng Group 4 | XML Scheme meeting and prep |  | Louis Newman | lifn501@york.ac.uk |  | Yes | 02/07/2020 | 10:00:00 AM | 02/07/2020 | 11:00:00 AM | 01:00:00 | 1 | 12.5 | 12.5
| Jb2200 | 00:00:00 | 00:00:00 | 01:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 01:00:00 | 01:00:00 | Research | SWEng Group 4 | researched how firebase stores user information and how to customise settings |  | Rea524 | rea524@york.ac.uk |  | Yes | 02/07/2020 | 11:00:00 AM | 02/07/2020 | 12:00:00 PM | 01:00:00 | 1 | 12.5 | 12.5
TOTAL |  | 13:30:00 | 03:45:00 | 06:00:00 | 10:00:00 | 07:00:00 | 00:00:00 | 00:15:00 | 40:30:00 | 40:30:00 | Meetings | SWEng Group 4 | Team Meeting |  | James Clawley | jc2421@york.ac.uk |  | Yes | 02/07/2020 | 11:00:00 AM | 02/07/2020 | 12:00:00 PM | 01:00:00 | 1 | 12.5 | 12.5
[11 empty] | Software | SWEng Group 4 | Finishing functionality | User story C3 | Jp1439 | jp1439@york.ac.uk |  | Yes | 02/07/2020 | 11:00:00 AM | 02/07/2020 | 12:00:00 PM | 01:00:00 | 1 | 12.5 | 12.5
[9 empty] | total: | 40.5 | Meetings | SWEng Group 4 | Setting up meeting & reading Schema |  | Jp1439 | jp1439@york.ac.uk |  | Yes | 02/09/2020 | 11:15:00 AM | 02/09/2020 | 11:30:00 AM | 00:15:00 | 0.25 | 12.5 | 3.13

## Week 20 labour
Project | User | 02/10/2020 | 02/11/2020 | 02/12/2020 | 02/13/2020 | 02/14/2020 | 02/15/2020 | 02/16/2020 | Total | Billable total | Project | Client | Description | Task | User | Email | Tags | Billable | Start Date | Start Time | End Date | End Time | Duration (h) | Duration (decimal) | Hourly Rate (GBP) | Amount (GBP)
Finance - SWEng Group 4 |  | 00:30:00 | 00:00:00 | 01:30:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 02:00:00 | 02:00:00 | Meetings | SWEng Group 4 | Group weekly meeting |  | Rea524 | rea524@york.ac.uk |  | Yes | 02/10/2020 | 09:00:00 AM | 02/10/2020 | 10:00:00 AM | 01:00:00 | 1 | 12.5 | 12.5
| Louis Newman | 00:30:00 | 00:00:00 | 01:30:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 02:00:00 | 02:00:00 | Marketing | SWEng Group 4 | Marketing section for group tender presentation |  | Rea524 | rea524@york.ac.uk |  | Yes | 02/10/2020 | 10:00:00 AM | 02/10/2020 | 11:00:00 AM | 01:00:00 | 1 | 12.5 | 12.5
Meetings - SWEng Group 4 |  | 09:00:00 | 00:00:00 | 00:00:00 | 01:00:00 | 02:00:00 | 00:00:00 | 00:00:00 | 12:00:00 | 12:00:00 | Meetings | SWEng Group 4 | Group meeting and discussion of UML Diagrams |  | nathanbillis | ncab500@york.ac.uk |  | Yes | 02/10/2020 | 10:00:00 AM | 02/10/2020 | 12:00:00 PM | 02:00:00 | 2 | 12.5 | 25
| Jp1439 | 01:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 01:00:00 | 01:00:00 | Meetings | SWEng Group 4 | Design and Team meetings |  | Jb2200 | jb2200@york.ac.uk |  | Yes | 02/10/2020 | 10:00:00 AM | 02/10/2020 | 12:00:00 PM | 02:00:00 | 2 | 12.5 | 25
| Louis Newman | 01:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 01:00:00 | 01:00:00 | Finance | SWEng Group 4 | Weekly finances |  | Louis Newman | lifn501@york.ac.uk |  | Yes | 02/10/2020 | 10:30:00 AM | 02/10/2020 | 11:00:00 AM | 00:30:00 | 0.5 | 12.5 | 6.25
| Rea524 | 01:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 01:00:00 | 01:00:00 | Design | SWEng Group 4 | UML diagram design |  | James Clawley | jc2421@york.ac.uk |  | Yes | 02/10/2020 | 10:30:00 AM | 02/10/2020 | 11:00:00 AM | 00:30:00 | 0.5 | 12.5 | 6.25
| nathanbillis | 02:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 02:00:00 | 02:00:00 | Meetings | SWEng Group 4 | Group meeting |  | Louis Newman | lifn501@york.ac.uk |  | Yes | 02/10/2020 | 11:00:00 AM | 02/10/2020 | 12:00:00 PM | 01:00:00 | 1 | 12.5 | 12.5
| Jm2285 | 01:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 01:00:00 | 01:00:00 | Meetings | SWEng Group 4 | Team meeting |  | James Clawley | jc2421@york.ac.uk |  | Yes | 02/10/2020 | 11:00:00 AM | 02/10/2020 | 12:00:00 PM | 01:00:00 | 1 | 12.5 | 12.5
| Jb2200 | 02:00:00 | 00:00:00 | 00:00:00 | 01:00:00 | 02:00:00 | 00:00:00 | 00:00:00 | 05:00:00 | 05:00:00 | Meetings | SWEng Group 4 | team meeting |  | Jm2285 | jm2285@york.ac.uk |  | Yes | 02/10/2020 | 11:00:00 AM | 02/10/2020 | 12:00:00 PM | 01:00:00 | 1 | 12.5 | 12.5
| James Clawley | 01:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 01:00:00 | 01:00:00 | Meetings | SWEng Group 4 | General Meeting |  | Jp1439 | jp1439@york.ac.uk |  | Yes | 02/10/2020 | 11:00:00 AM | 02/10/2020 | 12:00:00 PM | 01:00:00 | 1 | 12.5 | 12.5
Software - SWEng Group 4 |  | 00:00:00 | 03:00:00 | 03:00:00 | 00:00:00 | 02:45:00 | 03:00:00 | 00:30:00 | 12:15:00 | 12:15:00 | Design | SWEng Group 4 | Updated XML design themes for Android studio, edited recipe uml class diagram and started editing uml login class diagram |  | Jb2200 | jb2200@york.ac.uk |  | Yes | 02/10/2020 | 04:00:00 PM | 02/10/2020 | 05:00:00 PM | 01:00:00 | 1 | 12.5 | 12.5
| Jp1439 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 02:00:00 | 02:00:00 | 00:00:00 | 04:00:00 | 04:00:00 | Design | SWEng Group 4 | Updated Trello with new UML specification attachment information |  | Jb2200 | jb2200@york.ac.uk |  | Yes | 02/10/2020 | 07:00:00 PM | 02/10/2020 | 07:15:00 PM | 00:15:00 | 0.25 | 12.5 | 3.13
| Louis Newman | 00:00:00 | 03:00:00 | 03:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 06:00:00 | 06:00:00 | Administration | SWEng Group 4 | Updated presentation PowerPoint slides for look & feel, iterations and platform |  | Jb2200 | jb2200@york.ac.uk |  | Yes | 02/11/2020 | 02:30:00 AM | 02/11/2020 | 03:00:00 AM | 00:30:00 | 0.5 | 12.5 | 6.25
| Rea524 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:30:00 | 00:30:00 | 00:30:00 | Software | SWEng Group 4 | Setting up link to firestore database and build of local data structures | User story A2 | Louis Newman | lifn501@york.ac.uk |  | Yes | 02/11/2020 | 07:00:00 PM | 02/11/2020 | 10:00:00 PM | 03:00:00 | 3 | 12.5 | 37.5
| James Clawley | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:45:00 | 01:00:00 | 00:00:00 | 01:45:00 | 01:45:00 | Tender presentation | SWEng Group 4 | Marketing section of presentation& logo design |  | Rea524 | rea524@york.ac.uk |  | Yes | 02/12/2020 | 09:00:00 AM | 02/12/2020 | 10:00:00 AM | 01:00:00 | 1 | 12.5 | 12.5
Testing - SWEng Group 4 |  | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 01:45:00 | 00:00:00 | 01:45:00 | 01:45:00 | Finance | SWEng Group 4 | Putting together and organising finances for display in tender presentation |  | Louis Newman | lifn501@york.ac.uk |  | Yes | 02/12/2020 | 11:30:00 AM | 02/12/2020 | 01:00:00 PM | 01:30:00 | 1.5 | 12.5 | 18.75
| nathanbillis | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 01:45:00 | 00:00:00 | 01:45:00 | 01:45:00 | Tender presentation | SWEng Group 4 | Meeting to discuss presentation |  | nathanbillis | ncab500@york.ac.uk |  | Yes | 02/12/2020 | 12:00:00 PM | 02/12/2020 | 01:00:00 PM | 01:00:00 | 1 | 12.5 | 12.5
Marketing - SWEng Group 4 |  | 01:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 01:00:00 | 01:00:00 | Tender presentation | SWEng Group 4 | Presentation planning |  | James Clawley | jc2421@york.ac.uk |  | Yes | 02/12/2020 | 12:00:00 PM | 02/12/2020 | 02:00:00 PM | 02:00:00 | 2 | 12.5 | 25
| Rea524 | 01:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 01:00:00 | 01:00:00 | Tender presentation | SWEng Group 4 | Discussion about presentation |  | Jm2285 | jm2285@york.ac.uk |  | Yes | 02/12/2020 | 12:00:00 PM | 02/12/2020 | 01:30:00 PM | 01:30:00 | 1.5 | 12.5 | 18.75
Administration - SWEng Group 4 |  | 00:00:00 | 00:30:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:30:00 | 00:30:00 | Tender presentation | SWEng Group 4 | Presentation prep |  | Jp1439 | jp1439@york.ac.uk |  | Yes | 02/12/2020 | 12:00:00 PM | 02/12/2020 | 02:00:00 PM | 02:00:00 | 2 | 12.5 | 25
| Jb2200 | 00:00:00 | 00:30:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:30:00 | 00:30:00 | Software | SWEng Group 4 | Finished and commented full stories for A1 and A2 | User story A1 | Louis Newman | lifn501@york.ac.uk |  | Yes | 02/12/2020 | 07:00:00 PM | 02/12/2020 | 10:00:00 PM | 03:00:00 | 3 | 12.5 | 37.5
Research - SWEng Group 4 |  | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 01:00:00 | 00:00:00 | 00:00:00 | 01:00:00 | 01:00:00 | Design | SWEng Group 4 | Made wireframe models for recipe screens (both free and paid). Produced UI diagrams for the mealplanner, including multiple versions and different screens. Updated UML recipe diagram briefly to include new meal planner information. |  | Jb2200 | jb2200@york.ac.uk |  | Yes | 02/12/2020 | 07:00:00 PM | 02/12/2020 | 11:00:00 PM | 04:00:00 | 4 | 12.5 | 50
| James Clawley | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 01:00:00 | 00:00:00 | 00:00:00 | 01:00:00 | 01:00:00 | Tender presentation | SWEng Group 4 | Working on presentation |  | nathanbillis | ncab500@york.ac.uk |  | Yes | 02/12/2020 | 07:24:00 PM | 02/12/2020 | 08:24:00 PM | 01:00:00 | 1 | 12.5 | 12.5
Design - SWEng Group 4 |  | 01:45:00 | 00:00:00 | 04:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 05:45:00 | 05:45:00 | Tender presentation | SWEng Group 4 | tender presentation work |  | Rea524 | rea524@york.ac.uk |  | Yes | 02/13/2020 | 09:00:00 AM | 02/13/2020 | 11:00:00 AM | 02:00:00 | 2 | 12.5 | 25
| Jb2200 | 01:15:00 | 00:00:00 | 04:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 05:15:00 | 05:15:00 | Meetings | SWEng Group 4 | Presentation meeting |  | Jb2200 | jb2200@york.ac.uk |  | Yes | 02/13/2020 | 12:20:00 PM | 02/13/2020 | 01:20:00 PM | 01:00:00 | 1 | 12.5 | 12.5
| James Clawley | 00:30:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:30:00 | 00:30:00 | Tender presentation | SWEng Group 4 | Worked on tender presentation |  | Louis Newman | lifn501@york.ac.uk |  | Yes | 02/13/2020 | 01:00:00 PM | 02/13/2020 | 03:00:00 PM | 02:00:00 | 2 | 12.5 | 25
Tender presentation - SWEng Group 4 |  | 00:00:00 | 00:00:00 | 08:30:00 | 13:00:00 | 12:00:00 | 00:30:00 | 00:00:00 | 34:00:00 | 34:00:00 | Tender presentation | SWEng Group 4 | Group meeting for presentation and meeting |  | nathanbillis | ncab500@york.ac.uk |  | Yes | 02/13/2020 | 01:00:00 PM | 02/13/2020 | 03:00:00 PM | 02:00:00 | 2 | 12.5 | 25
| Jp1439 | 00:00:00 | 00:00:00 | 02:00:00 | 02:00:00 | 02:00:00 | 00:00:00 | 00:00:00 | 06:00:00 | 06:00:00 | Tender presentation | SWEng Group 4 | Presentation planning |  | James Clawley | jc2421@york.ac.uk |  | Yes | 02/13/2020 | 01:00:00 PM | 02/13/2020 | 03:00:00 PM | 02:00:00 | 2 | 12.5 | 25
| Louis Newman | 00:00:00 | 00:00:00 | 00:00:00 | 03:00:00 | 02:00:00 | 00:00:00 | 00:00:00 | 05:00:00 | 05:00:00 | Tender presentation | SWEng Group 4 | Discussion about presentation |  | Jm2285 | jm2285@york.ac.uk |  | Yes | 02/13/2020 | 01:00:00 PM | 02/13/2020 | 03:00:00 PM | 02:00:00 | 2 | 12.5 | 25
| Rea524 | 00:00:00 | 00:00:00 | 01:00:00 | 02:00:00 | 02:00:00 | 00:30:00 | 00:00:00 | 05:30:00 | 05:30:00 | Tender presentation | SWEng Group 4 | Presentation prep |  | Jp1439 | jp1439@york.ac.uk |  | Yes | 02/13/2020 | 01:00:00 PM | 02/13/2020 | 03:00:00 PM | 02:00:00 | 2 | 12.5 | 25
| nathanbillis | 00:00:00 | 00:00:00 | 02:00:00 | 02:00:00 | 02:00:00 | 00:00:00 | 00:00:00 | 06:00:00 | 06:00:00 | Tender presentation | SWEng Group 4 | worked on tender pres |  | Louis Newman | lifn501@york.ac.uk |  | Yes | 02/13/2020 | 04:00:00 PM | 02/13/2020 | 05:00:00 PM | 01:00:00 | 1 | 12.5 | 12.5
| Jm2285 | 00:00:00 | 00:00:00 | 01:30:00 | 02:00:00 | 02:00:00 | 00:00:00 | 00:00:00 | 05:30:00 | 05:30:00 | Tender presentation | SWEng Group 4 | group work on presentation |  | Rea524 | rea524@york.ac.uk |  | Yes | 02/14/2020 | 09:00:00 AM | 02/14/2020 | 11:00:00 AM | 02:00:00 | 2 | 12.5 | 25
| James Clawley | 00:00:00 | 00:00:00 | 02:00:00 | 02:00:00 | 02:00:00 | 00:00:00 | 00:00:00 | 06:00:00 | 06:00:00 | Tender presentation | SWEng Group 4 | Run through of tender presentation |  | Louis Newman | lifn501@york.ac.uk |  | Yes | 02/14/2020 | 10:00:00 AM | 02/14/2020 | 12:00:00 PM | 02:00:00 | 2 | 12.5 | 25
TOTAL |  | 12:15:00 | 03:30:00 | 17:00:00 | 14:00:00 | 17:45:00 | 05:15:00 | 00:30:00 | 70:15:00 | 70:15:00 | Tender presentation | SWEng Group 4 | Group meeting to discuss presention |  | nathanbillis | ncab500@york.ac.uk |  | Yes | 02/14/2020 | 10:00:00 AM | 02/14/2020 | 12:00:00 PM | 02:00:00 | 2 | 12.5 | 25
[11 empty] | Meetings | SWEng Group 4 | Presentation meeting and final mock presentations + timings. |  | Jb2200 | jb2200@york.ac.uk |  | Yes | 02/14/2020 | 10:00:00 AM | 02/14/2020 | 12:00:00 PM | 02:00:00 | 2 | 12.5 | 25
[9 empty] | Total hours: | 70.25 | Tender presentation | SWEng Group 4 | Presentation planning |  | James Clawley | jc2421@york.ac.uk |  | Yes | 02/14/2020 | 10:00:00 AM | 02/14/2020 | 12:00:00 PM | 02:00:00 | 2 | 12.5 | 25
[11 empty] | Tender presentation | SWEng Group 4 | rehearse presentation and discussion about questions |  | Jm2285 | jm2285@york.ac.uk |  | Yes | 02/14/2020 | 10:00:00 AM | 02/14/2020 | 12:00:00 PM | 02:00:00 | 2 | 12.5 | 25
[11 empty] | Tender presentation | SWEng Group 4 | Presentation prep |  | Jp1439 | jp1439@york.ac.uk |  | Yes | 02/14/2020 | 10:00:00 AM | 02/14/2020 | 12:00:00 PM | 02:00:00 | 2 | 12.5 | 25
[11 empty] | Software | SWEng Group 4 | Setting up scroll views to accept C3 when merging | User story C1 | James Clawley | jc2421@york.ac.uk |  | Yes | 02/14/2020 | 08:00:00 PM | 02/14/2020 | 08:45:00 PM | 00:45:00 | 0.75 | 12.5 | 9.38
[11 empty] | Software | SWEng Group 4 | Changing from Activity to Dialog Fragmnet | User story C3 | Jp1439 | jp1439@york.ac.uk |  | Yes | 02/14/2020 | 08:00:00 PM | 02/14/2020 | 10:00:00 PM | 02:00:00 | 2 | 12.5 | 25
[11 empty] | Research | SWEng Group 4 | Firebase documentation |  | James Clawley | jc2421@york.ac.uk |  | Yes | 02/14/2020 | 08:45:00 PM | 02/14/2020 | 09:45:00 PM | 01:00:00 | 1 | 12.5 | 12.5
[11 empty] | Tender presentation | SWEng Group 4 | Personal presentation practice |  | Rea524 | rea524@york.ac.uk |  | Yes | 02/15/2020 | 09:00:00 AM | 02/15/2020 | 09:30:00 AM | 00:30:00 | 0.5 | 12.5 | 6.25
[11 empty] | Software | SWEng Group 4 | Getting tabs to work again, trying to Unit test fragments | User story C3 | Jp1439 | jp1439@york.ac.uk |  | Yes | 02/15/2020 | 09:00:00 AM | 02/15/2020 | 11:00:00 AM | 02:00:00 | 2 | 12.5 | 25
[11 empty] | Software | SWEng Group 4 | Programmed images being pulled from Firebase servers | User story C1 | James Clawley | jc2421@york.ac.uk |  | Yes | 02/15/2020 | 01:00:00 PM | 02/15/2020 | 02:00:00 PM | 01:00:00 | 1 | 12.5 | 12.5
[11 empty] | Testing | SWEng Group 4 | Testing and peer review of A1 A2 user stories and merging into the master |  | nathanbillis | ncab500@york.ac.uk |  | Yes | 02/15/2020 | 02:30:00 PM | 02/15/2020 | 04:15:00 PM | 01:45:00 | 1.75 | 12.5 | 21.88
[11 empty] | Software | SWEng Group 4 | Redesigned Filter page, & researched firebase boolean connections | User story C20 | Rea524 | rea524@york.ac.uk |  | Yes | 02/16/2020 | 09:00:00 AM | 02/16/2020 | 09:30:00 AM | 00:30:00 | 0.5 | 12.5 | 6.25
NOTE: 15 MINS TAKEN FROM HOURS AT LATER DATE

## Week 21 Labour
Project | User | 02/17/2020 | 02/18/2020 | 02/19/2020 | 02/20/2020 | 02/21/2020 | 02/22/2020 | 02/23/2020 | Total | Billable Total |  | Project | Client | Description | Task | User | Email | Tags | Billable | Start Date | Start Time | End Date | End Time | Duration (h) | Duration (decimal) | Hourly Rate (GBP) | Amount (GBP)
Finance - SWEng Group 4 |  | 00:00:00 | 00:00:00 | 02:00:00 | 01:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 03:00:00 | 03:00:00 |  | Meetings | SWEng Group 4 |  |  | Rea524 | rea524@york.ac.uk |  | Yes | 02/17/2020 | 09:00:00 AM | 02/17/2020 | 10:00:00 AM | 01:00:00 | 1 | 12.5 | 12.5
| Louis Newman | 00:00:00 | 00:00:00 | 02:00:00 | 01:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 03:00:00 | 03:00:00 |  | Tender presentation | SWEng Group 4 |  |  | Rea524 | rea524@york.ac.uk |  | Yes | 02/17/2020 | 10:00:00 AM | 02/17/2020 | 11:00:00 AM | 01:00:00 | 1 | 12.5 | 12.5
Meetings - SWEng Group 4 |  | 05:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 05:00:00 | 05:00:00 |  | Meetings | SWEng Group 4 | Group meeting |  | Louis Newman | lifn501@york.ac.uk |  | Yes | 02/17/2020 | 11:00:00 AM | 02/17/2020 | 12:00:00 PM | 01:00:00 | 1 | 12.5 | 12.5
| Jp1439 | 01:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 01:00:00 | 01:00:00 |  | Meetings | SWEng Group 4 | Team meeting |  | Jm2285 | jm2285@york.ac.uk |  | Yes | 02/17/2020 | 11:00:00 AM | 02/17/2020 | 12:00:00 PM | 01:00:00 | 1 | 12.5 | 12.5
| Louis Newman | 01:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 01:00:00 | 01:00:00 |  | Meetings | SWEng Group 4 | Group meeting |  | Jp1439 | jp1439@york.ac.uk |  | Yes | 02/17/2020 | 11:00:00 AM | 02/17/2020 | 12:00:00 PM | 01:00:00 | 1 | 12.5 | 12.5
| Rea524 | 01:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 01:00:00 | 01:00:00 |  | Tender presentation | SWEng Group 4 | Presentation practice |  | James Clawley | jc2421@york.ac.uk |  | Yes | 02/17/2020 | 02:00:00 PM | 02/17/2020 | 03:00:00 PM | 01:00:00 | 1 | 12.5 | 12.5
| nathanbillis | 01:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 01:00:00 | 01:00:00 |  | Tender presentation | SWEng Group 4 | Prepare for the presentation |  | Jm2285 | jm2285@york.ac.uk |  | Yes | 02/17/2020 | 02:00:00 PM | 02/17/2020 | 03:00:00 PM | 01:00:00 | 1 | 12.5 | 12.5
| Jm2285 | 01:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 01:00:00 | 01:00:00 |  | Tender presentation | SWEng Group 4 | Run through and presented tender presentation |  | Louis Newman | lifn501@york.ac.uk |  | Yes | 02/17/2020 | 02:30:00 PM | 02/17/2020 | 03:30:00 PM | 01:00:00 | 1 | 12.5 | 12.5
Software - SWEng Group 4 |  | 00:00:00 | 00:00:00 | 00:00:00 | 05:00:00 | 03:00:00 | 01:30:00 | 05:45:00 | 15:15:00 | 15:15:00 |  | Administration | SWEng Group 4 | Iteration Planning and chart updating |  | Jp1439 | jp1439@york.ac.uk |  | Yes | 02/18/2020 | 01:00:00 PM | 02/18/2020 | 03:00:00 PM | 02:00:00 | 2 | 12.5 | 25
| Jp1439 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 01:30:00 | 00:30:00 | 02:00:00 | 02:00:00 |  | Administration | SWEng Group 4 | Iteration Planning and chart updating |  | Jp1439 | jp1439@york.ac.uk |  | Yes | 02/19/2020 | 10:00:00 AM | 02/19/2020 | 11:00:00 AM | 01:00:00 | 1 | 12.5 | 12.5
| Louis Newman | 00:00:00 | 00:00:00 | 00:00:00 | 01:00:00 | 00:00:00 | 00:00:00 | 01:30:00 | 02:30:00 | 02:30:00 |  | Finance | SWEng Group 4 | Financial report 1 & updated financial business plan with feedback from financial backer |  | Louis Newman | lifn501@york.ac.uk |  | Yes | 02/19/2020 | 06:00:00 PM | 02/19/2020 | 08:00:00 PM | 02:00:00 | 2 | 12.5 | 25
| Rea524 | 00:00:00 | 00:00:00 | 00:00:00 | 02:00:00 | 00:00:00 | 00:00:00 | 00:45:00 | 02:45:00 | 02:45:00 |  | Software | SWEng Group 4 | working on user story C20. all filters working and submit and skip buttons | User story C20 | Rea524 | rea524@york.ac.uk |  | Yes | 02/20/2020 | 09:00:00 AM | 02/20/2020 | 11:00:00 AM | 02:00:00 | 2 | 12.5 | 25
| Jb2200 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 03:00:00 | 03:00:00 | 03:00:00 |  | Finance | SWEng Group 4 | Finish off financial business plan & first financial report |  | Louis Newman | lifn501@york.ac.uk |  | Yes | 02/20/2020 | 01:00:00 PM | 02/20/2020 | 02:00:00 PM | 01:00:00 | 1 | 12.5 | 12.5
| James Clawley | 00:00:00 | 00:00:00 | 00:00:00 | 02:00:00 | 03:00:00 | 00:00:00 | 00:00:00 | 05:00:00 | 05:00:00 |  | Software | SWEng Group 4 | Worked on building up queries and getting other members up and running | User story C6 | Louis Newman | lifn501@york.ac.uk |  | Yes | 02/20/2020 | 01:00:00 PM | 02/20/2020 | 02:00:00 PM | 01:00:00 | 1 | 12.5 | 12.5
Administration - SWEng Group 4 |  | 00:00:00 | 02:00:00 | 01:00:00 | 00:00:00 | 00:30:00 | 01:00:00 | 00:00:00 | 04:30:00 | 04:30:00 |  | Design | SWEng Group 4 | Created wireframe models for profile page and 4 possible presentation screens |  | Jb2200 | jb2200@york.ac.uk |  | Yes | 02/20/2020 | 01:30:00 PM | 02/20/2020 | 02:15:00 PM | 00:45:00 | 0.75 | 12.5 | 9.38
| Jp1439 | 00:00:00 | 02:00:00 | 01:00:00 | 00:00:00 | 00:00:00 | 01:00:00 | 00:00:00 | 04:00:00 | 04:00:00 |  | Administration | SWEng Group 4 | Meeting to discuss purchase and sale of two modules |  | Louis Newman | lifn501@york.ac.uk |  | Yes | 02/21/2020 | 09:00:00 AM | 02/21/2020 | 09:30:00 AM | 00:30:00 | 0.5 | 12.5 | 6.25
| Louis Newman | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:30:00 | 00:00:00 | 00:00:00 | 00:30:00 | 00:30:00 |  | Software | SWEng Group 4 | fixing info gathering | User story C3 | Jp1439 | jp1439@york.ac.uk |  | Yes | 02/22/2020 | 10:00:00 AM | 02/22/2020 | 11:30:00 AM | 01:30:00 | 1.5 | 12.5 | 18.75
Design - SWEng Group 4 |  | 00:00:00 | 00:00:00 | 00:00:00 | 00:45:00 | 00:00:00 | 02:00:00 | 02:00:00 | 04:45:00 | 04:45:00 |  | Administration | SWEng Group 4 | Writing contract |  | Jp1439 | jp1439@york.ac.uk |  | Yes | 02/22/2020 | 11:30:00 AM | 02/22/2020 | 12:30:00 PM | 01:00:00 | 1 | 12.5 | 12.5
| Jm2285 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 02:00:00 | 02:00:00 | 04:00:00 | 0:00 | Questionable entries | Design | SWEng Group 4 | design the searching bar |  | Jm2285 | jm2285@york.ac.uk |  | Yes | 02/22/2020 | 07:00:00 PM | 02/22/2020 | 09:00:00 PM | 02:00:00 | 2 | 12.5 | 25
| Jb2200 | 00:00:00 | 00:00:00 | 00:00:00 | 00:45:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:45:00 | 00:45:00 |  | Software | SWEng Group 4 | Put together document of all queries | User story C7 | Louis Newman | lifn501@york.ac.uk |  | Yes | 02/23/2020 | 09:00:00 AM | 02/23/2020 | 10:00:00 AM | 01:00:00 | 1 | 12.5 | 12.5
Tender presentation - SWEng Group 4 |  | 04:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 04:00:00 | 04:00:00 |  | Software | SWEng Group 4 | trying to fix testing error | User story C3 | Jp1439 | jp1439@york.ac.uk |  | Yes | 02/23/2020 | 10:00:00 AM | 02/23/2020 | 10:30:00 AM | 00:30:00 | 0.5 | 12.5 | 6.25
| Louis Newman | 01:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 01:00:00 | 01:00:00 |  | Design | SWEng Group 4 | design the searching bar |  | Jm2285 | jm2285@york.ac.uk |  | Yes | 02/23/2020 | 03:00:00 PM | 02/23/2020 | 05:00:00 PM | 02:00:00 | 2 | 12.5 | 25
| Rea524 | 01:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 01:00:00 | 01:00:00 |  | Software | SWEng Group 4 | Modified user profile to allow local storage and safe access. Also added UI user screen. |  | Jb2200 | jb2200@york.ac.uk |  | Yes | 02/23/2020 | 04:00:00 PM | 02/23/2020 | 07:00:00 PM | 03:00:00 | 3 | 12.5 | 37.5
| Jm2285 | 01:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 01:00:00 | 01:00:00 |  | Software | SWEng Group 4 | Put together methods for A3 & A5 | User story A3 | Louis Newman | lifn501@york.ac.uk |  | Yes | 02/23/2020 | 08:00:00 PM | 02/23/2020 | 08:30:00 PM | 00:30:00 | 0.5 | 12.5 | 6.25
| James Clawley | 01:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 01:00:00 | 01:00:00
TOTAL |  | 09:00:00 | 02:00:00 | 03:00:00 | 06:45:00 | 03:30:00 | 04:30:00 | 07:45:00 | 36:30:00
[9 empty] | total: | 32.5
questionable entries rejected by team lead
NOTE: SOME HOURSE ALTERED BY MEMBERS AT A LATER DATE
BILLABLE BOURS = 32.5 HOURS

## Week 22 Labour
Project | User | 02/24/2020 | 02/25/2020 | 02/26/2020 | 02/27/2020 | 02/28/2020 | 02/29/2020 | 03/01/2020 | Total | Billable total | Project | Client | Description | Task | User | Email | Tags | Billable | Start Date | Start Time | End Date | End Time | Duration (h) | Duration (decimal) | Hourly Rate (GBP) | Amount (GBP)
Meetings - SWEng Group 4 |  | 04:45:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 04:45:00 | 04:45:00 | Meetings | SWEng Group 4 | Group meeting |  | Rea524 | rea524@york.ac.uk |  | Yes | 02/24/2020 | 09:00:00 AM | 02/24/2020 | 09:45:00 AM | 00:45:00 | 0.75 | 12.5 | 9.38
| James Pearson | 00:45:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:45:00 | 00:45:00 | Meetings | SWEng Group 4 | Group meeting |  | Louis Newman | lifn501@york.ac.uk |  | Yes | 02/24/2020 | 11:00:00 AM | 02/24/2020 | 11:45:00 AM | 00:45:00 | 0.75 | 12.5 | 9.38
| Louis Newman | 00:45:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:45:00 | 00:45:00 | Meetings | SWEng Group 4 | Team meeting |  | James Clawley | jc2421@york.ac.uk |  | Yes | 02/24/2020 | 11:00:00 AM | 02/24/2020 | 11:45:00 AM | 00:45:00 | 0.75 | 12.5 | 9.38
| Rebecca Anderson | 00:45:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:45:00 | 00:45:00 | Meetings | SWEng Group 4 | Team meeting |  | Jm2285 | jm2285@york.ac.uk |  | Yes | 02/24/2020 | 11:00:00 AM | 02/24/2020 | 12:00:00 PM | 01:00:00 | 1 | 12.5 | 12.5
| Nathan Billis | 00:45:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:45:00 | 00:45:00 | Meetings | SWEng Group 4 | General group meeting |  | Jp1439 | jp1439@york.ac.uk |  | Yes | 02/24/2020 | 11:00:00 AM | 02/24/2020 | 11:45:00 AM | 00:45:00 | 0.75 | 12.5 | 9.38
| Jun Ma | 01:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 01:00:00 | 0:45 | Meetings | SWEng Group 4 | Group Meeting |  | nathanbillis | ncab500@york.ac.uk |  | Yes | 02/24/2020 | 12:00:00 PM | 02/24/2020 | 12:45:00 PM | 00:45:00 | 0.75 | 12.5 | 9.38
| James Clawley | 00:45:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:45:00 | 00:45:00 | Software | SWEng Group 4 | Removed shared preferences code. Added JUnit tests for context and multiple creation possibilities for singletons. |  | Jb2200 | jb2200@york.ac.uk |  | Yes | 02/24/2020 | 10:15:00 PM | 02/24/2020 | 11:15:00 PM | 01:00:00 | 1 | 12.5 | 12.5
| Joe Butler | 0:45 | [7 empty] | 0:45
Software - SWEng Group 4 |  | 01:00:00 | 00:00:00 | 12:00:00 | 12:00:00 | 07:45:00 | 04:00:00 | 02:45:00 | 39:30:00 | 39:30:00 | Testing | SWEng Group 4 | Code review and documentation of C1 User Story | C1 | nathanbillis | ncab500@york.ac.uk |  | Yes | 02/25/2020 | 12:00:00 PM | 02/25/2020 | 12:45:00 PM | 00:45:00 | 0.75 | 12.5 | 9.38
| Louis Newman | 00:00:00 | 00:00:00 | 01:00:00 | 03:30:00 | 00:00:00 | 00:00:00 | 02:00:00 | 06:30:00 | 06:30:00 | Software | SWEng Group 4 | resolving issues involving login, However stuck with contact checks. Waiting for Joe to decided on contact checks | User story C20 | Rea524 | rea524@york.ac.uk |  | Yes | 02/26/2020 | 09:00:00 AM | 02/26/2020 | 10:00:00 AM | 01:00:00 | 1 | 12.5 | 12.5
| Rebecca Anderson | 00:00:00 | 00:00:00 | 03:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:45:00 | 03:45:00 | 03:45:00 | Software | SWEng Group 4 | Programming XML parser |  | James Clawley | jc2421@york.ac.uk |  | Yes | 02/26/2020 | 09:00:00 AM | 02/26/2020 | 05:00:00 PM | 08:00:00 | 8 | 12.5 | 100
| Nathan Billis | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 02:00:00 | 00:00:00 | 00:00:00 | 02:00:00 | 02:00:00 | Software | SWEng Group 4 | Wrote functions for shopping list implementation before releasing misunderstood the user story | User story C5 | Rea524 | rea524@york.ac.uk |  | Yes | 02/26/2020 | 10:00:00 AM | 02/26/2020 | 12:00:00 PM | 02:00:00 | 2 | 12.5 | 25
| Joe Butler | 01:00:00 | 00:00:00 | 00:00:00 | 02:30:00 | 00:45:00 | 04:00:00 | 00:00:00 | 08:15:00 | 08:15:00 | Administration | SWEng Group 4 | Finalising and signing contracts |  | Jp1439 | jp1439@york.ac.uk |  | Yes | 02/26/2020 | 11:15:00 AM | 02/26/2020 | 11:45:00 AM | 00:30:00 | 0.5 | 12.5 | 6.25
| James Clawley | 00:00:00 | 00:00:00 | 08:00:00 | 06:00:00 | 05:00:00 | 00:00:00 | 00:00:00 | 19:00:00 | 19:00:00 | Software | SWEng Group 4 | Building the search bar | User story C18 | Louis Newman | lifn501@york.ac.uk |  | Yes | 02/26/2020 | 06:00:00 PM | 02/26/2020 | 07:00:00 PM | 01:00:00 | 1 | 12.5 | 12.5
Testing - SWEng Group 4 |  | 00:00:00 | 00:45:00 | 00:00:00 | 00:30:00 | 00:00:00 | 00:00:00 | 00:00:00 | 01:15:00 | 01:15:00 | Software | SWEng Group 4 | Finished basic retrieval for users data to be displayed |  | Jb2200 | jb2200@york.ac.uk |  | Yes | 02/27/2020 | 06:30:00 AM | 02/27/2020 | 08:00:00 AM | 01:30:00 | 1.5 | 12.5 | 18.75
| Nathan Billis | 00:00:00 | 00:45:00 | 00:00:00 | 00:30:00 | 00:00:00 | 00:00:00 | 00:00:00 | 01:15:00 | 01:15:00 | Software | SWEng Group 4 | Programming XML parser |  | James Clawley | jc2421@york.ac.uk |  | Yes | 02/27/2020 | 09:00:00 AM | 02/27/2020 | 01:00:00 PM | 04:00:00 | 4 | 12.5 | 50
Administration - SWEng Group 4 |  | 00:00:00 | 00:00:00 | 00:30:00 | 01:15:00 | 00:00:00 | 00:00:00 | 00:00:00 | 01:45:00 | 01:45:00 | Software | SWEng Group 4 | Adding handler for parsed XML | User story B1 | James Clawley | jc2421@york.ac.uk |  | Yes | 02/27/2020 | 11:00:00 AM | 02/27/2020 | 01:00:00 PM | 02:00:00 | 2 | 12.5 | 25
| James Pearson | 00:00:00 | 00:00:00 | 00:30:00 | 01:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 01:30:00 | 01:30:00 | Software | SWEng Group 4 | Attempted to help Jun get up and running with the C18, he didn't have android studio fully set up, not did he have Github. He was very behind with the programming and was not capable of running with the story. After talking to the group leader it was decided to take him off such a complicated user story as it clearly would not get done properly. Jun was then given a smaller user story that would be more suitable for someone starting out with java and android for the first time. | User story C18 | Louis Newman | lifn501@york.ac.uk |  | Yes | 02/27/2020 | 01:00:00 PM | 02/27/2020 | 03:00:00 PM | 02:00:00 | 2 | 12.5 | 25
| Nathan Billis | 00:00:00 | 00:00:00 | 00:00:00 | 00:15:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:15:00 | 00:15:00 | Administration | SWEng Group 4 | Started work on researching and writing T&I plan |  | nathanbillis | ncab500@york.ac.uk |  | Yes | 02/27/2020 | 01:00:00 PM | 02/27/2020 | 01:15:00 PM | 00:15:00 | 0.25 | 12.5 | 3.13
User Stories - SWEng Group 4 |  | 00:00:00 | 00:00:00 | 00:00:00 | 01:00:00 | 00:00:00 | 01:00:00 | 02:00:00 | 04:00:00 | 04:00:00 | User Stories | SWEng Group 4 | researching Video handler ideas |  | Jp1439 | jp1439@york.ac.uk |  | Yes | 02/27/2020 | 01:00:00 PM | 02/27/2020 | 02:00:00 PM | 01:00:00 | 1 | 12.5 | 12.5
| James Pearson | 00:00:00 | 00:00:00 | 00:00:00 | 01:00:00 | 00:00:00 | 01:00:00 | 02:00:00 | 04:00:00 | 04:00:00 | Software | SWEng Group 4 | Pair programming with Jun to get the xml public profile screen and tests setup |  | Jb2200 | jb2200@york.ac.uk |  | Yes | 02/27/2020 | 02:00:00 PM | 02/27/2020 | 03:00:00 PM | 01:00:00 | 1 | 12.5 | 12.5
Design - SWEng Group 4 |  | 00:00:00 | 00:00:00 | 00:00:00 | 01:30:00 | 01:30:00 | 01:30:00 | 00:00:00 | 04:30:00 | 04:30:00 | Administration | SWEng Group 4 | Finishing user story administration |  | Jp1439 | jp1439@york.ac.uk |  | Yes | 02/27/2020 | 02:00:00 PM | 02/27/2020 | 03:00:00 PM | 01:00:00 | 1 | 12.5 | 12.5
| Jun Ma | 00:00:00 | 00:00:00 | 00:00:00 | 01:30:00 | 01:30:00 | 01:30:00 | 00:00:00 | 04:30:00 | 04:30:00 | Design | SWEng Group 4 | Set the layout and test of public profile of users |  | Jm2285 | jm2285@york.ac.uk |  | Yes | 02/27/2020 | 03:00:00 PM | 02/27/2020 | 04:30:00 PM | 01:30:00 | 1.5 | 12.5 | 18.75
TOTAL |  | 05:45:00 | 00:45:00 | 12:30:00 | 16:15:00 | 09:15:00 | 06:30:00 | 04:45:00 | 55:45:00 | 56.25.00 | Software | SWEng Group 4 | Building up functionality and search capability of C18 with filtering and sorting capability. | User story C18 | Louis Newman | lifn501@york.ac.uk |  | Yes | 02/27/2020 | 06:30:00 PM | 02/27/2020 | 08:00:00 PM | 01:30:00 | 1.5 | 12.5 | 18.75
[11 empty] | Testing | SWEng Group 4 | Code Review and Documentation for User story C3 | C3 | nathanbillis | ncab500@york.ac.uk |  | Yes | 02/27/2020 | 08:27:00 PM | 02/27/2020 | 08:57:00 PM | 00:30:00 | 0.5 | 12.5 | 6.25
|  | Joe lack of meeting entry has been added along with negating 15 minutes of Juns meeting entry as it was also wrong. | [8 empty] | Software | SWEng Group 4 | Fixed multiple merge errors within github and split profile and search branches into 2 sections |  | Jb2200 | jb2200@york.ac.uk |  | Yes | 02/28/2020 | 04:30:00 AM | 02/28/2020 | 05:00:00 AM | 00:30:00 | 0.5 | 12.5 | 6.25
[9 empty] | total billable | 56.25 | Software | SWEng Group 4 | Updated recipe info styling in android to better match wireframes and basic requirements |  | Jb2200 | jb2200@york.ac.uk |  | Yes | 02/28/2020 | 07:30:00 AM | 02/28/2020 | 07:45:00 AM | 00:15:00 | 0.25 | 12.5 | 3.13
[11 empty] | Software | SWEng Group 4 | Adding handler for parsed XML | User story B1 | James Clawley | jc2421@york.ac.uk |  | Yes | 02/28/2020 | 11:00:00 AM | 02/28/2020 | 04:00:00 PM | 05:00:00 | 5 | 12.5 | 62.5
[11 empty] | Software | SWEng Group 4 | Working on user story c35 - refactoring and adding tests | User story C35 | nathanbillis | ncab500@york.ac.uk |  | Yes | 02/28/2020 | 01:00:00 PM | 02/28/2020 | 03:00:00 PM | 02:00:00 | 2 | 12.5 | 25
[11 empty] | Design | SWEng Group 4 | Design the Favourite Recipe function |  | Jm2285 | jm2285@york.ac.uk |  | Yes | 02/28/2020 | 07:00:00 PM | 02/28/2020 | 08:30:00 PM | 01:30:00 | 1.5 | 12.5 | 18.75
[11 empty] | Software | SWEng Group 4 | About 90% completed the profile settings class. All .xml screens done for profile settings. Basic retrieval from firebase working but not done |  | Jb2200 | jb2200@york.ac.uk |  | Yes | 02/29/2020 | 12:00:00 AM | 02/29/2020 | 04:00:00 AM | 04:00:00 | 4 | 12.5 | 50
[11 empty] | User Stories | SWEng Group 4 | Implementing video handler for customer |  | Jp1439 | jp1439@york.ac.uk |  | Yes | 02/29/2020 | 11:00:00 AM | 02/29/2020 | 12:00:00 PM | 01:00:00 | 1 | 12.5 | 12.5
[11 empty] | Design | SWEng Group 4 | Design the Favourite recipe function |  | Jm2285 | jm2285@york.ac.uk |  | Yes | 02/29/2020 | 08:00:00 PM | 02/29/2020 | 09:30:00 PM | 01:30:00 | 1.5 | 12.5 | 18.75
[11 empty] | Software | SWEng Group 4 | set up new section following the correct. looked into following through pages using intents and tided up plan. However due to the meal planner not being completed much, this will have to be put on hold | User story C20 | Rea524 | rea524@york.ac.uk |  | Yes | 03/01/2020 | 09:00:00 AM | 03/01/2020 | 09:45:00 AM | 00:45:00 | 0.75 | 12.5 | 9.38
[11 empty] | Software | SWEng Group 4 | Trying to make an endless scroll on new window with the user input search query | User story C18 | Louis Newman | lifn501@york.ac.uk |  | Yes | 03/01/2020 | 10:00:00 AM | 03/01/2020 | 11:00:00 AM | 01:00:00 | 1 | 12.5 | 12.5
[11 empty] | User Stories | SWEng Group 4 | Implementing video handler for customer |  | Jp1439 | jp1439@york.ac.uk |  | Yes | 03/01/2020 | 02:00:00 PM | 03/01/2020 | 04:00:00 PM | 02:00:00 | 2 | 12.5 | 25
[11 empty] | Software | SWEng Group 4 | Nearly finished the search bar, not getting results and displaying message if nothing is found in the database | User story C18 | Louis Newman | lifn501@york.ac.uk |  | Yes | 03/01/2020 | 07:00:00 PM | 03/01/2020 | 08:00:00 PM | 01:00:00 | 1 | 12.5 | 12.5

## Week 23 Labour
Project | User | 03/02/2020 | 03/03/2020 | 03/04/2020 | 03/05/2020 | 03/06/2020 | 03/07/2020 | 03/08/2020 | Total | Billable total | Project | Client | Description | Task | User | Email | Tags | Billable | Start Date | Start Time | End Date | End Time | Duration (h) | Duration (decimal) | Hourly Rate (GBP) | Amount (GBP)
Finance - SWEng Group 4 |  | 00:00:00 | 01:00:00 | 00:00:00 | 00:30:00 | 00:00:00 | 00:00:00 | 00:00:00 | 01:30:00 | 01:30:00 | Meetings | SWEng Group 4 | Group weekly meeting |  | Rebecca Anderson | rea524@york.ac.uk |  | Yes | 03/02/2020 | 09:00:00 AM | 03/02/2020 | 09:30:00 AM | 00:30:00 | 0.5 | 12.5 | 6.25
| Louis Newman | 00:00:00 | 01:00:00 | 00:00:00 | 00:30:00 | 00:00:00 | 00:00:00 | 00:00:00 | 01:30:00 | 01:30:00 | Meetings | SWEng Group 4 | Team meeting |  | James Clawley | jc2421@york.ac.uk |  | Yes | 03/02/2020 | 09:00:00 AM | 03/02/2020 | 09:30:00 AM | 00:30:00 | 0.5 | 12.5 | 6.25
Meetings - SWEng Group 4 |  | 03:30:00 | 01:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 04:30:00 | 04:30:00 | Meetings | SWEng Group 4 | Group meeting |  | Louis Newman | lifn501@york.ac.uk |  | Yes | 03/02/2020 | 11:00:00 AM | 03/02/2020 | 11:30:00 AM | 00:30:00 | 0.5 | 12.5 | 6.25
| James Pearson | 00:30:00 | 00:30:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 01:00:00 | 01:00:00 | Meetings | SWEng Group 4 | Group meeting |  | Nathan Billis | ncab500@york.ac.uk |  | Yes | 03/02/2020 | 11:00:00 AM | 03/02/2020 | 11:30:00 AM | 00:30:00 | 0.5 | 12.5 | 6.25
| Louis Newman | 00:30:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:30:00 | 00:30:00 | Meetings | SWEng Group 4 | Project meeting |  | Joe Butler | jb2200@york.ac.uk |  | Yes | 03/02/2020 | 11:00:00 AM | 03/02/2020 | 11:30:00 AM | 00:30:00 | 0.5 | 12.5 | 6.25
| Rebecca Anderson | 00:30:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:30:00 | 00:30:00 | Meetings | SWEng Group 4 | team meeting |  | Jun Ma | jm2285@york.ac.uk |  | Yes | 03/02/2020 | 11:00:00 AM | 03/02/2020 | 11:30:00 AM | 00:30:00 | 0.5 | 12.5 | 6.25
| Nathan Billis | 00:30:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:30:00 | 00:30:00 | Meetings | SWEng Group 4 | General Group Meeting |  | James Pearson | jp1439@york.ac.uk |  | Yes | 03/02/2020 | 11:00:00 AM | 03/02/2020 | 11:30:00 AM | 00:30:00 | 0.5 | 12.5 | 6.25
| Jun Ma | 00:30:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:30:00 | 00:30:00 | Software | SWEng Group 4 | Cleaned up current recipes in Firestore and ensured that queries save and are able to query on multiple allergens, also cleaned up the code | User story C18 | Louis Newman | lifn501@york.ac.uk |  | Yes | 03/02/2020 | 08:00:00 PM | 03/02/2020 | 09:00:00 PM | 01:00:00 | 1 | 12.5 | 12.5
| Joe Butler | 00:30:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:30:00 | 00:30:00 | Meetings | SWEng Group 4 | Contracts meeting |  | James Clawley | jc2421@york.ac.uk |  | Yes | 03/03/2020 | 09:00:00 AM | 03/03/2020 | 09:30:00 AM | 00:30:00 | 0.5 | 12.5 | 6.25
| James Clawley | 00:30:00 | 00:30:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 01:00:00 | 01:00:00 | Meetings | SWEng Group 4 | Meeting with other group to discuss Modules being developed |  | James Pearson | jp1439@york.ac.uk |  | Yes | 03/03/2020 | 09:00:00 AM | 03/03/2020 | 09:30:00 AM | 00:30:00 | 0.5 | 12.5 | 6.25
Software - SWEng Group 4 |  | 01:00:00 | 01:00:00 | 02:00:00 | 15:15:00 | 04:30:00 | 04:30:00 | 03:00:00 | 31:15:00 | 31:15:00 | Software | SWEng Group 4 | Video Handler pair programming |  | James Clawley | jc2421@york.ac.uk |  | Yes | 03/03/2020 | 09:30:00 AM | 03/03/2020 | 10:00:00 AM | 00:30:00 | 0.5 | 12.5 | 6.25
| Louis Newman | 01:00:00 | 00:00:00 | 00:00:00 | 03:30:00 | 00:00:00 | 03:00:00 | 02:00:00 | 09:30:00 | 09:30:00 | User Stories | SWEng Group 4 | Debugging with James C |  | James Pearson | jp1439@york.ac.uk |  | Yes | 03/03/2020 | 09:30:00 AM | 03/03/2020 | 10:00:00 AM | 00:30:00 | 0.5 | 12.5 | 6.25
| Rebecca Anderson | 00:00:00 | 00:00:00 | 00:00:00 | 02:45:00 | 00:00:00 | 01:00:00 | 00:00:00 | 03:45:00 | 03:45:00 | Software | SWEng Group 4 | Text handler custom fonts |  | James Clawley | jc2421@york.ac.uk |  | Yes | 03/03/2020 | 11:00:00 AM | 03/03/2020 | 11:30:00 AM | 00:30:00 | 0.5 | 12.5 | 6.25
| Nathan Billis | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:30:00 | 00:30:00 | 00:30:00 | Finance | SWEng Group 4 | Put together bones of the Financial Report II |  | Louis Newman | lifn501@york.ac.uk |  | Yes | 03/03/2020 | 06:00:00 PM | 03/03/2020 | 07:00:00 PM | 01:00:00 | 1 | 12.5 | 12.5
| Jun Ma | 00:00:00 | 00:00:00 | 02:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 02:00:00 | 02:00:00 | Test and integration plan | SWEng Group 4 | Working on the Test and integration plan - Integration strategy |  | Nathan Billis | ncab500@york.ac.uk |  | Yes | 03/04/2020 | 05:30:00 PM | 03/04/2020 | 06:30:00 PM | 01:00:00 | 1 | 12.5 | 12.5
| Joe Butler | 00:00:00 | 00:00:00 | 00:00:00 | 07:00:00 | 02:30:00 | 00:30:00 | 00:30:00 | 10:30:00 | 10:30:00 | Software | SWEng Group 4 | coding about favourite recipes |  | Jun Ma | jm2285@york.ac.uk |  | Yes | 03/04/2020 | 07:00:00 PM | 03/04/2020 | 09:00:00 PM | 02:00:00 | 2 | 12.5 | 25
| James Clawley | 00:00:00 | 01:00:00 | 00:00:00 | 02:00:00 | 02:00:00 | 00:00:00 | 00:00:00 | 05:00:00 | 05:00:00 | Software | SWEng Group 4 | Finished the A4 user story + JUnit and Espresso tests. |  | Joe Butler | jb2200@york.ac.uk |  | Yes | 03/05/2020 | 12:00:00 AM | 03/05/2020 | 04:00:00 AM | 04:00:00 | 4 | 12.5 | 50
Testing - SWEng Group 4 |  | 00:00:00 | 00:00:00 | 00:00:00 | 00:15:00 | 00:00:00 | 00:00:00 | 00:30:00 | 00:45:00 | 00:45:00 | Software | SWEng Group 4 | Gone over on this user story. This was due to multiple reasons including other users stories changing how this user story should work. Aldo misjudged the time it would take as there was a lot to complete. | User story C20 | Rebecca Anderson | rea524@york.ac.uk |  | Yes | 03/05/2020 | 09:00:00 AM | 03/05/2020 | 11:45:00 AM | 02:45:00 | 2.75 | 12.5 | 34.38
| Nathan Billis | 00:00:00 | 00:00:00 | 00:00:00 | 00:15:00 | 00:00:00 | 00:00:00 | 00:30:00 | 00:45:00 | 00:45:00 | Software | SWEng Group 4 | Working on user stories B1-B5 | User story B1 | James Clawley | jc2421@york.ac.uk |  | Yes | 03/05/2020 | 09:00:00 AM | 03/05/2020 | 11:00:00 AM | 02:00:00 | 2 | 12.5 | 25
Administration - SWEng Group 4 |  | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 01:30:00 | 00:00:00 | 00:15:00 | 01:45:00 | 01:45:00 | Finance | SWEng Group 4 | Finished and set of financial report 2 |  | Louis Newman | lifn501@york.ac.uk |  | Yes | 03/05/2020 | 10:30:00 AM | 03/05/2020 | 11:00:00 AM | 00:30:00 | 0.5 | 12.5 | 6.25
| James Pearson | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:15:00 | 00:15:00 | 00:15:00 | Software | SWEng Group 4 | Created delete profile and reset password integration and made the profile settings screen scrollable. |  | Joe Butler | jb2200@york.ac.uk |  | Yes | 03/05/2020 | 11:00:00 AM | 03/05/2020 | 02:00:00 PM | 03:00:00 | 3 | 12.5 | 37.5
| James Clawley | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 01:30:00 | 00:00:00 | 00:00:00 | 01:30:00 | 01:30:00 | Software | SWEng Group 4 | Put delete profile and reset password into user profile settings, also helped Becky with C20 | User story A3 | Louis Newman | lifn501@york.ac.uk |  | Yes | 03/05/2020 | 01:00:00 PM | 03/05/2020 | 04:30:00 PM | 03:30:00 | 3.5 | 12.5 | 43.75
User Stories - SWEng Group 4 |  | 00:00:00 | 00:30:00 | 00:00:00 | 02:00:00 | 00:00:00 | 01:30:00 | 00:00:00 | 04:00:00 | 04:00:00 | User Stories | SWEng Group 4 | Changing some aspects of the video handler module with James C |  | James Pearson | jp1439@york.ac.uk |  | Yes | 03/05/2020 | 01:00:00 PM | 03/05/2020 | 03:00:00 PM | 02:00:00 | 2 | 12.5 | 25
| James Pearson | 00:00:00 | 00:30:00 | 00:00:00 | 02:00:00 | 00:00:00 | 01:30:00 | 00:00:00 | 04:00:00 | 04:00:00 | Test and integration plan | SWEng Group 4 | writing test plan and background in testing theory |  | Nathan Billis | ncab500@york.ac.uk |  | Yes | 03/05/2020 | 01:30:00 PM | 03/05/2020 | 03:00:00 PM | 01:30:00 | 1.5 | 12.5 | 18.75
Test and integration plan - SWEng Group 4 |  | 00:00:00 | 00:00:00 | 01:00:00 | 01:30:00 | 00:30:00 | 00:00:00 | 00:00:00 | 03:00:00 | 03:00:00 | Testing | SWEng Group 4 | Itergrate A4 into the master branch | A4 | Nathan Billis | ncab500@york.ac.uk |  | Yes | 03/05/2020 | 03:00:00 PM | 03/05/2020 | 03:15:00 PM | 00:15:00 | 0.25 | 12.5 | 3.13
| Nathan Billis | 00:00:00 | 00:00:00 | 01:00:00 | 01:30:00 | 00:30:00 | 00:00:00 | 00:00:00 | 03:00:00 | 03:00:00 | Software | SWEng Group 4 | Working on user stories B1-B5 | User story B1 | James Clawley | jc2421@york.ac.uk |  | Yes | 03/06/2020 | 09:00:00 AM | 03/06/2020 | 11:00:00 AM | 02:00:00 | 2 | 12.5 | 25
TOTAL |  | 04:30:00 | 03:30:00 | 03:00:00 | 19:30:00 | 06:30:00 | 06:00:00 | 03:45:00 | 46:45:00 | 46:45:00 | Administration | SWEng Group 4 | Module handover documentation |  | James Clawley | jc2421@york.ac.uk |  | Yes | 03/06/2020 | 11:00:00 AM | 03/06/2020 | 12:30:00 PM | 01:30:00 | 1.5 | 12.5 | 18.75
[11 empty] | Test and integration plan | SWEng Group 4 | Writing testing method overview and start test criteria |  | Nathan Billis | ncab500@york.ac.uk |  | Yes | 03/06/2020 | 11:30:00 AM | 03/06/2020 | 12:00:00 PM | 00:30:00 | 0.5 | 12.5 | 6.25
[11 empty] | Software | SWEng Group 4 | Added profile deletion and password tests in espresso, tested manually, added initial user parameters such as firstAppLaunch and fixed the order of operations for reset password and delete profile listeners. |  | Joe Butler | jb2200@york.ac.uk |  | Yes | 03/06/2020 | 07:00:00 PM | 03/06/2020 | 09:30:00 PM | 02:30:00 | 2.5 | 12.5 | 31.25
[11 empty] | Software | SWEng Group 4 | Fixed recipe and profile settings layout constraints |  | Joe Butler | jb2200@york.ac.uk |  | Yes | 03/07/2020 | 03:00:00 AM | 03/07/2020 | 03:30:00 AM | 00:30:00 | 0.5 | 12.5 | 6.25
[11 empty] | Software | SWEng Group 4 | Build home screen personalised infinite scroll queries | User story C18 | Louis Newman | lifn501@york.ac.uk |  | Yes | 03/07/2020 | 09:00:00 AM | 03/07/2020 | 12:00:00 PM | 03:00:00 | 3 | 12.5 | 37.5
[11 empty] | Software | SWEng Group 4 | Not much completed on this user story due to errors being present. Attempted to find the cause but was unsuccessful. Plan for this has been made | User story C5 | Rebecca Anderson | rea524@york.ac.uk |  | Yes | 03/07/2020 | 09:00:00 AM | 03/07/2020 | 10:00:00 AM | 01:00:00 | 1 | 12.5 | 12.5
[11 empty] | User Stories | SWEng Group 4 | Finishing video handler and writing documentation |  | James Pearson | jp1439@york.ac.uk |  | Yes | 03/07/2020 | 10:00:00 AM | 03/07/2020 | 11:30:00 AM | 01:30:00 | 1.5 | 12.5 | 18.75
[11 empty] | Software | SWEng Group 4 | Created public profile stuff. Only have testing and integration to finish. |  | Joe Butler | jb2200@york.ac.uk |  | Yes | 03/08/2020 | 03:30:00 AM | 03/08/2020 | 04:00:00 AM | 00:30:00 | 0.5 | 12.5 | 6.25
[11 empty] | Software | SWEng Group 4 | Finished home page and wrote tests to test each of the search and filter functions | User story C18 | Louis Newman | lifn501@york.ac.uk |  | Yes | 03/08/2020 | 09:00:00 AM | 03/08/2020 | 11:00:00 AM | 02:00:00 | 2 | 12.5 | 25
[11 empty] | Administration | SWEng Group 4 | Writing agenda and minutes for Monday morning meeting |  | James Pearson | jp1439@york.ac.uk |  | Yes | 03/08/2020 | 09:00:00 AM | 03/08/2020 | 09:15:00 AM | 00:15:00 | 0.25 | 12.5 | 3.13
[11 empty] | Software | SWEng Group 4 | finalised finalised C35 Side menu for intergation | User story C35 | Nathan Billis | ncab500@york.ac.uk |  | Yes | 03/08/2020 | 08:00:00 PM | 03/08/2020 | 08:30:00 PM | 00:30:00 | 0.5 | 12.5 | 6.25
[11 empty] | Testing | SWEng Group 4 | Completed manual testing for C35 | C35 | Nathan Billis | ncab500@york.ac.uk |  | Yes | 03/08/2020 | 08:30:00 PM | 03/08/2020 | 09:00:00 PM | 00:30:00 | 0.5 | 12.5 | 6.25

## Week 24 Labour
Project | User | 03/09/2020 | 03/10/2020 | 03/11/2020 | 03/12/2020 | 03/13/2020 | 03/14/2020 | 03/15/2020 | Total | Billable total | Project | Client | Description | Task | User | Email | Tags | Billable | Start Date | Start Time | End Date | End Time | Duration (h) | Duration (decimal) | Hourly Rate (GBP) | Amount (GBP)
Finance - SWEng Group 4 |  | 00:00:00 | 00:15:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:15:00 | 00:15:00 | Software | SWEng Group 4 | Finished all of the essential user profile elements. Including manual tests and espresso tests. Created pull request into master and integrated the sidebar with help from Nathan. |  | Joe Butler | jb2200@york.ac.uk |  | Yes | 03/09/2020 | 02:30:00 AM | 03/09/2020 | 03:00:00 AM | 00:30:00 | 0.5 | 12.5 | 6.25
| Louis Newman | 00:00:00 | 00:15:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:15:00 | 00:15:00 | Software | SWEng Group 4 | Added the ability to use the local UserInfoPrivate object instead to initiate a profile if available. Will reduce number of queries to firebase which is always good. |  | Joe Butler | jb2200@york.ac.uk |  | Yes | 03/09/2020 | 05:15:00 AM | 03/09/2020 | 05:30:00 AM | 00:15:00 | 0.25 | 12.5 | 3.13
Meetings - SWEng Group 4 |  | 03:15:00 | 00:00:00 | 00:30:00 | 00:00:00 | 01:00:00 | 00:00:00 | 00:00:00 | 04:45:00 | 04:45:00 | Meetings | SWEng Group 4 | group meeting |  | Rebecca Anderson | rea524@york.ac.uk |  | Yes | 03/09/2020 | 09:00:00 AM | 03/09/2020 | 09:30:00 AM | 00:30:00 | 0.5 | 12.5 | 6.25
| James Pearson | 00:30:00 | 00:00:00 | 00:30:00 | 00:00:00 | 00:15:00 | 00:00:00 | 00:00:00 | 01:15:00 | 01:15:00 | Administration | SWEng Group 4 | Writing up notes from meeting |  | Rebecca Anderson | rea524@york.ac.uk |  | Yes | 03/09/2020 | 09:00:00 AM | 03/09/2020 | 09:15:00 AM | 00:15:00 | 0.25 | 12.5 | 3.13
| Louis Newman | 00:30:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:15:00 | 00:00:00 | 00:00:00 | 00:45:00 | 00:45:00 | Meetings | SWEng Group 4 | Group meeting |  | James Pearson | jp1439@york.ac.uk |  | Yes | 03/09/2020 | 09:00:00 AM | 03/09/2020 | 09:30:00 AM | 00:30:00 | 0.5 | 12.5 | 6.25
| Rebecca Anderson | 00:30:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:30:00 | 00:30:00 | Meetings | SWEng Group 4 | Team meeting |  | Louis Newman | lifn501@york.ac.uk |  | Yes | 03/09/2020 | 11:00:00 AM | 03/09/2020 | 11:30:00 AM | 00:30:00 | 0.5 | 12.5 | 6.25
| Nathan Billis | 00:30:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:15:00 | 00:00:00 | 00:00:00 | 00:45:00 | 00:45:00 | Meetings | SWEng Group 4 | Group Meeting |  | Nathan Billis | ncab500@york.ac.uk |  | Yes | 03/09/2020 | 11:00:00 AM | 03/09/2020 | 11:30:00 AM | 00:30:00 | 0.5 | 12.5 | 6.25
| Jun Ma | 00:30:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:30:00 | 00:30:00 | Meetings | SWEng Group 4 | Team meeting |  | James Clawley | jc2421@york.ac.uk |  | Yes | 03/09/2020 | 11:00:00 AM | 03/09/2020 | 11:30:00 AM | 00:30:00 | 0.5 | 12.5 | 6.25
| James Clawley | 00:45:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:15:00 | 00:00:00 | 00:00:00 | 01:00:00 | 01:00:00 | Meetings | SWEng Group 4 | Team meeting |  | Jun Ma | jm2285@york.ac.uk |  | Yes | 03/09/2020 | 11:00:00 AM | 03/09/2020 | 11:30:00 AM | 00:30:00 | 0.5 | 12.5 | 6.25
Quality Manual - SWEng Group 4 |  | 00:00:00 | 00:00:00 | 00:15:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:15:00 | 00:15:00 | Meetings | SWEng Group 4 | Handover meeting |  | James Clawley | jc2421@york.ac.uk |  | Yes | 03/09/2020 | 12:00:00 PM | 03/09/2020 | 12:15:00 PM | 00:15:00 | 0.25 | 12.5 | 3.13
| James Pearson | 00:00:00 | 00:00:00 | 00:15:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:15:00 | 00:15:00 | Software | SWEng Group 4 | Commenting and writing up test plan for all search and sort |  | Louis Newman | lifn501@york.ac.uk |  | Yes | 03/09/2020 | 06:00:00 PM | 03/09/2020 | 08:00:00 PM | 02:00:00 | 2 | 12.5 | 25
Software - SWEng Group 4 |  | 02:45:00 | 03:15:00 | 00:00:00 | 04:00:00 | 02:30:00 | 00:00:00 | 00:00:00 | 12:30:00 | 12:30:00 | Marketing | SWEng Group 4 | writing customer feedback forms and researching into successful feedback forms. |  | Rebecca Anderson | rea524@york.ac.uk |  | Yes | 03/10/2020 | 09:00:00 AM | 03/10/2020 | 09:45:00 AM | 00:45:00 | 0.75 | 12.5 | 9.38
| Louis Newman | 02:00:00 | 00:00:00 | 00:00:00 | 02:00:00 | 00:30:00 | 00:00:00 | 00:00:00 | 04:30:00 | 04:30:00 | Testing | SWEng Group 4 | testing of user story. took a while as first time testing, so was figuring it all out swell | C20 | Rebecca Anderson | rea524@york.ac.uk |  | Yes | 03/10/2020 | 09:00:00 AM | 03/10/2020 | 11:00:00 AM | 02:00:00 | 2 | 12.5 | 25
| Rebecca Anderson | 00:00:00 | 00:45:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:45:00 | 00:45:00 | Software | SWEng Group 4 | comparing branches to others as there had been a lot of changes. | User story C20 | Rebecca Anderson | rea524@york.ac.uk |  | Yes | 03/10/2020 | 09:00:00 AM | 03/10/2020 | 09:45:00 AM | 00:45:00 | 0.75 | 12.5 | 9.38
| Joe Butler | 00:45:00 | 01:30:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 02:15:00 | 02:15:00 | Test and integration plan | SWEng Group 4 | Adding more detail to the T&I plan and iteration strategy |  | Nathan Billis | ncab500@york.ac.uk |  | Yes | 03/10/2020 | 10:00:00 AM | 03/10/2020 | 11:30:00 AM | 01:30:00 | 1.5 | 12.5 | 18.75
| James Clawley | 00:00:00 | 01:00:00 | 00:00:00 | 02:00:00 | 02:00:00 | 00:00:00 | 00:00:00 | 05:00:00 | 05:00:00 | Finance | SWEng Group 4 | Weekly finances |  | Louis Newman | lifn501@york.ac.uk |  | Yes | 03/10/2020 | 11:30:00 AM | 03/10/2020 | 11:45:00 AM | 00:15:00 | 0.25 | 12.5 | 3.13
Testing - SWEng Group 4 |  | 00:00:00 | 02:00:00 | 00:00:00 | 01:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 03:00:00 | 03:00:00 | Software | SWEng Group 4 | Fixing initial preferences (pair programming, Becky) |  | Joe Butler | jb2200@york.ac.uk |  | Yes | 03/10/2020 | 02:00:00 PM | 03/10/2020 | 03:30:00 PM | 01:30:00 | 1.5 | 12.5 | 18.75
| Rebecca Anderson | 00:00:00 | 02:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 02:00:00 | 02:00:00 | Software | SWEng Group 4 | Refactoring graphics module |  | James Clawley | jc2421@york.ac.uk |  | Yes | 03/10/2020 | 05:00:00 PM | 03/10/2020 | 06:00:00 PM | 01:00:00 | 1 | 12.5 | 12.5
| Nathan Billis | 00:00:00 | 00:00:00 | 00:00:00 | 01:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 01:00:00 | 01:00:00 | Test and integration plan | SWEng Group 4 | Added A4, 5, 3 and 11 to the testing and integration plan. |  | Joe Butler | jb2200@york.ac.uk |  | Yes | 03/11/2020 | 02:00:00 AM | 03/11/2020 | 03:30:00 AM | 01:30:00 | 1.5 | 12.5 | 18.75
Marketing - SWEng Group 4 |  | 00:00:00 | 00:45:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:15:00 | 01:00:00 | 01:00:00 | Test and integration plan | SWEng Group 4 | Writing up iteration 1 tests |  | Rebecca Anderson | rea524@york.ac.uk |  | Yes | 03/11/2020 | 09:00:00 AM | 03/11/2020 | 09:45:00 AM | 00:45:00 | 0.75 | 12.5 | 9.38
| Rebecca Anderson | 00:00:00 | 00:45:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:15:00 | 01:00:00 | 01:00:00 | Meetings | SWEng Group 4 | Meeting with Nathan to discuss and go through peer review and testing procedure |  | James Pearson | jp1439@york.ac.uk |  | Yes | 03/11/2020 | 10:00:00 AM | 03/11/2020 | 10:30:00 AM | 00:30:00 | 0.5 | 12.5 | 6.25
Administration - SWEng Group 4 |  | 00:15:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:15:00 | 00:15:00 | Test and integration plan | SWEng Group 4 | Writing more for the T&I plan |  | Nathan Billis | ncab500@york.ac.uk |  | Yes | 03/11/2020 | 11:00:00 AM | 03/11/2020 | 12:00:00 PM | 01:00:00 | 1 | 12.5 | 12.5
| Rebecca Anderson | 00:15:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:15:00 | 00:15:00 | Quality Manual | SWEng Group 4 | Updated QA with new process |  | James Pearson | jp1439@york.ac.uk |  | Yes | 03/11/2020 | 12:30:00 PM | 03/11/2020 | 12:45:00 PM | 00:15:00 | 0.25 | 12.5 | 3.13
Design - SWEng Group 4 |  | 00:00:00 | 00:00:00 | 00:00:00 | 01:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 01:00:00 | 01:00:00 | Test and integration plan | SWEng Group 4 | Writing tests for the T&I Plan |  | James Pearson | jp1439@york.ac.uk |  | Yes | 03/11/2020 | 12:45:00 PM | 03/11/2020 | 01:30:00 PM | 00:45:00 | 0.75 | 12.5 | 9.38
| James Pearson | 00:00:00 | 00:00:00 | 00:00:00 | 01:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 01:00:00 | 01:00:00 | Test and integration plan | SWEng Group 4 | Adding tests for user stories to the test and integration plan |  | Louis Newman | lifn501@york.ac.uk |  | Yes | 03/11/2020 | 06:00:00 PM | 03/11/2020 | 07:00:00 PM | 01:00:00 | 1 | 12.5 | 12.5
Test and integration plan - SWEng Group 4 |  | 00:00:00 | 01:30:00 | 05:00:00 | 10:00:00 | 00:30:00 | 00:00:00 | 00:00:00 | 17:00:00 | 17:00:00 | Test and integration plan | SWEng Group 4 |  |  | Rebecca Anderson | rea524@york.ac.uk |  | Yes | 03/12/2020 | 09:00:00 AM | 03/12/2020 | 10:30:00 AM | 01:30:00 | 1.5 | 12.5 | 18.75
| James Pearson | 00:00:00 | 00:00:00 | 00:45:00 | 02:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 02:45:00 | 02:45:00 | Software | SWEng Group 4 | Adding modules from contracts |  | James Clawley | jc2421@york.ac.uk |  | Yes | 03/12/2020 | 09:00:00 AM | 03/12/2020 | 11:00:00 AM | 02:00:00 | 2 | 12.5 | 25
| Louis Newman | 00:00:00 | 00:00:00 | 01:00:00 | 02:30:00 | 00:00:00 | 00:00:00 | 00:00:00 | 03:30:00 | 03:30:00 | Design | SWEng Group 4 | Refactored code | C3 | James Pearson | jp1439@york.ac.uk |  | Yes | 03/12/2020 | 10:00:00 AM | 03/12/2020 | 11:00:00 AM | 01:00:00 | 1 | 12.5 | 12.5
| Rebecca Anderson | 00:00:00 | 00:00:00 | 00:45:00 | 01:30:00 | 00:00:00 | 00:00:00 | 00:00:00 | 02:15:00 | 02:15:00 | Test and integration plan | SWEng Group 4 | Add test of user story to the test and integration plan |  | Jun Ma | jm2285@york.ac.uk |  | Yes | 03/12/2020 | 10:30:00 AM | 03/12/2020 | 11:30:00 AM | 01:00:00 | 1 | 12.5 | 12.5
| Nathan Billis | 00:00:00 | 01:30:00 | 01:00:00 | 01:00:00 | 00:30:00 | 00:00:00 | 00:00:00 | 04:00:00 | 04:00:00 | Test and integration plan | SWEng Group 4 | Adding tests for user stories to the test and integration plan |  | Louis Newman | lifn501@york.ac.uk |  | Yes | 03/12/2020 | 12:30:00 PM | 03/12/2020 | 03:00:00 PM | 02:30:00 | 2.5 | 12.5 | 31.25
| Jun Ma | 00:00:00 | 00:00:00 | 00:00:00 | 03:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 03:00:00 | 03:00:00 | Test and integration plan | SWEng Group 4 | Working on T&I plan |  | Nathan Billis | ncab500@york.ac.uk |  | Yes | 03/12/2020 | 01:00:00 PM | 03/12/2020 | 02:00:00 PM | 01:00:00 | 1 | 12.5 | 12.5
| Joe Butler | 00:00:00 | 00:00:00 | 01:30:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 01:30:00 | 01:30:00 | Test and integration plan | SWEng Group 4 | Add user story test to the test and integration plan |  | Jun Ma | jm2285@york.ac.uk |  | Yes | 03/12/2020 | 01:00:00 PM | 03/12/2020 | 03:00:00 PM | 02:00:00 | 2 | 12.5 | 25
TOTAL |  | 06:15:00 | 07:45:00 | 05:45:00 | 16:00:00 | 04:00:00 | 00:00:00 | 00:15:00 | 40:00:00 | 40:00:00 | Test and integration plan | SWEng Group 4 | Testing and Integration Plan |  | James Pearson | jp1439@york.ac.uk |  | Yes | 03/12/2020 | 01:00:00 PM | 03/12/2020 | 03:00:00 PM | 02:00:00 | 2 | 12.5 | 25
[11 empty] | Testing | SWEng Group 4 | Intergrating and peer review of modules A11, C20 | A11 | Nathan Billis | ncab500@york.ac.uk |  | Yes | 03/12/2020 | 02:00:00 PM | 03/12/2020 | 03:00:00 PM | 01:00:00 | 1 | 12.5 | 12.5
[11 empty] | Software | SWEng Group 4 | Adding recipes to Firebase |  | Louis Newman | lifn501@york.ac.uk |  | Yes | 03/12/2020 | 07:30:00 PM | 03/12/2020 | 09:30:00 PM | 02:00:00 | 2 | 12.5 | 25
[11 empty] | Software | SWEng Group 4 | Demo clean up |  | Louis Newman | lifn501@york.ac.uk |  | Yes | 03/13/2020 | 08:30:00 AM | 03/13/2020 | 09:00:00 AM | 00:30:00 | 0.5 | 12.5 | 6.25
[11 empty] | Test and integration plan | SWEng Group 4 | Finalising T&I plan |  | Nathan Billis | ncab500@york.ac.uk |  | Yes | 03/13/2020 | 09:00:00 AM | 03/13/2020 | 09:30:00 AM | 00:30:00 | 0.5 | 12.5 | 6.25
[11 empty] | Meetings | SWEng Group 4 | Demo meeting |  | James Clawley | jc2421@york.ac.uk |  | Yes | 03/13/2020 | 09:00:00 AM | 03/13/2020 | 09:15:00 AM | 00:15:00 | 0.25 | 12.5 | 3.13
[11 empty] | Software | SWEng Group 4 | First demo clean up |  | James Clawley | jc2421@york.ac.uk |  | Yes | 03/13/2020 | 09:00:00 AM | 03/13/2020 | 11:00:00 AM | 02:00:00 | 2 | 12.5 | 25
[11 empty] | Meetings | SWEng Group 4 | Customer demo |  | Louis Newman | lifn501@york.ac.uk |  | Yes | 03/13/2020 | 01:00:00 PM | 03/13/2020 | 01:15:00 PM | 00:15:00 | 0.25 | 12.5 | 3.13
[11 empty] | Meetings | SWEng Group 4 | Project demo |  | Nathan Billis | ncab500@york.ac.uk |  | Yes | 03/13/2020 | 01:00:00 PM | 03/13/2020 | 01:15:00 PM | 00:15:00 | 0.25 | 12.5 | 3.13
[11 empty] | Meetings | SWEng Group 4 | Customer Demo |  | James Pearson | jp1439@york.ac.uk |  | Yes | 03/13/2020 | 01:00:00 PM | 03/13/2020 | 01:15:00 PM | 00:15:00 | 0.25 | 12.5 | 3.13
[11 empty] | Marketing | SWEng Group 4 |  |  | Rebecca Anderson | rea524@york.ac.uk |  | Yes | 03/15/2020 | 09:00:00 AM | 03/15/2020 | 09:15:00 AM | 00:15:00 | 0.25 | 12.5 | 3.13

## Week 25 Labour
Project | User | 03/16/2020 | 03/17/2020 | 03/18/2020 | 03/19/2020 | 03/20/2020 | 03/21/2020 | 03/22/2020 | Total | Billable total | Project | Client | Description | Task | User | Email | Tags | Billable | Start Date | Start Time | End Date | End Time | Duration (h) | Duration (decimal) | Hourly Rate (GBP) | Amount (GBP)
Finance - SWEng Group 4 |  | 00:30:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:30:00 | 00:30:00 | Finance | SWEng Group 4 | Weekly finances - Finished off iteration 1, comment of financial positioning going into iteration 2 |  | Louis Newman | lifn501@york.ac.uk |  | Yes | 03/16/2020 | 10:15:00 AM | 03/16/2020 | 10:45:00 AM | 00:30:00 | 0.5 | 12.5 | 6.25
| Louis Newman | 00:30:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:30:00 | 00:30:00 | Software | SWEng Group 4 | Code about favourite recipe |  | Jun Ma | jm2285@york.ac.uk |  | Yes | 03/16/2020 | 08:00:00 PM | 03/16/2020 | 09:00:00 PM | 01:00:00 | 1 | 12.5 | 12.5
Software - SWEng Group 4 |  | 01:00:00 | 11:45:00 | 10:00:00 | 03:15:00 | 03:00:00 | 05:00:00 | 02:00:00 | 36:00:00 | 36:00:00 | Software | SWEng Group 4 | Putting together all of the main components for comments. THe good thing is, these can be reused on the social side when adding comments to any user posts. | User story B6 | Louis Newman | lifn501@york.ac.uk |  | Yes | 03/17/2020 | 09:00:00 AM | 03/17/2020 | 02:00:00 PM | 05:00:00 | 5 | 12.5 | 62.5
| James Pearson | 00:00:00 | 00:00:00 | 04:00:00 | 03:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 07:00:00 | 07:00:00 | Software | SWEng Group 4 | Overhauling meal planner | User story C4 | James Clawley | jc2421@york.ac.uk |  | Yes | 03/17/2020 | 12:00:00 PM | 03/17/2020 | 05:15:00 PM | 05:15:00 | 5.25 | 12.5 | 65.63
| Louis Newman | 00:00:00 | 05:00:00 | 04:00:00 | 00:15:00 | 00:00:00 | 00:00:00 | 00:00:00 | 09:15:00 | 09:15:00 | Testing | SWEng Group 4 | SWEng Group 4: Peer Review - Customer - Text Handler |  | Nathan Billis | ncab500@york.ac.uk |  | Yes | 03/17/2020 | 01:00:00 PM | 03/17/2020 | 01:30:00 PM | 00:30:00 | 0.5 | 12.5 | 6.25
| Rebecca Anderson | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 02:00:00 | 02:00:00 | 02:00:00 | Software | SWEng Group 4 | C12 API Handling | User story C12 | Nathan Billis | ncab500@york.ac.uk |  | Yes | 03/17/2020 | 04:30:00 PM | 03/17/2020 | 06:00:00 PM | 01:30:00 | 1.5 | 12.5 | 18.75
| Nathan Billis | 00:00:00 | 01:30:00 | 02:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 03:30:00 | 03:30:00 | Software | SWEng Group 4 | Finished off, made sure tests pass and added pop out menus for deleting and visiting other users profiles | User story B6 | Louis Newman | lifn501@york.ac.uk |  | Yes | 03/18/2020 | 09:00:00 AM | 03/18/2020 | 01:00:00 PM | 04:00:00 | 4 | 12.5 | 50
| Jun Ma | 01:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 01:00:00 | 01:00:00 | Testing | SWEng Group 4 | PR#35 update and fix all tests, for the user info unit tests | A4 | Nathan Billis | ncab500@york.ac.uk |  | Yes | 03/18/2020 | 09:50:00 AM | 03/18/2020 | 10:05:00 AM | 00:15:00 | 0.25 | 12.5 | 3.13
| Joe Butler | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 03:00:00 | 05:00:00 | 00:00:00 | 08:00:00 | 08:00:00 | Software | SWEng Group 4 | More on C12 API having issues with junit testing | User story C12 | Nathan Billis | ncab500@york.ac.uk |  | Yes | 03/18/2020 | 12:00:00 PM | 03/18/2020 | 02:00:00 PM | 02:00:00 | 2 | 12.5 | 25
| James Clawley | 00:00:00 | 05:15:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 05:15:00 | 05:15:00 | Software | SWEng Group 4 | Changing layout of the recipe info screen to make it scrollable. Got rid of the list view for ingredients and made it a linear layout | User story C14 | James Pearson | jp1439@york.ac.uk |  | Yes | 03/18/2020 | 01:00:00 PM | 03/18/2020 | 05:00:00 PM | 04:00:00 | 4 | 12.5 | 50
Testing - SWEng Group 4 |  | 00:00:00 | 00:30:00 | 00:30:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:30:00 | 01:30:00 | 01:30:00 | Testing | SWEng Group 4 | Pull and review code for B6 comments | B6 | Nathan Billis | ncab500@york.ac.uk |  | Yes | 03/18/2020 | 08:30:00 PM | 03/18/2020 | 08:45:00 PM | 00:15:00 | 0.25 | 12.5 | 3.13
| Nathan Billis | 00:00:00 | 00:30:00 | 00:30:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:30:00 | 01:30:00 | 01:30:00 | Software | SWEng Group 4 | Added extra information to the recipe info screen while hiding some of the info for non paying customers | User story C14 | James Pearson | jp1439@york.ac.uk |  | Yes | 03/19/2020 | 01:00:00 PM | 03/19/2020 | 04:00:00 PM | 03:00:00 | 3 | 12.5 | 37.5
Administration - SWEng Group 4 |  | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:15:00 | 00:15:00 | 00:15:00 | Software | SWEng Group 4 | Assisted Jun with C8, adding the ability to both add and remove favourites. User is notified and this favourite now shows up on the home searches. | User story C8 | Louis Newman | lifn501@york.ac.uk |  | Yes | 03/19/2020 | 07:30:00 PM | 03/19/2020 | 07:45:00 PM | 00:15:00 | 0.25 | 12.5 | 3.13
| James Pearson | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:15:00 | 00:15:00 | 00:15:00 | Software | SWEng Group 4 | 90% finished tests for audio module. Added proper presentation timers. Looked at the shapes module. Had a mini breakdown. Will consider how to go about it tommorow. |  | Joe Butler | jb2200@york.ac.uk |  | Yes | 03/20/2020 | 12:00:00 AM | 03/20/2020 | 03:00:00 AM | 03:00:00 | 3 | 12.5 | 37.5
TOTAL |  | 01:30:00 | 12:15:00 | 10:30:00 | 03:15:00 | 03:00:00 | 05:00:00 | 02:45:00 | 38:15:00 | 38:15:00 | Software | SWEng Group 4 | Finally got audio working through xml. Added timers to presentation so I can test it. |  | Joe Butler | jb2200@york.ac.uk |  | Yes | 03/21/2020 | 02:00:00 AM | 03/21/2020 | 04:00:00 AM | 02:00:00 | 2 | 12.5 | 25
[11 empty] | Software | SWEng Group 4 | Finished timer + audio stuff. |  | Joe Butler | jb2200@york.ac.uk |  | Yes | 03/21/2020 | 08:00:00 PM | 03/21/2020 | 11:00:00 PM | 03:00:00 | 3 | 12.5 | 37.5
[11 empty] | Software | SWEng Group 4 | Re-set up C5 after previous work was lost. Still unsure why, but now set up in new branch | User story C5 | Rebecca Anderson | rea524@york.ac.uk |  | Yes | 03/22/2020 | 09:00:00 AM | 03/22/2020 | 11:00:00 AM | 02:00:00 | 2 | 12.5 | 25
[9 empty] | total | 38.25 | Administration | SWEng Group 4 | Planner adjustments and tracking |  | James Pearson | jp1439@york.ac.uk |  | Yes | 03/22/2020 | 10:00:00 AM | 03/22/2020 | 10:15:00 AM | 00:15:00 | 0.25 | 12.5 | 3.13
[11 empty] | Testing | SWEng Group 4 | Write tests and merge audio and timer to the master |  | Nathan Billis | ncab500@york.ac.uk |  | Yes | 03/22/2020 | 06:15:00 PM | 03/22/2020 | 06:45:00 PM | 00:30:00 | 0.5 | 12.5 | 6.25

## Week 26 Labour
Project | User | 03/23/2020 | 03/24/2020 | 03/25/2020 | 03/26/2020 | 03/27/2020 | 03/28/2020 | 03/29/2020 | Total | Total billable | Project | Client | Description | Task | User | Email | Tags | Billable | Start Date | Start Time | End Date | End Time | Duration (h) | Duration (decimal) | Hourly Rate (GBP) | Amount (GBP)
Finance - SWEng Group 4 |  | 00:45:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:45:00 | 00:45:00 | Meetings | SWEng Group 4 | Group weekly meeting |  | Rebecca Anderson | rea524@york.ac.uk |  | Yes | 03/23/2020 | 09:00:00 AM | 03/23/2020 | 10:00:00 AM | 01:00:00 | 1 | 12.5 | 12.5
| Louis Newman | 00:45:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:45:00 | 00:45:00 | Meetings | SWEng Group 4 | Team meeting |  | James Clawley | jc2421@york.ac.uk |  | Yes | 03/23/2020 | 09:01:00 AM | 03/23/2020 | 10:01:00 AM | 01:00:00 | 1 | 12.5 | 12.5
Meetings - SWEng Group 4 |  | 02:00:00 | 05:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 07:00:00 | 07:00:00 | Finance | SWEng Group 4 | Weekly finances |  | Louis Newman | lifn501@york.ac.uk |  | Yes | 03/23/2020 | 09:30:00 AM | 03/23/2020 | 09:45:00 AM | 00:15:00 | 0.25 | 12.5 | 3.13
| James Pearson | 00:00:00 | 01:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 01:00:00 | 01:00:00 | Finance | SWEng Group 4 | Sorting past three weeks for financial report III |  | Louis Newman | lifn501@york.ac.uk |  | Yes | 03/23/2020 | 09:45:00 AM | 03/23/2020 | 10:15:00 AM | 00:30:00 | 0.5 | 12.5 | 6.25
| Louis Newman | 00:00:00 | 01:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 01:00:00 | 01:00:00 | Administration | SWEng Group 4 | Writing up minutes |  | Rebecca Anderson | rea524@york.ac.uk |  | Yes | 03/23/2020 | 10:00:00 AM | 03/23/2020 | 10:30:00 AM | 00:30:00 | 0.5 | 12.5 | 6.25
| Rebecca Anderson | 01:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 01:00:00 | 01:00:00 | Software | SWEng Group 4 | Adding allergy icons and information | User story C22 | James Pearson | jp1439@york.ac.uk |  | Yes | 03/23/2020 | 01:00:00 PM | 03/23/2020 | 04:00:00 PM | 03:00:00 | 3 | 12.5 | 37.5
| Nathan Billis | 00:00:00 | 01:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 01:00:00 | 01:00:00 | Software | SWEng Group 4 | Meal planner | User story C4 | James Clawley | jc2421@york.ac.uk |  | Yes | 03/24/2020 | 09:00:00 AM | 03/24/2020 | 11:00:00 AM | 02:00:00 | 2 | 12.5 | 25
| Jun Ma | 00:00:00 | 01:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 01:00:00 | 01:00:00 | Meetings | SWEng Group 4 | Weekly meeting |  | Louis Newman | lifn501@york.ac.uk |  | Yes | 03/24/2020 | 10:00:00 AM | 03/24/2020 | 11:00:00 AM | 01:00:00 | 1 | 12.5 | 12.5
| Joe Butler | 00:00:00 | 01:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 01:00:00 | 01:00:00 | Meetings | SWEng Group 4 | Weekly Skype Meeting |  | Nathan Billis | ncab500@york.ac.uk |  | Yes | 03/24/2020 | 10:00:00 AM | 03/24/2020 | 11:00:00 AM | 01:00:00 | 1 | 12.5 | 12.5
| James Clawley | 01:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 01:00:00 | 01:00:00 | Meetings | SWEng Group 4 |  |  | Joe Butler | jb2200@york.ac.uk |  | Yes | 03/24/2020 | 10:00:00 AM | 03/24/2020 | 11:00:00 AM | 01:00:00 | 1 | 12.5 | 12.5
Software - SWEng Group 4 |  | 03:00:00 | 07:30:00 | 10:00:00 | 12:00:00 | 07:00:00 | 02:00:00 | 15:30:00 | 57:00:00 | 57:00:00 | Meetings | SWEng Group 4 | General Meeting |  | James Pearson | jp1439@york.ac.uk |  | Yes | 03/24/2020 | 10:00:00 AM | 03/24/2020 | 11:00:00 AM | 01:00:00 | 1 | 12.5 | 12.5
| James Pearson | 03:00:00 | 04:00:00 | 00:00:00 | 01:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 08:00:00 | 08:00:00 | Software | SWEng Group 4 | Built recycler for social feed and researched how it will all fit together | User story C29 | Louis Newman | lifn501@york.ac.uk |  | Yes | 03/24/2020 | 11:00:00 AM | 03/24/2020 | 12:30:00 PM | 01:30:00 | 1.5 | 12.5 | 18.75
| Louis Newman | 00:00:00 | 01:30:00 | 03:00:00 | 03:00:00 | 02:00:00 | 00:00:00 | 07:30:00 | 17:00:00 | 17:00:00 | Software | SWEng Group 4 | Adding allergy icons and information | User story C22 | James Pearson | jp1439@york.ac.uk |  | Yes | 03/24/2020 | 11:00:00 AM | 03/24/2020 | 03:00:00 PM | 04:00:00 | 4 | 12.5 | 50
| Rebecca Anderson | 00:00:00 | 00:00:00 | 01:00:00 | 00:00:00 | 00:00:00 | 02:00:00 | 03:00:00 | 06:00:00 | 06:00:00 | Meetings | SWEng Group 4 | Weekly meeting |  | Jun Ma | jm2285@york.ac.uk |  | Yes | 03/24/2020 | 10:00:00 PM | 03/24/2020 | 11:00:00 PM | 01:00:00 | 1 | 12.5 | 12.5
| Nathan Billis | 00:00:00 | 00:00:00 | 01:00:00 | 00:00:00 | 02:00:00 | 00:00:00 | 00:00:00 | 03:00:00 | 03:00:00 | Software | SWEng Group 4 | Set connections up and got data to be displayed on the screen | User story C5 | Rebecca Anderson | rea524@york.ac.uk |  | Yes | 03/25/2020 | 08:00:00 AM | 03/25/2020 | 09:00:00 AM | 01:00:00 | 1 | 12.5 | 12.5
| Jun Ma | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 01:00:00 | 01:00:00 | 01:00:00 | Software | SWEng Group 4 | Meal planner | User story C4 | James Clawley | jc2421@york.ac.uk |  | Yes | 03/25/2020 | 09:00:00 AM | 03/25/2020 | 12:00:00 PM | 03:00:00 | 3 | 12.5 | 37.5
| Joe Butler | 00:00:00 | 00:00:00 | 02:00:00 | 06:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 08:00:00 | 08:00:00 | Software | SWEng Group 4 | Building the social feed components and back end | User story C29 | Louis Newman | lifn501@york.ac.uk |  | Yes | 03/25/2020 | 11:00:00 AM | 03/25/2020 | 02:00:00 PM | 03:00:00 | 3 | 12.5 | 37.5
| James Clawley | 00:00:00 | 02:00:00 | 03:00:00 | 02:00:00 | 03:00:00 | 00:00:00 | 04:00:00 | 14:00:00 | 14:00:00 | Software | SWEng Group 4 | Working on C12 | User story C12 | Nathan Billis | ncab500@york.ac.uk |  | Yes | 03/25/2020 | 11:00:00 AM | 03/25/2020 | 12:00:00 PM | 01:00:00 | 1 | 12.5 | 12.5
Testing - SWEng Group 4 |  | 00:00:00 | 00:00:00 | 03:00:00 | 02:30:00 | 00:00:00 | 00:00:00 | 00:00:00 | 05:30:00 | 05:30:00 | Testing | SWEng Group 4 | Test for C8 |  | Jun Ma | jm2285@york.ac.uk |  | Yes | 03/25/2020 | 02:00:00 PM | 03/25/2020 | 03:00:00 PM | 01:00:00 | 1 | 12.5 | 12.5
| Nathan Billis | 00:00:00 | 00:00:00 | 02:00:00 | 02:30:00 | 00:00:00 | 00:00:00 | 00:00:00 | 04:30:00 | 04:30:00 | Testing | SWEng Group 4 | Worked on merging C4 | C4 | Nathan Billis | ncab500@york.ac.uk |  | Yes | 03/25/2020 | 03:00:00 PM | 03/25/2020 | 04:00:00 PM | 01:00:00 | 1 | 12.5 | 12.5
| Jun Ma | 00:00:00 | 00:00:00 | 01:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 01:00:00 | 01:00:00 | Testing | SWEng Group 4 | Helping people out and peer review | C8 | Nathan Billis | ncab500@york.ac.uk |  | Yes | 03/25/2020 | 04:00:00 PM | 03/25/2020 | 05:00:00 PM | 01:00:00 | 1 | 12.5 | 12.5
Administration - SWEng Group 4 |  | 00:30:00 | 00:00:00 | 00:15:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:15:00 | 01:00:00 | 01:00:00 | Administration | SWEng Group 4 | Writing Wiki article |  | Nathan Billis | ncab500@york.ac.uk |  | Yes | 03/25/2020 | 05:00:00 PM | 03/25/2020 | 05:15:00 PM | 00:15:00 | 0.25 | 12.5 | 3.13
| James Pearson | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:15:00 | 00:15:00 | 00:15:00 | Software | SWEng Group 4 | Added new test screen keyword support and started adding profile image stuff |  | Joe Butler | jb2200@york.ac.uk |  | Yes | 03/25/2020 | 08:00:00 PM | 03/25/2020 | 10:00:00 PM | 02:00:00 | 2 | 12.5 | 25
| Rebecca Anderson | 00:30:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:30:00 | 00:30:00 | Software | SWEng Group 4 | Meal planner | User story C4 | James Clawley | jc2421@york.ac.uk |  | Yes | 03/26/2020 | 08:00:00 AM | 03/26/2020 | 10:00:00 AM | 02:00:00 | 2 | 12.5 | 25
| Nathan Billis | 00:00:00 | 00:00:00 | 00:15:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:15:00 | 00:15:00 | Software | SWEng Group 4 | Fixing and testing social feed to display posts in order | User story C29 | Louis Newman | lifn501@york.ac.uk |  | Yes | 03/26/2020 | 11:00:00 AM | 03/26/2020 | 02:00:00 PM | 03:00:00 | 3 | 12.5 | 37.5
Design - SWEng Group 4 |  | 00:00:00 | 00:00:00 | 00:00:00 | 01:00:00 | 01:00:00 | 00:00:00 | 00:00:00 | 02:00:00 | 02:00:00 | Testing | SWEng Group 4 | Intergration of C4 | C4 | Nathan Billis | ncab500@york.ac.uk |  | Yes | 03/26/2020 | 11:00:00 AM | 03/26/2020 | 12:30:00 PM | 01:30:00 | 1.5 | 12.5 | 18.75
| Jun Ma | 00:00:00 | 00:00:00 | 00:00:00 | 01:00:00 | 01:00:00 | 00:00:00 | 00:00:00 | 02:00:00 | 02:00:00 | Software | SWEng Group 4 | Wrote tests and PR'd | User story C22 | James Pearson | jp1439@york.ac.uk |  | Yes | 03/26/2020 | 03:00:00 PM | 03/26/2020 | 04:00:00 PM | 01:00:00 | 1 | 12.5 | 12.5
TOTAL |  | 06:15:00 | 12:30:00 | 13:15:00 | 15:30:00 | 08:00:00 | 02:00:00 | 15:45:00 | 73:15:00 | 73:15:00 | Testing | SWEng Group 4 | Integration of C14C22 |  | Nathan Billis | ncab500@york.ac.uk |  | Yes | 03/26/2020 | 05:00:00 PM | 03/26/2020 | 06:00:00 PM | 01:00:00 | 1 | 12.5 | 12.5
[11 empty] | Software | SWEng Group 4 | Fixed initial preferences styling, added images to the profile (took forever), began splitting preferences into individual fragments. |  | Joe Butler | jb2200@york.ac.uk |  | Yes | 03/26/2020 | 06:00:00 PM | 03/27/2020 | 12:00:00 AM | 06:00:00 | 6 | 12.5 | 75
[9 empty] | total | 73.25 | Design | SWEng Group 4 | Design about timeline |  | Jun Ma | jm2285@york.ac.uk |  | Yes | 03/26/2020 | 08:00:00 PM | 03/26/2020 | 09:00:00 PM | 01:00:00 | 1 | 12.5 | 12.5
[11 empty] | Design | SWEng Group 4 | Design about timeline |  | Jun Ma | jm2285@york.ac.uk |  | Yes | 03/27/2020 | 03:00:00 AM | 03/27/2020 | 04:00:00 AM | 01:00:00 | 1 | 12.5 | 12.5
[11 empty] | Software | SWEng Group 4 | Continued the build. displays as it should. need to add functionality to add photo, review & picture | User story C29 | Louis Newman | lifn501@york.ac.uk |  | Yes | 03/27/2020 | 09:00:00 AM | 03/27/2020 | 11:00:00 AM | 02:00:00 | 2 | 12.5 | 25
[11 empty] | Software | SWEng Group 4 | Adapting graphics package | User story B1 | James Clawley | jc2421@york.ac.uk |  | Yes | 03/27/2020 | 10:00:00 AM | 03/27/2020 | 01:00:00 PM | 03:00:00 | 3 | 12.5 | 37.5
[11 empty] | Software | SWEng Group 4 | Bug Fixes for Fav and Presentation | User story B2 | Nathan Billis | ncab500@york.ac.uk |  | Yes | 03/27/2020 | 11:30:00 AM | 03/27/2020 | 01:30:00 PM | 02:00:00 | 2 | 12.5 | 25
[11 empty] | Software | SWEng Group 4 | Tried to set up a button to export shopping list but struggled to left that and concentrated on displaying the meal planner. Finding this harder then expected and need to spend more time figuring it out | User story C5 | Rebecca Anderson | rea524@york.ac.uk |  | Yes | 03/28/2020 | 08:00:00 AM | 03/28/2020 | 10:00:00 AM | 02:00:00 | 2 | 12.5 | 25
[11 empty] | Software | SWEng Group 4 |  | User story C5 | Rebecca Anderson | rea524@york.ac.uk |  | Yes | 03/29/2020 | 09:00:00 AM | 03/29/2020 | 12:00:00 PM | 03:00:00 | 3 | 12.5 | 37.5
[11 empty] | Software | SWEng Group 4 | Adapting graphics package | User story B1 | James Clawley | jc2421@york.ac.uk |  | Yes | 03/29/2020 | 09:00:00 AM | 03/29/2020 | 12:00:00 PM | 03:00:00 | 3 | 12.5 | 37.5
[11 empty] | Software | SWEng Group 4 | Tried to get the back end to update the followers collection. Has been a bit of a nightmare through and through. Involved a lot of research and learning typescript. Managed to get basic functions working but was having issues getting arrays to update and repopulate via typescript. Ended up purchasing a course through fireship.io to learn more about cloud functions and data structures but these could again only get me so far. I think a redesign of the followers collection is now necessary as Firestore array manipulation only works with basic variables and I have been unable to get arrays to populate at all in Typescript. I think I have found a new solution, however there will be need for more variables within the document to track positions, however this will allow the use of maps and will allow updating of fewer variables within the Firestore. | User story C29 | Louis Newman | lifn501@york.ac.uk |  | Yes | 03/29/2020 | 11:00:00 AM | 03/29/2020 | 05:30:00 PM | 06:30:00 | 6.5 | 12.5 | 81.25
[11 empty] | Software | SWEng Group 4 | Xml Parser updates |  | James Clawley | jc2421@york.ac.uk |  | Yes | 03/29/2020 | 12:00:00 PM | 03/29/2020 | 01:00:00 PM | 01:00:00 | 1 | 12.5 | 12.5
[11 empty] | Administration | SWEng Group 4 | Agenda and Meeting prep |  | James Pearson | jp1439@york.ac.uk |  | Yes | 03/29/2020 | 12:30:00 PM | 03/29/2020 | 12:45:00 PM | 00:15:00 | 0.25 | 12.5 | 3.13
[11 empty] | Software | SWEng Group 4 | Changed data structure to maps and managed to get the data refreshing as it should from the cloud function | User story C29 | Louis Newman | lifn501@york.ac.uk |  | Yes | 03/29/2020 | 07:00:00 PM | 03/29/2020 | 08:00:00 PM | 01:00:00 | 1 | 12.5 | 12.5
[11 empty] | Software | SWEng Group 4 | Coding about the timeline |  | Jun Ma | jm2285@york.ac.uk |  | Yes | 03/29/2020 | 08:30:00 PM | 03/29/2020 | 09:30:00 PM | 01:00:00 | 1 | 12.5 | 12.5

## Week 27 Labour
Project | User | 03/30/2020 | 03/31/2020 | 04/01/2020 | 04/02/2020 | 04/03/2020 | 04/04/2020 | 04/05/2020 | Total | Billable hours | Project | Client | Description | Task | User | Email | Tags | Billable | Start Date | Start Time | End Date | End Time | Duration (h) | Duration (decimal) | Hourly Rate (GBP) | Amount (GBP)
Finance - SWEng Group 4 |  | 00:30:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:30:00 | 00:30:00 | Meetings | SWEng Group 4 | Meeting |  | Rebecca Anderson | rea524@york.ac.uk |  | Yes | 03/30/2020 | 09:00:00 AM | 03/30/2020 | 09:30:00 AM | 00:30:00 | 0.5 | 12.5 | 6.25
| Louis Newman | 00:30:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:30:00 | 00:30:00 | Meetings | SWEng Group 4 |  |  | James Clawley | jc2421@york.ac.uk |  | Yes | 03/30/2020 | 09:00:00 AM | 03/30/2020 | 09:45:00 AM | 00:45:00 | 0.75 | 12.5 | 9.38
Meetings - SWEng Group 4 |  | 04:15:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 04:15:00 | 04:15:00 | Administration | SWEng Group 4 | meeting notes |  | Rebecca Anderson | rea524@york.ac.uk |  | Yes | 03/30/2020 | 09:30:00 AM | 03/30/2020 | 10:00:00 AM | 00:30:00 | 0.5 | 12.5 | 6.25
| James Pearson | 00:30:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:30:00 | 00:30:00 | Meetings | SWEng Group 4 | Team meeting |  | Louis Newman | lifn501@york.ac.uk |  | Yes | 03/30/2020 | 10:00:00 AM | 03/30/2020 | 10:30:00 AM | 00:30:00 | 0.5 | 12.5 | 6.25
| Louis Newman | 00:30:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:30:00 | 00:30:00 | Meetings | SWEng Group 4 | Weekly Skype Meeting |  | Nathan Billis | ncab500@york.ac.uk |  | Yes | 03/30/2020 | 10:00:00 AM | 03/30/2020 | 10:30:00 AM | 00:30:00 | 0.5 | 12.5 | 6.25
| Rebecca Anderson | 00:30:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:30:00 | 00:30:00 | Meetings | SWEng Group 4 | Meeting |  | Joe Butler | jb2200@york.ac.uk |  | Yes | 03/30/2020 | 10:00:00 AM | 03/30/2020 | 10:45:00 AM | 00:45:00 | 0.75 | 12.5 | 9.38
| Nathan Billis | 00:30:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:30:00 | 00:30:00 | Meetings | SWEng Group 4 | Weekly team meeting |  | Jun Ma | jm2285@york.ac.uk |  | Yes | 03/30/2020 | 10:00:00 AM | 03/30/2020 | 10:45:00 AM | 00:45:00 | 0.75 | 12.5 | 9.38
| Jun Ma | 00:45:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:45:00 | 00:45:00 | Meetings | SWEng Group 4 | General team meeting |  | James Pearson | jp1439@york.ac.uk |  | Yes | 03/30/2020 | 10:00:00 AM | 03/30/2020 | 10:30:00 AM | 00:30:00 | 0.5 | 12.5 | 6.25
| Joe Butler | 00:45:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:45:00 | 00:45:00 | Finance | SWEng Group 4 | Weekly finances |  | Louis Newman | lifn501@york.ac.uk |  | Yes | 03/30/2020 | 11:00:00 AM | 03/30/2020 | 11:30:00 AM | 00:30:00 | 0.5 | 12.5 | 6.25
| James Clawley | 00:45:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:45:00 | 00:45:00 | Software | SWEng Group 4 | Finished new user profile design layout and function. Refactored basically everything by this point to fit new spec for public profile and profile settings. Some bugs still exist but there relatively small. Testing not done yet. |  | Joe Butler | jb2200@york.ac.uk |  | Yes | 03/30/2020 | 06:00:00 PM | 03/31/2020 | 02:00:00 AM | 08:00:00 | 8 | 12.5 | 100
Software - SWEng Group 4 |  | 08:00:00 | 07:00:00 | 09:00:00 | 09:00:00 | 09:00:00 | 01:00:00 | 00:00:00 | 43:00:00 | 43:00:00 | Software | SWEng Group 4 | information screens |  | Rebecca Anderson | rea524@york.ac.uk |  | Yes | 03/31/2020 | 09:00:00 AM | 03/31/2020 | 11:00:00 AM | 02:00:00 | 2 | 12.5 | 25
| James Pearson | 00:00:00 | 00:00:00 | 02:00:00 | 02:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 04:00:00 | 04:00:00 | Software | SWEng Group 4 |  | User story A12 | James Clawley | jc2421@york.ac.uk |  | Yes | 03/31/2020 | 09:00:00 AM | 03/31/2020 | 12:00:00 PM | 03:00:00 | 3 | 12.5 | 37.5
| Louis Newman | 00:00:00 | 02:00:00 | 02:00:00 | 01:00:00 | 01:00:00 | 01:00:00 | 00:00:00 | 07:00:00 | 07:00:00 | Software | SWEng Group 4 | Building the feed UI, comments, getting a like button and adding all elements to a post | User story C16 | Louis Newman | lifn501@york.ac.uk |  | Yes | 03/31/2020 | 02:00:00 PM | 03/31/2020 | 04:00:00 PM | 02:00:00 | 2 | 12.5 | 25
| Rebecca Anderson | 00:00:00 | 02:00:00 | 00:00:00 | 01:00:00 | 02:00:00 | 00:00:00 | 00:00:00 | 05:00:00 | 05:00:00 | Software | SWEng Group 4 |  | User story A12 | James Clawley | jc2421@york.ac.uk |  | Yes | 04/01/2020 | 09:00:00 AM | 04/01/2020 | 12:00:00 PM | 03:00:00 | 3 | 12.5 | 37.5
| Nathan Billis | 00:00:00 | 00:00:00 | 01:00:00 | 02:00:00 | 04:00:00 | 00:00:00 | 00:00:00 | 07:00:00 | 07:00:00 | Software | SWEng Group 4 | Finishing touches to feed | User story C16 | Louis Newman | lifn501@york.ac.uk |  | Yes | 04/01/2020 | 10:01:00 AM | 04/01/2020 | 12:01:00 PM | 02:00:00 | 2 | 12.5 | 25
| Jun Ma | 00:00:00 | 00:00:00 | 00:00:00 | 01:00:00 | 01:00:00 | 00:00:00 | 00:00:00 | 02:00:00 | 02:00:00 | Software | SWEng Group 4 | Implementing the review and rating tab | User story C9 | James Pearson | jp1439@york.ac.uk |  | Yes | 04/01/2020 | 11:00:00 AM | 04/01/2020 | 01:00:00 PM | 02:00:00 | 2 | 12.5 | 25
| Joe Butler | 08:00:00 | 00:00:00 | 01:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 09:00:00 | 09:00:00 | Software | SWEng Group 4 | Started work on search refactor |  | Nathan Billis | ncab500@york.ac.uk |  | Yes | 04/01/2020 | 01:00:00 PM | 04/01/2020 | 02:00:00 PM | 01:00:00 | 1 | 12.5 | 12.5
| James Clawley | 00:00:00 | 03:00:00 | 03:00:00 | 02:00:00 | 01:00:00 | 00:00:00 | 00:00:00 | 09:00:00 | 09:00:00 | Software | SWEng Group 4 | Prepared user info and profile settings ready for merge pull request. |  | Joe Butler | jb2200@york.ac.uk |  | Yes | 04/01/2020 | 08:00:00 PM | 04/01/2020 | 09:00:00 PM | 01:00:00 | 1 | 12.5 | 12.5
Administration - SWEng Group 4 |  | 00:30:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:30:00 | 00:30:00 | Software | SWEng Group 4 | information screens |  | Rebecca Anderson | rea524@york.ac.uk |  | Yes | 04/02/2020 | 09:00:00 AM | 04/02/2020 | 10:00:00 AM | 01:00:00 | 1 | 12.5 | 12.5
| Rebecca Anderson | 00:30:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:30:00 | 00:30:00 | Software | SWEng Group 4 |  | User story A12 | James Clawley | jc2421@york.ac.uk |  | Yes | 04/02/2020 | 09:00:00 AM | 04/02/2020 | 11:00:00 AM | 02:00:00 | 2 | 12.5 | 25
TOTAL |  | 13:15:00 | 07:00:00 | 09:00:00 | 09:00:00 | 09:00:00 | 01:00:00 | 00:00:00 | 48:15:00 | 48:15:00 | Software | SWEng Group 4 | Added Algolia and uploaded data from firebase |  | Nathan Billis | ncab500@york.ac.uk |  | Yes | 04/02/2020 | 11:00:00 AM | 04/02/2020 | 01:00:00 PM | 02:00:00 | 2 | 12.5 | 25
[11 empty] | Software | SWEng Group 4 | integrating all parts to a post | User story C16 | Louis Newman | lifn501@york.ac.uk |  | Yes | 04/02/2020 | 12:00:00 PM | 04/02/2020 | 01:00:00 PM | 01:00:00 | 1 | 12.5 | 12.5
[9 empty] | Total: | 48.25 | Software | SWEng Group 4 | Implementing the review and rating tab | User story C9 | James Pearson | jp1439@york.ac.uk |  | Yes | 04/02/2020 | 02:00:00 PM | 04/02/2020 | 04:00:00 PM | 02:00:00 | 2 | 12.5 | 25
[11 empty] | Software | SWEng Group 4 | Coding about new queries and add types in database. Save the space for favourite recipes |  | Jun Ma | jm2285@york.ac.uk |  | Yes | 04/02/2020 | 08:00:00 PM | 04/02/2020 | 09:00:00 PM | 01:00:00 | 1 | 12.5 | 12.5
[11 empty] | Software | SWEng Group 4 | Editing profile page to hold a timeline/picture feed/recipes | User story C16 | Louis Newman | lifn501@york.ac.uk |  | Yes | 04/03/2020 | 09:00:00 AM | 04/03/2020 | 10:00:00 AM | 01:00:00 | 1 | 12.5 | 12.5
[11 empty] | Software | SWEng Group 4 | information screens |  | Rebecca Anderson | rea524@york.ac.uk |  | Yes | 04/03/2020 | 09:00:00 AM | 04/03/2020 | 11:00:00 AM | 02:00:00 | 2 | 12.5 | 25
[11 empty] | Software | SWEng Group 4 |  | User story A12 | James Clawley | jc2421@york.ac.uk |  | Yes | 04/03/2020 | 09:00:00 AM | 04/03/2020 | 10:00:00 AM | 01:00:00 | 1 | 12.5 | 12.5
[11 empty] | Software | SWEng Group 4 | Fixed search functionality without filters |  | Nathan Billis | ncab500@york.ac.uk |  | Yes | 04/03/2020 | 01:00:00 PM | 04/03/2020 | 03:00:00 PM | 02:00:00 | 2 | 12.5 | 25
[11 empty] | Software | SWEng Group 4 | Finish off search and add back filters |  | Nathan Billis | ncab500@york.ac.uk |  | Yes | 04/03/2020 | 04:00:00 PM | 04/03/2020 | 06:00:00 PM | 02:00:00 | 2 | 12.5 | 25
[11 empty] | Software | SWEng Group 4 | Coding about type fragments |  | Jun Ma | jm2285@york.ac.uk |  | Yes | 04/03/2020 | 09:00:00 PM | 04/03/2020 | 10:00:00 PM | 01:00:00 | 1 | 12.5 | 12.5
[11 empty] | Software | SWEng Group 4 | Adding followers and following to profile and options for either public or private to settings | User story C16 | Louis Newman | lifn501@york.ac.uk |  | Yes | 04/04/2020 | 09:00:00 AM | 04/04/2020 | 10:00:00 AM | 01:00:00 | 1 | 12.5 | 12.5

## Week 28 Labour
Project | User | 04/06/2020 | 04/07/2020 | 04/08/2020 | 04/09/2020 | 04/10/2020 | 04/11/2020 | 04/12/2020 | Total | Billable total | Project | Client | Description | Task | User | Email | Tags | Billable | Start Date | Start Time | End Date | End Time | Duration (h) | Duration (decimal) | Hourly Rate (GBP) | Amount (GBP)
Finance - SWEng Group 4 |  | 00:15:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:15:00 | 00:15:00 | Meetings | SWEng Group 4 | Group weekly meeting |  | Rebecca Anderson | rea524@york.ac.uk |  | Yes | 04/06/2020 | 09:00:00 AM | 04/06/2020 | 09:45:00 AM | 00:45:00 | 0.75 | 12.5 | 9.38
| Louis Newman | 00:15:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:15:00 | 00:15:00 | Meetings | SWEng Group 4 | Team meeting |  | James Clawley | jc2421@york.ac.uk |  | Yes | 04/06/2020 | 09:00:00 AM | 04/06/2020 | 09:45:00 AM | 00:45:00 | 0.75 | 12.5 | 9.38
Meetings - SWEng Group 4 |  | 04:30:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 04:30:00 | 04:30:00 | Meetings | SWEng Group 4 | Team meeting |  | Louis Newman | lifn501@york.ac.uk |  | Yes | 04/06/2020 | 10:00:00 AM | 04/06/2020 | 10:45:00 AM | 00:45:00 | 0.75 | 12.5 | 9.38
| James Pearson | 00:45:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:45:00 | 00:45:00 | Meetings | SWEng Group 4 | meetings |  | Nathan Billis | ncab500@york.ac.uk |  | Yes | 04/06/2020 | 10:00:00 AM | 04/06/2020 | 10:45:00 AM | 00:45:00 | 0.75 | 12.5 | 9.38
| Louis Newman | 00:45:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:45:00 | 00:45:00 | Meetings | SWEng Group 4 | weekly team meeting |  | Jun Ma | jm2285@york.ac.uk |  | Yes | 04/06/2020 | 10:00:00 AM | 04/06/2020 | 10:45:00 AM | 00:45:00 | 0.75 | 12.5 | 9.38
| Rebecca Anderson | 00:45:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:45:00 | 00:45:00 | Meetings | SWEng Group 4 | General Meeting |  | James Pearson | jp1439@york.ac.uk |  | Yes | 04/06/2020 | 10:00:00 AM | 04/06/2020 | 10:45:00 AM | 00:45:00 | 0.75 | 12.5 | 9.38
| Nathan Billis | 00:45:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:45:00 | 00:45:00 | Software | SWEng Group 4 | Building user generated recipe functionality | User story A12 | James Clawley | jc2421@york.ac.uk |  | Yes | 04/06/2020 | 12:45:00 PM | 04/06/2020 | 04:45:00 PM | 04:00:00 | 4 | 12.5 | 50
| Jun Ma | 00:45:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:45:00 | 00:45:00 | Finance | SWEng Group 4 | Weekly finances |  | Louis Newman | lifn501@york.ac.uk |  | Yes | 04/06/2020 | 05:00:00 PM | 04/06/2020 | 05:15:00 PM | 00:15:00 | 0.25 | 12.5 | 3.13
| James Clawley | 00:45:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:45:00 | 00:45:00 | Software | SWEng Group 4 | Rebase the master branch to the TimeFrame branch and do some fix | User story C17 | Jun Ma | jm2285@york.ac.uk |  | Yes | 04/06/2020 | 07:30:00 PM | 04/06/2020 | 08:30:00 PM | 01:00:00 | 1 | 12.5 | 12.5
Quality Manual - SWEng Group 4 |  | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:15:00 | 00:00:00 | 00:15:00 | 00:15:00 | Software | SWEng Group 4 | Successfully got posts posting and populating on the feed | User story C29 | Louis Newman | lifn501@york.ac.uk |  | Yes | 04/07/2020 | 09:00:00 AM | 04/07/2020 | 11:00:00 AM | 02:00:00 | 2 | 12.5 | 25
| James Pearson | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:15:00 | 00:00:00 | 00:15:00 | 00:15:00 | Software | SWEng Group 4 | Fixed bugs with the feed and got endless scroll operating as we would like | User story C29 | Louis Newman | lifn501@york.ac.uk |  | Yes | 04/08/2020 | 09:00:00 AM | 04/08/2020 | 11:00:00 AM | 02:00:00 | 2 | 12.5 | 25
Software - SWEng Group 4 |  | 05:00:00 | 02:00:00 | 06:30:00 | 02:00:00 | 00:30:00 | 00:00:00 | 00:00:00 | 16:00:00 | 16:00:00 | Software | SWEng Group 4 | Sorted maps on firestore and linked with code | User story C9 | James Pearson | jp1439@york.ac.uk |  | Yes | 04/08/2020 | 01:00:00 PM | 04/08/2020 | 02:00:00 PM | 01:00:00 | 1 | 12.5 | 12.5
| James Pearson | 00:00:00 | 00:00:00 | 01:00:00 | 02:00:00 | 00:30:00 | 00:00:00 | 00:00:00 | 03:30:00 | 03:30:00 | Software | SWEng Group 4 | Do the test for the C17 and write the test report. Fix some bug in the meantime. | User story C17 | Jun Ma | jm2285@york.ac.uk |  | Yes | 04/08/2020 | 08:30:00 PM | 04/08/2020 | 10:15:00 PM | 01:45:00 | 1.75 | 12.5 | 21.88
| Louis Newman | 00:00:00 | 02:00:00 | 02:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 04:00:00 | 04:00:00 | Software | SWEng Group 4 | Refactored userinfoprivate class to include a proper intent return. Had some issues implementing the privacy stuff. Will likely split into fragments. | User story A4 | Joe Butler | jb2200@york.ac.uk |  | Yes | 04/08/2020 | 10:00:00 PM | 04/08/2020 | 11:45:00 PM | 01:45:00 | 1.75 | 12.5 | 21.88
| Jun Ma | 01:00:00 | 00:00:00 | 01:45:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 02:45:00 | 02:45:00 | Software | SWEng Group 4 | Fixing bugs. Could change map data with floats but later, maps could only be changed by doubles. | User story C9 | James Pearson | jp1439@york.ac.uk |  | Yes | 04/09/2020 | 11:00:00 AM | 04/09/2020 | 01:00:00 PM | 02:00:00 | 2 | 12.5 | 25
| Joe Butler | 00:00:00 | 00:00:00 | 01:45:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 01:45:00 | 01:45:00 | Marketing | SWEng Group 4 | Created new marketing plan and created a survey for the market audience. |  | Rebecca Anderson | rea524@york.ac.uk |  | Yes | 04/10/2020 | 09:00:00 AM | 04/10/2020 | 11:00:00 AM | 02:00:00 | 2 | 12.5 | 25
| James Clawley | 04:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 04:00:00 | 04:00:00 | Software | SWEng Group 4 | Added ability to refresh info screen in real time. Drew up plans for next part of review story | User story C9 | James Pearson | jp1439@york.ac.uk |  | Yes | 04/10/2020 | 01:00:00 PM | 04/10/2020 | 01:30:00 PM | 00:30:00 | 0.5 | 12.5 | 6.25
Marketing - SWEng Group 4 |  | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 02:00:00 | 00:00:00 | 00:00:00 | 02:00:00 | 02:00:00 | Quality Manual | SWEng Group 4 | Updated QA to reflect new working methods |  | James Pearson | jp1439@york.ac.uk |  | Yes | 04/11/2020 | 11:00:00 AM | 04/11/2020 | 11:15:00 AM | 00:15:00 | 0.25 | 12.5 | 3.13
| Rebecca Anderson | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 02:00:00 | 00:00:00 | 00:00:00 | 02:00:00 | 02:00:00
TOTAL |  | 09:45:00 | 02:00:00 | 06:30:00 | 02:00:00 | 02:30:00 | 00:15:00 | 00:00:00 | 23:00:00 | 23:00:00
[9 empty] | totat: | 23

## Week 29 Labour
Project | User | 04/13/2020 | 04/14/2020 | 04/15/2020 | 04/16/2020 | 04/17/2020 | 04/18/2020 | 04/19/2020 | Total | Billable total | Project | Client | Description | Task | User | Email | Tags | Billable | Start Date | Start Time | End Date | End Time | Duration (h) | Duration (decimal) | Hourly Rate (GBP) | Amount (GBP)
Finance - SWEng Group 4 |  | 00:00:00 | 00:00:00 | 00:15:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:15:00 | 00:15:00 | Meetings | SWEng Group 4 | group weekly meeting |  | Rebecca Anderson | rea524@york.ac.uk |  | Yes | 04/13/2020 | 09:00:00 AM | 04/13/2020 | 09:30:00 AM | 00:30:00 | 0.5 | 12.5 | 6.25
| Louis Newman | 00:00:00 | 00:00:00 | 00:15:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:15:00 | 00:15:00 | Quality Manual | SWEng Group 4 | Updating QA manual with new plan |  | Rebecca Anderson | rea524@york.ac.uk |  | Yes | 04/13/2020 | 09:30:00 AM | 04/13/2020 | 09:45:00 AM | 00:15:00 | 0.25 | 12.5 | 3.13
Meetings - SWEng Group 4 |  | 03:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 03:00:00 | 03:00:00 | Administration | SWEng Group 4 | Minuets write up |  | Rebecca Anderson | rea524@york.ac.uk |  | Yes | 04/13/2020 | 09:45:00 AM | 04/13/2020 | 10:00:00 AM | 00:15:00 | 0.25 | 12.5 | 3.13
| James Pearson | 00:30:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:30:00 | 00:30:00 | Meetings | SWEng Group 4 | Team meeting |  | Louis Newman | lifn501@york.ac.uk |  | Yes | 04/13/2020 | 10:00:00 AM | 04/13/2020 | 10:30:00 AM | 00:30:00 | 0.5 | 12.5 | 6.25
| Louis Newman | 00:30:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:30:00 | 00:30:00 | Meetings | SWEng Group 4 | Weekly Meeting |  | Nathan Billis | ncab500@york.ac.uk |  | Yes | 04/13/2020 | 10:00:00 AM | 04/13/2020 | 10:30:00 AM | 00:30:00 | 0.5 | 12.5 | 6.25
| Rebecca Anderson | 00:30:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:30:00 | 00:30:00 | Meetings | SWEng Group 4 | Weekly meeting |  | Joe Butler | jb2200@york.ac.uk |  | Yes | 04/13/2020 | 10:00:00 AM | 04/13/2020 | 10:30:00 AM | 00:30:00 | 0.5 | 12.5 | 6.25
| Nathan Billis | 00:30:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:30:00 | 00:30:00 | Meetings | SWEng Group 4 | Team meeting |  | James Clawley | jc2421@york.ac.uk |  | Yes | 04/13/2020 | 10:00:00 AM | 04/13/2020 | 10:30:00 AM | 00:30:00 | 0.5 | 12.5 | 6.25
| Joe Butler | 00:30:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:30:00 | 00:30:00 | Meetings | SWEng Group 4 | General team meeting |  | James Pearson | jp1439@york.ac.uk |  | Yes | 04/13/2020 | 10:00:00 AM | 04/13/2020 | 10:30:00 AM | 00:30:00 | 0.5 | 12.5 | 6.25
| James Clawley | 00:30:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:30:00 | 00:30:00 | Quality Manual | SWEng Group 4 | updated QA Manual with COVID-19 details |  | Nathan Billis | ncab500@york.ac.uk |  | Yes | 04/13/2020 | 10:45:00 AM | 04/13/2020 | 11:00:00 AM | 00:15:00 | 0.25 | 12.5 | 3.13
Quality Manual - SWEng Group 4 |  | 00:30:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:30:00 | 00:30:00 | Design | SWEng Group 4 | Fixed 3 layout issues with the app. - portrait > landscape crashes. - Kitkat 4.4 issues , crashing. Switched to minimum version of 5.0. - adjusted filter search design to accommodate older android SDK versions. |  | Joe Butler | jb2200@york.ac.uk |  | Yes | 04/14/2020 | 01:00:00 AM | 04/14/2020 | 02:00:00 AM | 01:00:00 | 1 | 12.5 | 12.5
| Rebecca Anderson | 00:15:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:15:00 | 00:15:00 | Marketing | SWEng Group 4 | Ethics forms and finishing the survey and sending the survey out on multiple platforms. |  | Rebecca Anderson | rea524@york.ac.uk |  | Yes | 04/14/2020 | 09:00:00 AM | 04/14/2020 | 12:00:00 PM | 03:00:00 | 3 | 12.5 | 37.5
| Nathan Billis | 00:15:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:15:00 | 00:15:00 | Software | SWEng Group 4 | Finished tests for the user profile settings and public profile. | User story A11 | Joe Butler | jb2200@york.ac.uk |  | Yes | 04/14/2020 | 10:00:00 PM | 04/15/2020 | 01:00:00 AM | 03:00:00 | 3 | 12.5 | 37.5
Software - SWEng Group 4 |  | 00:00:00 | 03:00:00 | 00:30:14 | 02:00:00 | 03:00:00 | 05:00:00 | 18:30:00 | 32:00:14 | 32:00:14 | Software | SWEng Group 4 | Wrote and ran kudos tests | User story A10 | Joe Butler | jb2200@york.ac.uk |  | Yes | 04/15/2020 | 03:00:00 AM | 04/15/2020 | 03:30:14 AM | 00:30:14 | 0.50389 | 12.5 | 6.3
| James Pearson | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 03:00:00 | 02:00:00 | 05:00:00 | 05:00:00 | Testing | SWEng Group 4 | Testing A4 A11 Pull request | A4 | Nathan Billis | ncab500@york.ac.uk |  | Yes | 04/15/2020 | 11:00:00 AM | 04/15/2020 | 11:30:00 AM | 00:30:00 | 0.5 | 12.5 | 6.25
| Louis Newman | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 10:00:00 | 10:00:00 | 10:00:00 | Finance | SWEng Group 4 | Weekly finances |  | Louis Newman | lifn501@york.ac.uk |  | Yes | 04/15/2020 | 12:00:00 PM | 04/15/2020 | 12:15:00 PM | 00:15:00 | 0.25 | 12.5 | 3.13
| Rebecca Anderson | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 01:30:00 | 01:30:00 | 01:30:00 | Marketing | SWEng Group 4 | collecting figures are writing up findings |  | Rebecca Anderson | rea524@york.ac.uk |  | Yes | 04/16/2020 | 10:30:00 AM | 04/16/2020 | 12:15:00 PM | 01:45:00 | 1.75 | 12.5 | 21.88
| Nathan Billis | 00:00:00 | 00:00:00 | 00:00:00 | 02:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 02:00:00 | 02:00:00 | Software | SWEng Group 4 | Working on user searching, getting search to display a list of users and to display the profile when clicked | User story C18 | Nathan Billis | ncab500@york.ac.uk |  | Yes | 04/16/2020 | 12:00:00 PM | 04/16/2020 | 02:00:00 PM | 02:00:00 | 2 | 12.5 | 25
| Joe Butler | 00:00:00 | 03:00:00 | 00:30:14 | 00:00:00 | 03:00:00 | 00:00:00 | 01:00:00 | 07:30:14 | 07:30:14 | Administration | SWEng Group 4 | pricing for algolia |  | Nathan Billis | ncab500@york.ac.uk |  | Yes | 04/16/2020 | 02:00:00 PM | 04/16/2020 | 02:15:00 PM | 00:15:00 | 0.25 | 12.5 | 3.13
| James Clawley | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 02:00:00 | 04:00:00 | 06:00:00 | 06:00:00 | Software | SWEng Group 4 | Added portion control. Includes basically everything including tests, with the exception of UI. | User story C34 | Joe Butler | jb2200@york.ac.uk |  | Yes | 04/17/2020 | 11:00:00 PM | 04/18/2020 | 02:00:00 AM | 03:00:00 | 3 | 12.5 | 37.5
Testing - SWEng Group 4 |  | 00:00:00 | 00:00:00 | 00:30:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:30:00 | 00:30:00 | Marketing | SWEng Group 4 | finishing write up of marketing |  | Rebecca Anderson | rea524@york.ac.uk |  | Yes | 04/18/2020 | 09:00:00 AM | 04/18/2020 | 10:00:00 AM | 01:00:00 | 1 | 12.5 | 12.5
| Nathan Billis | 00:00:00 | 00:00:00 | 00:30:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:30:00 | 00:30:00 | Software | SWEng Group 4 | Building up making recipes | User story A12 | James Clawley | jc2421@york.ac.uk |  | Yes | 04/18/2020 | 09:00:00 AM | 04/18/2020 | 11:00:00 AM | 02:00:00 | 2 | 12.5 | 25
Marketing - SWEng Group 4 |  | 00:00:00 | 03:00:00 | 00:00:00 | 01:45:00 | 00:00:00 | 01:00:00 | 00:00:00 | 05:45:00 | 05:45:00 | Administration | SWEng Group 4 | Updated change log, organized meeting times with Noel and sorted out signing and commenting of time sheet |  | James Pearson | jp1439@york.ac.uk |  | Yes | 04/18/2020 | 09:00:00 AM | 04/18/2020 | 09:30:00 AM | 00:30:00 | 0.5 | 12.5 | 6.25
| Rebecca Anderson | 00:00:00 | 03:00:00 | 00:00:00 | 01:45:00 | 00:00:00 | 01:00:00 | 00:00:00 | 05:45:00 | 05:45:00 | Software | SWEng Group 4 | Merging updated social feed and fixing errors on my side of the code afterwards. Started implementing adding reviews to firestore | User story C11 | James Pearson | jp1439@york.ac.uk |  | Yes | 04/18/2020 | 01:00:00 PM | 04/18/2020 | 04:00:00 PM | 03:00:00 | 3 | 12.5 | 37.5
Administration - SWEng Group 4 |  | 00:15:00 | 00:00:00 | 00:00:00 | 00:15:00 | 00:00:00 | 00:30:00 | 00:15:00 | 01:15:00 | 01:15:00 | Software | SWEng Group 4 | Tried to create UI for adjusting recipe portions. Fell a bit short. Will query James P about it. | User story C34 | Joe Butler | jb2200@york.ac.uk |  | Yes | 04/19/2020 | 12:00:00 AM | 04/19/2020 | 01:00:00 AM | 01:00:00 | 1 | 12.5 | 12.5
| James Pearson | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:30:00 | 00:15:00 | 00:45:00 | 00:45:00 | Software | SWEng Group 4 | Feed fully functional, posts send and are then updated | User story C16 | Louis Newman | lifn501@york.ac.uk |  | Yes | 04/19/2020 | 09:00:00 AM | 04/19/2020 | 12:00:00 PM | 03:00:00 | 3 | 12.5 | 37.5
| Rebecca Anderson | 00:15:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:15:00 | 00:15:00 | Software | SWEng Group 4 | Redesigning the user story as the way I was implementing it wasn't going to work for multiple recipes | User story C5 | Rebecca Anderson | rea524@york.ac.uk |  | Yes | 04/19/2020 | 09:00:00 AM | 04/19/2020 | 10:30:00 AM | 01:30:00 | 1.5 | 12.5 | 18.75
| Nathan Billis | 00:00:00 | 00:00:00 | 00:00:00 | 00:15:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:15:00 | 00:15:00 | Software | SWEng Group 4 | Building up making recipes | User story A12 | James Clawley | jc2421@york.ac.uk |  | Yes | 04/19/2020 | 09:00:00 AM | 04/19/2020 | 01:00:00 PM | 04:00:00 | 4 | 12.5 | 50
Design - SWEng Group 4 |  | 00:00:00 | 01:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 01:00:00 | 01:00:00 | Software | SWEng Group 4 | Added ability to add review data to firestore. Started adding functionality of posting to app | User story C11 | James Pearson | jp1439@york.ac.uk |  | Yes | 04/19/2020 | 10:00:00 AM | 04/19/2020 | 12:00:00 PM | 02:00:00 | 2 | 12.5 | 25
| Joe Butler | 00:00:00 | 01:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 01:00:00 | 01:00:00 | Software | SWEng Group 4 | Time line on user profile and post page | User story C16 | Louis Newman | lifn501@york.ac.uk |  | Yes | 04/19/2020 | 12:00:00 PM | 04/19/2020 | 07:00:00 PM | 07:00:00 | 7 | 12.5 | 87.5
TOTAL |  | 03:45:00 | 07:00:00 | 01:15:14 | 04:00:00 | 03:00:00 | 06:30:00 | 18:45:00 | 44:15:14 | 44:15:14 | Administration | SWEng Group 4 | Sorted out meeting agenda and minutes |  | James Pearson | jp1439@york.ac.uk |  | Yes | 04/19/2020 | 12:00:00 PM | 04/19/2020 | 12:15:00 PM | 00:15:00 | 0.25 | 12.5 | 3.13
[9 empty] | Total: | 44.25

## Week 30 Labour
Project | User | 04/20/2020 | 04/21/2020 | 04/22/2020 | 04/23/2020 | 04/24/2020 | 04/25/2020 | 04/26/2020 | Total | Billable total | Project | Client | Description | Task | User | Email | Tags | Billable | Start Date | Start Time | End Date | End Time | Duration (h) | Duration (decimal) | Billable Rate (GBP) | Billable Amount (GBP)
Finance - SWEng Group 4 |  | 00:00:00 | 00:00:00 | 00:15:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:15:00 | 00:15:00 | Software | SWEng Group 4 | Got recipes and images sort of working, images need to be made square and need to be tidied, but provision is present | User story C16 | Louis Newman | lifn501@york.ac.uk |  | Yes | 04/26/2020 | 10:00:00 AM | 04/26/2020 | 01:00:00 PM | 03:00:00 | 3 | 12.5 | 37.5
| Louis Newman | 00:00:00 | 00:00:00 | 00:15:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:15:00 | 00:15:00 | Software | SWEng Group 4 | Posting reviews to app | User story C11 | James Pearson | jp1439@york.ac.uk |  | Yes | 04/25/2020 | 01:00:00 PM | 04/25/2020 | 03:30:00 PM | 02:30:00 | 2.5 | 12.5 | 31.25
Meetings - SWEng Group 4 |  | 03:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 03:00:00 | 03:00:00 | Software | SWEng Group 4 | corking on the initial set up info pages |  | Rebecca Anderson | rea524@york.ac.uk |  | Yes | 04/25/2020 | 09:00:00 AM | 04/25/2020 | 10:00:00 AM | 01:00:00 | 1 | 12.5 | 12.5
| James Pearson | 00:30:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:30:00 | 00:30:00 | Software | SWEng Group 4 | Setting up back end properly and starting to properly implement reviews | User story C11 | James Pearson | jp1439@york.ac.uk |  | Yes | 04/24/2020 | 01:00:00 PM | 04/24/2020 | 03:00:00 PM | 02:00:00 | 2 | 12.5 | 25
| Louis Newman | 00:30:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:30:00 | 00:30:00 | HTML Tour | SWEng Group 4 | Start work on the HTML tour |  | Nathan Billis | ncab500@york.ac.uk |  | Yes | 04/24/2020 | 12:00:00 PM | 04/24/2020 | 12:30:00 PM | 00:30:00 | 0.5 | 12.5 | 6.25
| Rebecca Anderson | 00:30:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:30:00 | 00:30:00 | Software | SWEng Group 4 | Redesigning the way the shopping list works. Gone over time as it has taken me a while to get my head round the way it works. Also had to change a few things around and test multiple ways of writing it | User story C5 | Rebecca Anderson | rea524@york.ac.uk |  | Yes | 04/24/2020 | 09:00:00 AM | 04/24/2020 | 12:00:00 PM | 03:00:00 | 3 | 12.5 | 37.5
| Nathan Billis | 00:30:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:30:00 | 00:30:00 | Testing | SWEng Group 4 | Testing untested stories (B1-4) | B1 | Nathan Billis | ncab500@york.ac.uk |  | Yes | 04/23/2020 | 12:30:00 PM | 04/23/2020 | 01:00:00 PM | 00:30:00 | 0.5 | 12.5 | 6.25
| Joe Butler | 00:30:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:30:00 | 00:30:00 | Software | SWEng Group 4 | Comments full rework with picture, timestamp and likes | User story C16 | Louis Newman | lifn501@york.ac.uk |  | Yes | 04/23/2020 | 12:00:00 PM | 04/23/2020 | 03:00:00 PM | 03:00:00 | 3 | 12.5 | 37.5
| James Clawley | 00:30:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:30:00 | 00:30:00 | Software | SWEng Group 4 |  | User story A12 | James Clawley | jc2421@york.ac.uk |  | Yes | 04/23/2020 | 09:00:00 AM | 04/23/2020 | 11:00:00 AM | 02:00:00 | 2 | 12.5 | 25
Software - SWEng Group 4 |  | 02:00:00 | 02:00:00 | 02:00:00 | 05:00:00 | 05:00:00 | 03:30:00 | 03:00:00 | 22:30:00 | 22:30:00 | Finance | SWEng Group 4 | Weekly finances |  | Louis Newman | lifn501@york.ac.uk |  | Yes | 04/22/2020 | 12:00:00 PM | 04/22/2020 | 12:15:00 PM | 00:15:00 | 0.25 | 12.5 | 3.13
| James Pearson | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 02:00:00 | 02:30:00 | 00:00:00 | 04:30:00 | 04:30:00 | Software | SWEng Group 4 |  | User story A12 | James Clawley | jc2421@york.ac.uk |  | Yes | 04/22/2020 | 09:00:00 AM | 04/22/2020 | 11:00:00 AM | 02:00:00 | 2 | 12.5 | 25
| Louis Newman | 00:00:00 | 00:00:00 | 00:00:00 | 03:00:00 | 00:00:00 | 00:00:00 | 03:00:00 | 06:00:00 | 06:00:00 | Software | SWEng Group 4 | Solve the problems about C17. | User story C17 | Jun Ma | jm2285@york.ac.uk |  | Yes | 04/21/2020 | 06:30:00 PM | 04/21/2020 | 08:30:00 PM | 02:00:00 | 2 | 12.5 | 25
| Rebecca Anderson | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 03:00:00 | 01:00:00 | 00:00:00 | 04:00:00 | 04:00:00 | Testing | SWEng Group 4 | code review for bug fix |  | Nathan Billis | ncab500@york.ac.uk |  | Yes | 04/20/2020 | 04:15:00 PM | 04/20/2020 | 04:30:00 PM | 00:15:00 | 0.25 | 12.5 | 3.13
| Jun Ma | 00:00:00 | 02:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 02:00:00 | 02:00:00 | Meetings | SWEng Group 4 | Team meeting |  | Louis Newman | lifn501@york.ac.uk |  | Yes | 04/20/2020 | 10:00:00 AM | 04/20/2020 | 10:30:00 AM | 00:30:00 | 0.5 | 12.5 | 6.25
| James Clawley | 02:00:00 | 00:00:00 | 02:00:00 | 02:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 06:00:00 | 06:00:00 | Meetings | SWEng Group 4 | Weekly Meeting |  | Nathan Billis | ncab500@york.ac.uk |  | Yes | 04/20/2020 | 10:00:00 AM | 04/20/2020 | 10:30:00 AM | 00:30:00 | 0.5 | 12.5 | 6.25
Testing - SWEng Group 4 |  | 00:15:00 | 00:00:00 | 00:00:00 | 00:30:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:45:00 | 00:45:00 | Meetings | SWEng Group 4 | Meeting |  | Joe Butler | jb2200@york.ac.uk |  | Yes | 04/20/2020 | 10:00:00 AM | 04/20/2020 | 10:30:00 AM | 00:30:00 | 0.5 | 12.5 | 6.25
| Nathan Billis | 00:15:00 | 00:00:00 | 00:00:00 | 00:30:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:45:00 | 00:45:00 | Meetings | SWEng Group 4 | General team meeting |  | James Pearson | jp1439@york.ac.uk |  | Yes | 04/20/2020 | 10:00:00 AM | 04/20/2020 | 10:30:00 AM | 00:30:00 | 0.5 | 12.5 | 6.25
Administration - SWEng Group 4 |  | 00:30:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:30:00 | 00:30:00 | Administration | SWEng Group 4 | writing up minutes |  | Rebecca Anderson | rea524@york.ac.uk |  | Yes | 04/20/2020 | 09:30:00 AM | 04/20/2020 | 10:00:00 AM | 00:30:00 | 0.5 | 12.5 | 6.25
| Rebecca Anderson | 00:30:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:30:00 | 00:30:00 | Software | SWEng Group 4 |  | User story A12 | James Clawley | jc2421@york.ac.uk |  | Yes | 04/20/2020 | 09:30:00 AM | 04/20/2020 | 11:30:00 AM | 02:00:00 | 2 | 12.5 | 25
HTML Tour - SWEng Group 4 |  | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:30:00 | 00:00:00 | 00:00:00 | 00:30:00 | 00:30:00 | Meetings | SWEng Group 4 | group meeting |  | Rebecca Anderson | rea524@york.ac.uk |  | Yes | 04/20/2020 | 09:00:00 AM | 04/20/2020 | 09:30:00 AM | 00:30:00 | 0.5 | 12.5 | 6.25
| Nathan Billis | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:30:00 | 00:00:00 | 00:00:00 | 00:30:00 | 00:30:00 | Meetings | SWEng Group 4 |  |  | James Clawley | jc2421@york.ac.uk |  | Yes | 04/20/2020 | 09:00:00 AM | 04/20/2020 | 09:30:00 AM | 00:30:00 | 0.5 | 12.5 | 6.25
TOTAL |  | 05:45:00 | 02:00:00 | 02:15:00 | 05:30:00 | 05:30:00 | 03:30:00 | 03:00:00 | 27:30:00 | 27:30:00
[9 empty] | total | 27.5

## Week 31 Labour
Project | User | 04/27/2020 | 04/28/2020 | 04/29/2020 | 04/30/2020 | 05/01/2020 | 05/02/2020 | 05/03/2020 | Total | Total billable | Project | Client | Description | Task | User | Email | Tags | Billable | Start Date | Start Time | End Date | End Time | Duration (h) | Duration (decimal) | Billable Rate (GBP) | Billable Amount (GBP)
Finance - SWEng Group 4 |  | 00:00:00 | 00:00:00 | 02:45:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 02:45:00 | 02:45:00 | Administration | SWEng Group 4 | Setting up agenda and minutes |  | James Pearson | jp1439@york.ac.uk |  | Yes | 05/03/2020 | 10:00:00 AM | 05/03/2020 | 10:15:00 AM | 00:15:00 | 0.25 | 12.5 | 3.13
| Louis Newman | 00:00:00 | 00:00:00 | 02:45:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 02:45:00 | 02:45:00 | Software | SWEng Group 4 | Added ability to delete posts and comments from all pages, still small bugs but this will allow all tests to pass once complete | User story C29 | Louis Newman | lifn501@york.ac.uk |  | Yes | 05/02/2020 | 09:00:00 AM | 05/02/2020 | 02:00:00 PM | 05:00:00 | 5 | 12.5 | 62.5
Meetings - SWEng Group 4 |  | 03:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 03:00:00 | 03:00:00 | Software | SWEng Group 4 | Fixed portions UI, added portions tests, added ingredient icon support (kinda by accident) and completely re formatted ingredients list. | User story C34 | Joe Butler | jb2200@york.ac.uk |  | Yes | 05/01/2020 | 10:00:00 PM | 05/01/2020 | 11:30:00 PM | 01:30:00 | 1.5 | 12.5 | 18.75
| James Pearson | 00:30:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:30:00 | 00:30:00 | Software | SWEng Group 4 | Looking into notifications & shopping apis |  | Joe Butler | jb2200@york.ac.uk |  | Yes | 05/01/2020 | 12:00:00 PM | 05/01/2020 | 01:00:00 PM | 01:00:00 | 1 | 12.5 | 12.5
| Louis Newman | 00:30:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:30:00 | 00:30:00 | Software | SWEng Group 4 | Helping Jun simplify the Timer tests | User story C17 | Joe Butler | jb2200@york.ac.uk |  | Yes | 05/01/2020 | 11:00:00 AM | 05/01/2020 | 11:30:00 AM | 00:30:00 | 0.5 | 12.5 | 6.25
| Rebecca Anderson | 00:30:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:30:00 | 00:30:00 | Testing | SWEng Group 4 | review C17 - tests failing | C17 | Nathan Billis | ncab500@york.ac.uk |  | Yes | 04/30/2020 | 06:00:00 PM | 04/30/2020 | 06:15:00 PM | 00:15:00 | 0.25 | 12.5 | 3.13
| Nathan Billis | 00:30:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:30:00 | 00:30:00 | Testing | SWEng Group 4 | update documentation and fix remaining tests |  | Nathan Billis | ncab500@york.ac.uk |  | Yes | 04/30/2020 | 05:00:00 PM | 04/30/2020 | 06:00:00 PM | 01:00:00 | 1 | 12.5 | 12.5
| Jun Ma | 00:30:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:30:00 | 00:30:00 | Software | SWEng Group 4 | Pair programming with Becky and Fixing ArrayList issue by replacing with a HashMap implementation. |  | Joe Butler | jb2200@york.ac.uk |  | Yes | 04/30/2020 | 02:00:00 PM | 04/30/2020 | 03:30:00 PM | 01:30:00 | 1.5 | 12.5 | 18.75
| James Clawley | 00:30:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:30:00 | 00:30:00 | Design | SWEng Group 4 | Changed the layout of the recipe info screen and changed image buttons at the top of the screen |  | James Pearson | jp1439@york.ac.uk |  | Yes | 04/30/2020 | 01:00:00 PM | 04/30/2020 | 03:30:00 PM | 02:30:00 | 2.5 | 12.5 | 31.25
Software - SWEng Group 4 |  | 01:30:00 | 06:00:00 | 00:00:00 | 01:30:00 | 03:00:00 | 05:00:00 | 00:00:00 | 17:00:00 | 17:00:00 | Testing | SWEng Group 4 | Create Testing Report |  | Nathan Billis | ncab500@york.ac.uk |  | Yes | 04/29/2020 | 05:00:00 PM | 04/29/2020 | 05:30:00 PM | 00:30:00 | 0.5 | 12.5 | 6.25
| James Pearson | 00:00:00 | 03:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 03:00:00 | 03:00:00 | Testing | SWEng Group 4 | Fix remaining tests |  | Nathan Billis | ncab500@york.ac.uk |  | Yes | 04/29/2020 | 04:00:00 PM | 04/29/2020 | 05:00:00 PM | 01:00:00 | 1 | 12.5 | 12.5
| Louis Newman | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 05:00:00 | 00:00:00 | 05:00:00 | 05:00:00 | Finance | SWEng Group 4 | Financial report 3 - complete and sent |  | Louis Newman | lifn501@york.ac.uk |  | Yes | 04/29/2020 | 09:00:00 AM | 04/29/2020 | 11:45:00 AM | 02:45:00 | 2.75 | 12.5 | 34.38
| Rebecca Anderson | 00:00:00 | 03:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 03:00:00 | 03:00:00 | Software | SWEng Group 4 | Fixed review recycler adapter with Louis and implemented likes | User story C11 | James Pearson | jp1439@york.ac.uk |  | Yes | 04/28/2020 | 01:00:00 PM | 04/28/2020 | 04:00:00 PM | 03:00:00 | 3 | 12.5 | 37.5
| Joe Butler | 01:30:00 | 00:00:00 | 00:00:00 | 01:30:00 | 03:00:00 | 00:00:00 | 00:00:00 | 06:00:00 | 06:00:00 | Software | SWEng Group 4 | rewriting hash map for ingredients and displaying. tried lots of ways of deleting and that took a while and longer then expected | User story C5 | Rebecca Anderson | rea524@york.ac.uk |  | Yes | 04/28/2020 | 09:00:00 AM | 04/28/2020 | 12:00:00 PM | 03:00:00 | 3 | 12.5 | 37.5
Testing - SWEng Group 4 |  | 02:00:00 | 00:00:00 | 01:30:00 | 01:15:00 | 00:00:00 | 00:00:00 | 00:00:00 | 04:45:00 | 04:45:00 | Testing | SWEng Group 4 | Working on Planner fragment tests ( and searching) | C4 | Nathan Billis | ncab500@york.ac.uk |  | Yes | 04/27/2020 | 01:30:00 PM | 04/27/2020 | 02:00:00 PM | 00:30:00 | 0.5 | 12.5 | 6.25
| Nathan Billis | 02:00:00 | 00:00:00 | 01:30:00 | 01:15:00 | 00:00:00 | 00:00:00 | 00:00:00 | 04:45:00 | 04:45:00 | Administration | SWEng Group 4 | Updated gantt charts and sent to business mentor |  | James Pearson | jp1439@york.ac.uk |  | Yes | 04/27/2020 | 01:00:00 PM | 04/27/2020 | 01:15:00 PM | 00:15:00 | 0.25 | 12.5 | 3.13
Administration - SWEng Group 4 |  | 00:45:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:15:00 | 01:00:00 | 01:00:00 | Testing | SWEng Group 4 | Update searching test (hometest.java) | C18 | Nathan Billis | ncab500@york.ac.uk |  | Yes | 04/27/2020 | 12:30:00 PM | 04/27/2020 | 01:00:00 PM | 00:30:00 | 0.5 | 12.5 | 6.25
| James Pearson | 00:15:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:15:00 | 00:30:00 | 00:30:00 | Testing | SWEng Group 4 | Re-runnning all tests |  | Nathan Billis | ncab500@york.ac.uk |  | Yes | 04/27/2020 | 12:00:00 PM | 04/27/2020 | 12:30:00 PM | 00:30:00 | 0.5 | 12.5 | 6.25
| Rebecca Anderson | 00:30:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:30:00 | 00:30:00 | Testing | SWEng Group 4 | Testing C34 & audio tests | C34 | Nathan Billis | ncab500@york.ac.uk |  | Yes | 04/27/2020 | 10:45:00 AM | 04/27/2020 | 11:15:00 AM | 00:30:00 | 0.5 | 12.5 | 6.25
Design - SWEng Group 4 |  | 00:00:00 | 00:00:00 | 00:00:00 | 02:30:00 | 00:00:00 | 00:00:00 | 00:00:00 | 02:30:00 | 02:30:00 | Meetings | SWEng Group 4 | Weekly meeting |  | Nathan Billis | ncab500@york.ac.uk |  | Yes | 04/27/2020 | 10:00:00 AM | 04/27/2020 | 10:30:00 AM | 00:30:00 | 0.5 | 12.5 | 6.25
| James Pearson | 00:00:00 | 00:00:00 | 00:00:00 | 02:30:00 | 00:00:00 | 00:00:00 | 00:00:00 | 02:30:00 | 02:30:00 | Meetings | SWEng Group 4 | Weekly meeting |  | Jun Ma | jm2285@york.ac.uk |  | Yes | 04/27/2020 | 10:00:00 AM | 04/27/2020 | 10:30:00 AM | 00:30:00 | 0.5 | 12.5 | 6.25
HTML Tour - SWEng Group 4 |  | 01:15:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 01:15:00 | 01:15:00 | Meetings | SWEng Group 4 | General team meeting |  | James Pearson | jp1439@york.ac.uk |  | Yes | 04/27/2020 | 10:00:00 AM | 04/27/2020 | 10:30:00 AM | 00:30:00 | 0.5 | 12.5 | 6.25
| Joe Butler | 01:15:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 01:15:00 | 01:15:00 | Administration | SWEng Group 4 | Notes |  | Rebecca Anderson | rea524@york.ac.uk |  | Yes | 04/27/2020 | 09:30:00 AM | 04/27/2020 | 10:00:00 AM | 00:30:00 | 0.5 | 12.5 | 6.25
TOTAL |  | 08:30:00 | 06:00:00 | 04:15:00 | 05:15:00 | 03:00:00 | 05:00:00 | 00:15:00 | 32:15:00 | 32:15:00 | Meetings | SWEng Group 4 | Team meeting |  | Louis Newman | lifn501@york.ac.uk |  | Yes | 04/27/2020 | 09:00:00 AM | 04/27/2020 | 09:30:00 AM | 00:30:00 | 0.5 | 12.5 | 6.25
[11 empty] | Meetings | SWEng Group 4 | Team meeting |  | Rebecca Anderson | rea524@york.ac.uk |  | Yes | 04/27/2020 | 09:00:00 AM | 04/27/2020 | 09:30:00 AM | 00:30:00 | 0.5 | 12.5 | 6.25
[9 empty] | Total | 32.25 | Meetings | SWEng Group 4 | Team meeting |  | James Clawley | jc2421@york.ac.uk |  | Yes | 04/27/2020 | 09:00:00 AM | 04/27/2020 | 09:30:00 AM | 00:30:00 | 0.5 | 12.5 | 6.25
[11 empty] | HTML Tour | SWEng Group 4 | Updated the scranplan html tour website. Moved roles to a new page and implemented a documentation page. |  | Joe Butler | jb2200@york.ac.uk |  | Yes | 04/27/2020 | 03:00:00 AM | 04/27/2020 | 04:15:00 AM | 01:15:00 | 1.25 | 12.5 | 15.63
[11 empty] | Software | SWEng Group 4 | Added Timer UI tests and helper methods for finding recipes in tests. |  | Joe Butler | jb2200@york.ac.uk |  | Yes | 04/27/2020 | 01:00:00 AM | 04/27/2020 | 02:30:00 AM | 01:30:00 | 1.5 | 12.5 | 18.75

## Week 32 Labour
Project | User | 05/04/2020 | 05/05/2020 | 05/06/2020 | 05/07/2020 | 05/08/2020 | 05/09/2020 | 05/10/2020 | Total | Billable total | Project | Client | Description | Task | User | Email | Tags | Billable | Start Date | Start Time | End Date | End Time | Duration (h) | Duration (decimal) | Billable Rate (GBP) | Billable Amount (GBP)
Finance - SWEng Group 4 |  | 00:00:00 | 00:00:00 | 00:15:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:15:00 | 00:15:00 | Software | SWEng Group 4 | Worked on adMob intergration | User story C19 | Nathan Billis | ncab500@york.ac.uk |  | Yes | 05/09/2020 | 04:00:00 PM | 05/09/2020 | 05:30:00 PM | 01:30:00 | 1.5 | 12.5 | 18.75
| Louis Newman | 00:00:00 | 00:00:00 | 00:15:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:15:00 | 00:15:00 | Software | SWEng Group 4 | Recalculation of overall rating | User story C11 | James Pearson | jp1439@york.ac.uk |  | Yes | 05/08/2020 | 01:00:00 PM | 05/08/2020 | 04:00:00 PM | 03:00:00 | 3 | 12.5 | 37.5
Meetings - SWEng Group 4 |  | 03:30:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 03:30:00 | 03:30:00 | Software | SWEng Group 4 | Merged main into social and worked on getting tests to pass | User story C31 | Louis Newman | lifn501@york.ac.uk |  | Yes | 05/08/2020 | 11:00:00 AM | 05/08/2020 | 02:00:00 PM | 03:00:00 | 3 | 12.5 | 37.5
| James Pearson | 00:30:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:30:00 | 00:30:00 | Software | SWEng Group 4 |  | User story A12 | James Clawley | jc2421@york.ac.uk |  | Yes | 05/08/2020 | 09:00:00 AM | 05/08/2020 | 11:00:00 AM | 02:00:00 | 2 | 12.5 | 25
| Louis Newman | 00:30:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:30:00 | 00:30:00 | Software | SWEng Group 4 | pulled from master to update branch. Had issues |  | James Pearson | jp1439@york.ac.uk |  | Yes | 05/07/2020 | 10:00:00 AM | 05/07/2020 | 12:00:00 PM | 02:00:00 | 2 | 12.5 | 25
| Rebecca Anderson | 00:30:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:30:00 | 00:30:00 | Software | SWEng Group 4 |  | User story A12 | James Clawley | jc2421@york.ac.uk |  | Yes | 05/07/2020 | 09:00:00 AM | 05/07/2020 | 12:00:00 PM | 03:00:00 | 3 | 12.5 | 37.5
| Nathan Billis | 00:30:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:30:00 | 00:30:00 | Finance | SWEng Group 4 | Weekly finances |  | Louis Newman | lifn501@york.ac.uk |  | Yes | 05/06/2020 | 10:45:00 AM | 05/06/2020 | 11:00:00 AM | 00:15:00 | 0.25 | 12.5 | 3.13
| Jun Ma | 00:30:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:30:00 | 00:30:00 | Software | SWEng Group 4 |  | User story A12 | James Clawley | jc2421@york.ac.uk |  | Yes | 05/05/2020 | 09:00:00 AM | 05/05/2020 | 11:00:00 AM | 02:00:00 | 2 | 12.5 | 25
| Joe Butler | 00:30:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:30:00 | 00:30:00 | HTML Tour | SWEng Group 4 | Created an about page, updated developer images and added additional documents such as the XML schema |  | Joe Butler | jb2200@york.ac.uk |  | Yes | 05/04/2020 | 10:00:00 PM | 05/04/2020 | 11:30:00 PM | 01:30:00 | 1.5 | 12.5 | 18.75
| James Clawley | 00:30:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:30:00 | 00:30:00 | Design | SWEng Group 4 | UI design questionare |  | Joe Butler | jb2200@york.ac.uk |  | Yes | 05/04/2020 | 07:00:00 PM | 05/04/2020 | 08:30:00 PM | 01:30:00 | 1.5 | 12.5 | 18.75
Software - SWEng Group 4 |  | 00:00:00 | 02:00:00 | 00:00:00 | 05:00:00 | 08:00:00 | 01:30:00 | 00:00:00 | 16:30:00 | 16:30:00 | Meetings | SWEng Group 4 | Team meeting |  | Louis Newman | lifn501@york.ac.uk |  | Yes | 05/04/2020 | 10:00:00 AM | 05/04/2020 | 10:30:00 AM | 00:30:00 | 0.5 | 12.5 | 6.25
| James Pearson | 00:00:00 | 00:00:00 | 00:00:00 | 02:00:00 | 03:00:00 | 00:00:00 | 00:00:00 | 05:00:00 | 05:00:00 | Meetings | SWEng Group 4 | Weekly Meeting |  | Nathan Billis | ncab500@york.ac.uk |  | Yes | 05/04/2020 | 10:00:00 AM | 05/04/2020 | 10:30:00 AM | 00:30:00 | 0.5 | 12.5 | 6.25
| Louis Newman | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 03:00:00 | 00:00:00 | 00:00:00 | 03:00:00 | 03:00:00 | Meetings | SWEng Group 4 | Meeting |  | Joe Butler | jb2200@york.ac.uk |  | Yes | 05/04/2020 | 10:00:00 AM | 05/04/2020 | 10:30:00 AM | 00:30:00 | 0.5 | 12.5 | 6.25
| Nathan Billis | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 01:30:00 | 00:00:00 | 01:30:00 | 01:30:00 | Meetings | SWEng Group 4 | Weekly meeting |  | Jun Ma | jm2285@york.ac.uk |  | Yes | 05/04/2020 | 10:00:00 AM | 05/04/2020 | 10:30:00 AM | 00:30:00 | 0.5 | 12.5 | 6.25
| James Clawley | 00:00:00 | 02:00:00 | 00:00:00 | 03:00:00 | 02:00:00 | 00:00:00 | 00:00:00 | 07:00:00 | 07:00:00 | Meetings | SWEng Group 4 |  |  | Rebecca Anderson | rea524@york.ac.uk |  | Yes | 05/04/2020 | 09:00:00 AM | 05/04/2020 | 09:30:00 AM | 00:30:00 | 0.5 | 12.5 | 6.25
Design - SWEng Group 4 |  | 01:30:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 01:30:00 | 01:30:00 | Meetings | SWEng Group 4 |  |  | James Clawley | jc2421@york.ac.uk |  | Yes | 05/04/2020 | 09:00:00 AM | 05/04/2020 | 09:30:00 AM | 00:30:00 | 0.5 | 12.5 | 6.25
| Joe Butler | 01:30:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 01:30:00 | 01:30:00 | Meetings | SWEng Group 4 | General meeting |  | James Pearson | jp1439@york.ac.uk |  | Yes | 05/04/2020 | 09:00:00 AM | 05/04/2020 | 09:30:00 AM | 00:30:00 | 0.5 | 12.5 | 6.25
HTML Tour - SWEng Group 4 |  | 01:30:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 01:30:00 | 01:30:00
| Joe Butler | 01:30:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 01:30:00 | 01:30:00
TOTAL |  | 06:30:00 | 02:00:00 | 00:15:00 | 05:00:00 | 08:00:00 | 01:30:00 | 00:00:00 | 23:15:00 | 23:15:00
[9 empty] | total | 23.25

## Week 33 Labour
Project | User | 05/11/2020 | 05/12/2020 | 05/13/2020 | 05/14/2020 | 05/15/2020 | 05/16/2020 | 05/17/2020 | Total | total billable | Project | Client | Description | Task | User | Email | Tags | Billable | Start Date | Start Time | End Date | End Time | Duration (h) | Duration (decimal) | Billable Rate (GBP) | Billable Amount (GBP)
Finance - SWEng Group 4 |  | 00:00:00 | 00:00:00 | 00:15:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:15:00 | 00:15:00 | Administration | SWEng Group 4 | Setting up agenda and minutes |  | James Pearson | jp1439@york.ac.uk |  | Yes | 05/17/2020 | 07:00:00 PM | 05/17/2020 | 07:15:00 PM | 00:15:00 | 0.25 | 12.5 | 3.13
| Louis Newman | 00:00:00 | 00:00:00 | 00:15:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:15:00 | 00:15:00 | Software | SWEng Group 4 | Getting expresso tests to pass and commenting code ready for peer review | User story C27 | Louis Newman | lifn501@york.ac.uk |  | Yes | 05/17/2020 | 10:00:00 AM | 05/17/2020 | 01:00:00 PM | 03:00:00 | 3 | 12.5 | 37.5
Meetings - SWEng Group 4 |  | 01:45:00 | 03:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 04:45:00 | 04:45:00 | Software | SWEng Group 4 | Simplify the code in meal planner and move it based on RecipeFragment | User story C17 | Jun Ma | jm2285@york.ac.uk |  | Yes | 05/16/2020 | 06:00:00 PM | 05/16/2020 | 07:30:00 PM | 01:30:00 | 1.5 | 12.5 | 18.75
| James Pearson | 00:00:00 | 00:45:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:45:00 | 00:45:00 | Software | SWEng Group 4 | Fixing reviews, adding pictures and fixing bugs that were linked to my code the existing posts system. | User story C11 | James Pearson | jp1439@york.ac.uk |  | Yes | 05/16/2020 | 01:00:00 PM | 05/16/2020 | 05:00:00 PM | 04:00:00 | 4 | 12.5 | 50
| Louis Newman | 00:00:00 | 00:45:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:45:00 | 00:45:00 | Software | SWEng Group 4 | Fixing lots of bugs and worked on getting expresso tests to pass | User story C24 | Louis Newman | lifn501@york.ac.uk |  | Yes | 05/16/2020 | 10:00:00 AM | 05/16/2020 | 04:00:00 PM | 06:00:00 | 6 | 12.5 | 75
| Rebecca Anderson | 00:00:00 | 00:45:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:45:00 | 00:45:00 | Software | SWEng Group 4 | worked on saving states of list. tried a lot of ways but didn't manage to get any working properly. Will ask at the meeting if anyone has any other idea. all other sections of this users story are done. | User story C5 | Rebecca Anderson | rea524@york.ac.uk |  | Yes | 05/16/2020 | 09:00:00 AM | 05/16/2020 | 11:00:00 AM | 02:00:00 | 2 | 12.5 | 25
| Nathan Billis | 00:00:00 | 00:45:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:45:00 | 00:45:00 | HTML Tour | SWEng Group 4 | Working on my page for the HTML Tour - offline |  | Nathan Billis | ncab500@york.ac.uk |  | Yes | 05/15/2020 | 12:00:00 PM | 05/15/2020 | 12:30:00 PM | 00:30:00 | 0.5 | 12.5 | 6.25
| Jun Ma | 00:30:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:30:00 | 00:30:00 | Software | SWEng Group 4 | Working on messaging C26 - recycler view | User story C26 | Nathan Billis | ncab500@york.ac.uk |  | Yes | 05/15/2020 | 11:00:00 AM | 05/15/2020 | 12:00:00 PM | 01:00:00 | 1 | 12.5 | 12.5
| Joe Butler | 00:45:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:45:00 | 00:45:00 | Software | SWEng Group 4 | Worked on integrating reviews from feed in | User story C23 | Louis Newman | lifn501@york.ac.uk |  | Yes | 05/15/2020 | 10:00:00 AM | 05/15/2020 | 03:00:00 PM | 05:00:00 | 5 | 12.5 | 62.5
| James Clawley | 00:30:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:30:00 | 00:30:00 | Design | SWEng Group 4 | Design and interaction survey results and outreach |  | Joe Butler | jb2200@york.ac.uk |  | Yes | 05/15/2020 | 10:00:00 AM | 05/15/2020 | 11:30:00 AM | 01:30:00 | 1.5 | 12.5 | 18.75
Software - SWEng Group 4 |  | 06:00:00 | 03:00:00 | 00:00:00 | 05:00:00 | 10:30:00 | 13:30:00 | 03:00:00 | 41:00:00 | 41:00:00 | Software | SWEng Group 4 | Implementing kudos on recipe info screen | User story A8 | James Pearson | jp1439@york.ac.uk |  | Yes | 05/15/2020 | 10:00:00 AM | 05/15/2020 | 01:00:00 PM | 03:00:00 | 3 | 12.5 | 37.5
| James Pearson | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 03:00:00 | 04:00:00 | 00:00:00 | 07:00:00 | 07:00:00 | Software | SWEng Group 4 | Set up buttons on the shopping list to make the list be saved after it is edited. Dididnt managed to get this sorted. Thinking of changing it to a list on firebase but need to look into if that is the best option | User story C5 | Rebecca Anderson | rea524@york.ac.uk |  | Yes | 05/15/2020 | 09:00:00 AM | 05/15/2020 | 10:30:00 AM | 01:30:00 | 1.5 | 12.5 | 18.75
| Louis Newman | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 05:00:00 | 06:00:00 | 03:00:00 | 14:00:00 | 14:00:00 | Marketing | SWEng Group 4 | Research on sales presentation and made a list of good articles and websites to reference for when we are planning |  | Rebecca Anderson | rea524@york.ac.uk |  | Yes | 05/14/2020 | 12:00:00 PM | 05/14/2020 | 12:30:00 PM | 00:30:00 | 0.5 | 12.5 | 6.25
| Rebecca Anderson | 00:00:00 | 02:30:00 | 00:00:00 | 03:00:00 | 01:30:00 | 02:00:00 | 00:00:00 | 09:00:00 | 09:00:00 | Testing | SWEng Group 4 | Checking through all the tests and updating documentation | C19 | Nathan Billis | ncab500@york.ac.uk |  | Yes | 05/14/2020 | 10:00:00 AM | 05/14/2020 | 10:15:00 AM | 00:15:00 | 0.25 | 12.5 | 3.13
| Nathan Billis | 03:00:00 | 00:30:00 | 00:00:00 | 00:00:00 | 01:00:00 | 00:00:00 | 00:00:00 | 04:30:00 | 04:30:00 | Software | SWEng Group 4 | got deleting of ingredients working well and updates constantly. had a bug with it repopulating with the last value but fixed that. it took some time to sort bug out so have gone over time | User story C5 | Rebecca Anderson | rea524@york.ac.uk |  | Yes | 05/14/2020 | 09:00:00 AM | 05/14/2020 | 12:00:00 PM | 03:00:00 | 3 | 12.5 | 37.5
| Jun Ma | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 01:30:00 | 00:00:00 | 01:30:00 | 01:30:00 | Software | SWEng Group 4 |  | User story A12 | James Clawley | jc2421@york.ac.uk |  | Yes | 05/14/2020 | 09:00:00 AM | 05/14/2020 | 11:00:00 AM | 02:00:00 | 2 | 12.5 | 25
| James Clawley | 03:00:00 | 00:00:00 | 00:00:00 | 02:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 05:00:00 | 05:00:00 | Finance | SWEng Group 4 | Weekly finances |  | Louis Newman | lifn501@york.ac.uk |  | Yes | 05/13/2020 | 10:00:00 AM | 05/13/2020 | 10:15:00 AM | 00:15:00 | 0.25 | 12.5 | 3.13
Testing - SWEng Group 4 |  | 00:00:00 | 00:00:00 | 00:00:00 | 00:15:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:15:00 | 00:15:00 | Software | SWEng Group 4 | redesigned the shopping list into a recyler view making it easier to control | User story C5 | Rebecca Anderson | rea524@york.ac.uk |  | Yes | 05/12/2020 | 01:15:00 PM | 05/12/2020 | 03:45:00 PM | 02:30:00 | 2.5 | 12.5 | 31.25
| Nathan Billis | 00:00:00 | 00:00:00 | 00:00:00 | 00:15:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:15:00 | 00:15:00 | Software | SWEng Group 4 | Investigating Messaging C26 | User story C26 | Nathan Billis | ncab500@york.ac.uk |  | Yes | 05/12/2020 | 12:00:00 PM | 05/12/2020 | 12:30:00 PM | 00:30:00 | 0.5 | 12.5 | 6.25
Marketing - SWEng Group 4 |  | 00:00:00 | 01:00:00 | 00:00:00 | 00:30:00 | 00:00:00 | 00:00:00 | 00:00:00 | 01:30:00 | 01:30:00 | Marketing | SWEng Group 4 | going through organising what marketing to use for the presentation |  | Rebecca Anderson | rea524@york.ac.uk |  | Yes | 05/12/2020 | 10:15:00 AM | 05/12/2020 | 11:15:00 AM | 01:00:00 | 1 | 12.5 | 12.5
| Rebecca Anderson | 00:00:00 | 01:00:00 | 00:00:00 | 00:30:00 | 00:00:00 | 00:00:00 | 00:00:00 | 01:30:00 | 01:30:00 | Meetings | SWEng Group 4 | Weekly meeting |  | Louis Newman | lifn501@york.ac.uk |  | Yes | 05/12/2020 | 10:00:00 AM | 05/12/2020 | 10:45:00 AM | 00:45:00 | 0.75 | 12.5 | 9.38
Administration - SWEng Group 4 |  | 00:15:00 | 00:30:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:15:00 | 01:00:00 | 01:00:00 | Meetings | SWEng Group 4 | Weekly Meeting |  | Nathan Billis | ncab500@york.ac.uk |  | Yes | 05/12/2020 | 10:00:00 AM | 05/12/2020 | 10:45:00 AM | 00:45:00 | 0.75 | 12.5 | 9.38
| James Pearson | 00:15:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:15:00 | 00:30:00 | 00:30:00 | Meetings | SWEng Group 4 | General team meeting |  | James Pearson | jp1439@york.ac.uk |  | Yes | 05/12/2020 | 10:00:00 AM | 05/12/2020 | 10:45:00 AM | 00:45:00 | 0.75 | 12.5 | 9.38
| Rebecca Anderson | 00:00:00 | 00:30:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:30:00 | 00:30:00 | Meetings | SWEng Group 4 | group meeting |  | Rebecca Anderson | rea524@york.ac.uk |  | Yes | 05/12/2020 | 09:30:00 AM | 05/12/2020 | 10:15:00 AM | 00:45:00 | 0.75 | 12.5 | 9.38
Design - SWEng Group 4 |  | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 01:30:00 | 00:00:00 | 00:00:00 | 01:30:00 | 01:30:00 | Administration | SWEng Group 4 | Minutes of meeting |  | Rebecca Anderson | rea524@york.ac.uk |  | Yes | 05/12/2020 | 09:00:00 AM | 05/12/2020 | 09:30:00 AM | 00:30:00 | 0.5 | 12.5 | 6.25
| Joe Butler | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 01:30:00 | 00:00:00 | 00:00:00 | 01:30:00 | 01:30:00 | Administration | SWEng Group 4 | Setting up agenda and minutes for the meeting |  | James Pearson | jp1439@york.ac.uk |  | Yes | 05/11/2020 | 04:00:00 PM | 05/11/2020 | 04:15:00 PM | 00:15:00 | 0.25 | 12.5 | 3.13
HTML Tour - SWEng Group 4 |  | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:30:00 | 00:00:00 | 00:00:00 | 00:30:00 | 00:30:00 | Meetings | SWEng Group 4 |  |  | James Clawley | jc2421@york.ac.uk |  | Yes | 05/11/2020 | 12:00:00 PM | 05/11/2020 | 12:30:00 PM | 00:30:00 | 0.5 | 12.5 | 6.25
| Nathan Billis | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:30:00 | 00:00:00 | 00:00:00 | 00:30:00 | 00:30:00 | Software | SWEng Group 4 | Finishing adMob intergration for C19 | User story C19 | Nathan Billis | ncab500@york.ac.uk |  | Yes | 05/11/2020 | 11:30:00 AM | 05/11/2020 | 02:30:00 PM | 03:00:00 | 3 | 12.5 | 37.5
TOTAL |  | 08:00:00 | 07:30:00 | 00:15:00 | 05:45:00 | 12:30:00 | 13:30:00 | 03:15:00 | 50:45:00 | 50:45:00 | Meetings | SWEng Group 4 | Meeting |  | Joe Butler | jb2200@york.ac.uk |  | Yes | 05/11/2020 | 10:00:00 AM | 05/11/2020 | 10:45:00 AM | 00:45:00 | 0.75 | 12.5 | 9.38
[11 empty] | Meetings | SWEng Group 4 | Weekly |  | Jun Ma | jm2285@york.ac.uk |  | Yes | 05/11/2020 | 10:00:00 AM | 05/11/2020 | 10:30:00 AM | 00:30:00 | 0.5 | 12.5 | 6.25
[9 empty] | Total: | 50.75 | Software | SWEng Group 4 |  | User story A12 | James Clawley | jc2421@york.ac.uk |  | Yes | 05/11/2020 | 09:00:00 AM | 05/11/2020 | 12:00:00 PM | 03:00:00 | 3 | 12.5 | 37.5

## Week 34 Labour
Project | User | 05/18/2020 | 05/19/2020 | 05/20/2020 | 05/21/2020 | 05/22/2020 | 05/23/2020 | 05/24/2020 | Total | Billable total | Project | Client | Description | Task | User | Email | Tags | Billable | Start Date | Start Time | End Date | End Time | Duration (h) | Duration (decimal) | Billable Rate (GBP) | Billable Amount (GBP)
Finance - SWEng Group 4 |  | 00:15:00 | 03:00:00 | 02:00:00 | 06:00:00 | 03:00:00 | 00:00:00 | 00:00:00 | 14:15:00 | 14:15:00 | Administration | SWEng Group 4 | Setting up agenda and minutes |  | James Pearson | jp1439@york.ac.uk |  | Yes | 05/24/2020 | 07:00:00 PM | 05/24/2020 | 07:15:00 PM | 00:15:00 | 0.25 | 12.5 | 3.13
| Louis Newman | 00:15:00 | 03:00:00 | 02:00:00 | 04:00:00 | 03:00:00 | 00:00:00 | 00:00:00 | 12:15:00 | 12:15:00 | Software | SWEng Group 4 | Working more on the messaging | User story C26 | Nathan Billis | ncab500@york.ac.uk |  | Yes | 05/24/2020 | 10:13:00 AM | 05/24/2020 | 01:13:00 PM | 03:00:00 | 3 | 12.5 | 37.5
| Jun Ma | 00:00:00 | 00:00:00 | 00:00:00 | 02:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 02:00:00 | 02:00:00 | Software | SWEng Group 4 | Follow and unfollow nearly done with private user, need to get around all the privacy with private and public accounts | User story C27 | Louis Newman | lifn501@york.ac.uk |  | Yes | 05/24/2020 | 09:00:00 AM | 05/24/2020 | 06:00:00 PM | 09:00:00 | 9 | 12.5 | 112.5
Meetings - SWEng Group 4 |  | 04:15:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 04:15:00 | 04:15:00 | Software | SWEng Group 4 |  | User story A12 | James Clawley | jc2421@york.ac.uk |  | Yes | 05/24/2020 | 09:00:00 AM | 05/24/2020 | 11:00:00 AM | 02:00:00 | 2 | 12.5 | 25
| James Pearson | 00:30:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:30:00 | 00:30:00 | Software | SWEng Group 4 | Implementing extras like extra alert fragments and getting to the recipe info screen through images on the feed |  | James Pearson | jp1439@york.ac.uk |  | Yes | 05/23/2020 | 02:00:00 PM | 05/23/2020 | 07:00:00 PM | 05:00:00 | 5 | 12.5 | 62.5
| Louis Newman | 00:45:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:45:00 | 00:45:00 | Software | SWEng Group 4 | setting up suggestion box | User story C23 | James Pearson | jp1439@york.ac.uk |  | Yes | 05/23/2020 | 10:00:00 AM | 05/23/2020 | 12:00:00 PM | 02:00:00 | 2 | 12.5 | 25
| Rebecca Anderson | 00:45:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:45:00 | 00:45:00 | Software | SWEng Group 4 | follow and unfollow | User story C27 | Louis Newman | lifn501@york.ac.uk |  | Yes | 05/23/2020 | 09:00:00 AM | 05/23/2020 | 05:00:00 PM | 08:00:00 | 8 | 12.5 | 100
| Jun Ma | 00:45:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:45:00 | 00:45:00 | Software | SWEng Group 4 |  | User story A12 | James Clawley | jc2421@york.ac.uk |  | Yes | 05/23/2020 | 09:00:00 AM | 05/23/2020 | 11:00:00 AM | 02:00:00 | 2 | 12.5 | 25
| Joe Butler | 00:45:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:45:00 | 00:45:00 | Software | SWEng Group 4 | Implementing kudos | User story A8 | James Pearson | jp1439@york.ac.uk |  | Yes | 05/22/2020 | 05:00:00 PM | 05/22/2020 | 06:00:00 PM | 01:00:00 | 1 | 12.5 | 12.5
| James Clawley | 00:45:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:45:00 | 00:45:00 | Software | SWEng Group 4 | Setting up class for reporting of content | User story C23 | James Pearson | jp1439@york.ac.uk |  | Yes | 05/22/2020 | 03:00:00 PM | 05/22/2020 | 05:00:00 PM | 02:00:00 | 2 | 12.5 | 25
Software - SWEng Group 4 |  | 01:00:00 | 03:00:00 | 03:30:00 | 03:00:00 | 11:00:00 | 17:00:00 | 14:00:00 | 52:30:00 | 52:30:00 | Design | SWEng Group 4 | Collating design survey results |  | Joe Butler | jb2200@york.ac.uk |  | Yes | 05/22/2020 | 02:00:00 PM | 05/22/2020 | 04:00:00 PM | 02:00:00 | 2 | 12.5 | 25
| James Pearson | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 08:00:00 | 07:00:00 | 00:00:00 | 15:00:00 | 15:00:00 | Software | SWEng Group 4 | Setting up follower, deletion, and menus in the review recycler | User story C11 | James Pearson | jp1439@york.ac.uk |  | Yes | 05/22/2020 | 10:00:00 AM | 05/22/2020 | 03:00:00 PM | 05:00:00 | 5 | 12.5 | 62.5
| Louis Newman | 01:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 08:00:00 | 09:00:00 | 18:00:00 | 18:00:00 | Finance | SWEng Group 4 | Financial Summary and Future Business plan |  | Louis Newman | lifn501@york.ac.uk |  | Yes | 05/22/2020 | 09:00:00 AM | 05/22/2020 | 12:00:00 PM | 03:00:00 | 3 | 12.5 | 37.5
| Rebecca Anderson | 00:00:00 | 00:00:00 | 02:00:00 | 00:00:00 | 01:00:00 | 00:00:00 | 00:00:00 | 03:00:00 | 03:00:00 | Software | SWEng Group 4 | Carrying on, worked with Joe to try eliminate the problem but didn't manage to solve it | User story C20 | Rebecca Anderson | rea524@york.ac.uk |  | Yes | 05/22/2020 | 09:00:00 AM | 05/22/2020 | 10:00:00 AM | 01:00:00 | 1 | 12.5 | 12.5
| Nathan Billis | 00:00:00 | 00:00:00 | 00:00:00 | 03:00:00 | 00:00:00 | 00:00:00 | 03:00:00 | 06:00:00 | 06:00:00 | Software | SWEng Group 4 |  | User story A12 | James Clawley | jc2421@york.ac.uk |  | Yes | 05/22/2020 | 09:00:00 AM | 05/22/2020 | 11:00:00 AM | 02:00:00 | 2 | 12.5 | 25
| Joe Butler | 00:00:00 | 00:00:00 | 01:30:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 01:30:00 | 01:30:00 | Finance | SWEng Group 4 | report about cost of Firebase based on the recent usage |  | Jun Ma | jm2285@york.ac.uk |  | Yes | 05/21/2020 | 01:00:00 PM | 05/21/2020 | 03:00:00 PM | 02:00:00 | 2 | 12.5 | 25
| James Clawley | 00:00:00 | 03:00:00 | 00:00:00 | 00:00:00 | 02:00:00 | 02:00:00 | 02:00:00 | 09:00:00 | 09:00:00 | Software | SWEng Group 4 | C26 - Working on messaging things | User story C26 | Nathan Billis | ncab500@york.ac.uk |  | Yes | 05/21/2020 | 12:00:00 PM | 05/21/2020 | 03:00:00 PM | 03:00:00 | 3 | 12.5 | 37.5
Testing - SWEng Group 4 |  | 00:00:00 | 00:45:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:45:00 | 00:45:00 | Finance | SWEng Group 4 | Financial Summary and Future Business plan |  | Louis Newman | lifn501@york.ac.uk |  | Yes | 05/21/2020 | 09:00:00 AM | 05/21/2020 | 01:00:00 PM | 04:00:00 | 4 | 12.5 | 50
| Rebecca Anderson | 00:00:00 | 00:45:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:45:00 | 00:45:00 | Software | SWEng Group 4 | Review of C28, C16, C31, C29 and C24. A few quick bugfixes + identification of larger version issues with API level 21. |  | Joe Butler | jb2200@york.ac.uk |  | Yes | 05/20/2020 | 06:30:00 PM | 05/20/2020 | 08:00:00 PM | 01:30:00 | 1.5 | 12.5 | 18.75
Marketing - SWEng Group 4 |  | 01:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 01:00:00 | 01:00:00 | Finance | SWEng Group 4 | Financial Summary |  | Louis Newman | lifn501@york.ac.uk |  | Yes | 05/20/2020 | 09:00:00 AM | 05/20/2020 | 11:00:00 AM | 02:00:00 | 2 | 12.5 | 25
| Rebecca Anderson | 01:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 01:00:00 | 01:00:00 | Software | SWEng Group 4 | Trying to fix the bug and finish up everything else that needs doing | User story C20 | Rebecca Anderson | rea524@york.ac.uk |  | Yes | 05/20/2020 | 09:00:00 AM | 05/20/2020 | 11:00:00 AM | 02:00:00 | 2 | 12.5 | 25
Administration - SWEng Group 4 |  | 00:30:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:15:00 | 00:45:00 | 00:45:00 | Finance | SWEng Group 4 | Worked on Financial Summary |  | Louis Newman | lifn501@york.ac.uk |  | Yes | 05/19/2020 | 09:00:00 AM | 05/19/2020 | 12:00:00 PM | 03:00:00 | 3 | 12.5 | 37.5
| James Pearson | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:15:00 | 00:15:00 | 00:15:00 | Testing | SWEng Group 4 | writing tests for user story c20. found a bug so currently working on that before carrying now with testing | C20 | Rebecca Anderson | rea524@york.ac.uk |  | Yes | 05/19/2020 | 09:00:00 AM | 05/19/2020 | 09:45:00 AM | 00:45:00 | 0.75 | 12.5 | 9.38
| Rebecca Anderson | 00:30:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:30:00 | 00:30:00 | Software | SWEng Group 4 |  | User story A12 | James Clawley | jc2421@york.ac.uk |  | Yes | 05/19/2020 | 09:00:00 AM | 05/19/2020 | 12:00:00 PM | 03:00:00 | 3 | 12.5 | 37.5
Design - SWEng Group 4 |  | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 02:00:00 | 00:00:00 | 00:00:00 | 02:00:00 | 02:00:00 | Finance | SWEng Group 4 | weekly finances |  | Louis Newman | lifn501@york.ac.uk |  | Yes | 05/18/2020 | 11:45:00 AM | 05/18/2020 | 12:00:00 PM | 00:15:00 | 0.25 | 12.5 | 3.13
| Joe Butler | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 02:00:00 | 00:00:00 | 00:00:00 | 02:00:00 | 02:00:00 | Tender presentation | SWEng Group 4 | Started planning presentation structure |  | Rebecca Anderson | rea524@york.ac.uk |  | Yes | 05/18/2020 | 11:15:00 AM | 05/18/2020 | 12:00:00 PM | 00:45:00 | 0.75 | 12.5 | 9.38
Tender presentation - SWEng Group 4 |  | 00:45:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:45:00 | 00:45:00 | Software | SWEng Group 4 | Finished stories and wrote test report | User story C27 | Louis Newman | lifn501@york.ac.uk |  | Yes | 05/18/2020 | 10:45:00 AM | 05/18/2020 | 11:45:00 AM | 01:00:00 | 1 | 12.5 | 12.5
| Rebecca Anderson | 00:45:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:45:00 | 00:45:00 | Marketing | SWEng Group 4 | working out which statistics to use in the presentation and writing up where to use |  | Rebecca Anderson | rea524@york.ac.uk |  | Yes | 05/18/2020 | 10:15:00 AM | 05/18/2020 | 11:15:00 AM | 01:00:00 | 1 | 12.5 | 12.5
TOTAL |  | 07:45:00 | 06:45:00 | 05:30:00 | 09:00:00 | 16:00:00 | 17:00:00 | 14:15:00 | 76:15:00 | 76:15:00 | Meetings | SWEng Group 4 | Team meeting |  | Louis Newman | lifn501@york.ac.uk |  | Yes | 05/18/2020 | 10:00:00 AM | 05/18/2020 | 10:45:00 AM | 00:45:00 | 0.75 | 12.5 | 9.38
[11 empty] | Meetings | SWEng Group 4 | Meeting |  | Joe Butler | jb2200@york.ac.uk |  | Yes | 05/18/2020 | 10:00:00 AM | 05/18/2020 | 10:45:00 AM | 00:45:00 | 0.75 | 12.5 | 9.38
[9 empty] | Billable total | 76.25 | Meetings | SWEng Group 4 | weekly meeting |  | Jun Ma | jm2285@york.ac.uk |  | Yes | 05/18/2020 | 10:00:00 AM | 05/18/2020 | 10:45:00 AM | 00:45:00 | 0.75 | 12.5 | 9.38
[11 empty] | Meetings | SWEng Group 4 | General Meeting |  | James Pearson | jp1439@york.ac.uk |  | Yes | 05/18/2020 | 10:00:00 AM | 05/18/2020 | 10:30:00 AM | 00:30:00 | 0.5 | 12.5 | 6.25
[11 empty] | Administration | SWEng Group 4 | writing up minutes |  | Rebecca Anderson | rea524@york.ac.uk |  | Yes | 05/18/2020 | 09:45:00 AM | 05/18/2020 | 10:15:00 AM | 00:30:00 | 0.5 | 12.5 | 6.25
[11 empty] | Meetings | SWEng Group 4 | Group meeting |  | Rebecca Anderson | rea524@york.ac.uk |  | Yes | 05/18/2020 | 09:00:00 AM | 05/18/2020 | 09:45:00 AM | 00:45:00 | 0.75 | 12.5 | 9.38
[11 empty] | Meetings | SWEng Group 4 |  |  | James Clawley | jc2421@york.ac.uk |  | Yes | 05/18/2020 | 09:00:00 AM | 05/18/2020 | 09:45:00 AM | 00:45:00 | 0.75 | 12.5 | 9.38

## Week 35 labour
Project | User | 05/25/2020 | 05/26/2020 | 05/27/2020 | 05/28/2020 | 05/29/2020 | 05/30/2020 | 05/31/2020 | Total | Billable total | Project | Client | Description | Task | User | Email | Tags | Billable | Start Date | Start Time | End Date | End Time | Duration (h) | Duration (decimal) | Billable Rate (GBP) | Billable Amount (GBP)
Finance - SWEng Group 4 |  | 00:00:00 | 00:15:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:15:00 | 00:15:00 | Software | SWEng Group 4 | Recipe scrollview fixes and search options fixes |  | Joe Butler | jb2200@york.ac.uk |  | Yes | 05/31/2020 | 10:00:00 PM | 06/01/2020 | 12:00:00 AM | 02:00:00 | 2 | 12.5 | 25
| Louis Newman | 00:00:00 | 00:15:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:15:00 | 00:15:00 | HTML Tour | SWEng Group 4 | Setting up project management tab |  | James Pearson | jp1439@york.ac.uk |  | Yes | 05/31/2020 | 01:03:00 PM | 05/31/2020 | 01:33:00 PM | 00:30:00 | 0.5 | 12.5 | 6.25
Meetings - SWEng Group 4 |  | 04:15:00 | 00:00:00 | 00:00:00 | 03:30:00 | 00:00:00 | 00:00:00 | 02:30:00 | 10:15:00 | 10:15:00 | Sales Presentation | SWEng Group 4 | gif creation, editing slides |  | Joe Butler | jb2200@york.ac.uk |  | Yes | 05/31/2020 | 01:00:25 PM | 05/31/2020 | 04:00:25 PM | 03:00:00 | 3 | 12.5 | 37.5
| James Pearson | 00:45:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:45:00 | 00:45:00 | Meetings | SWEng Group 4 |  |  | James Clawley | jc2421@york.ac.uk |  | Yes | 05/31/2020 | 01:00:00 PM | 05/31/2020 | 02:00:00 PM | 01:00:00 | 1 | 12.5 | 12.5
| Louis Newman | 00:45:00 | 00:00:00 | 00:00:00 | 02:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 02:45:00 | 02:45:00 | Software | SWEng Group 4 | profile fixes |  | Joe Butler | jb2200@york.ac.uk |  | Yes | 05/31/2020 | 11:00:31 AM | 05/31/2020 | 11:15:31 AM | 00:15:00 | 0.25 | 12.5 | 3.13
| Rebecca Anderson | 00:45:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:45:00 | 00:45:00 | Meetings | SWEng Group 4 | meeting |  | Joe Butler | jb2200@york.ac.uk |  | Yes | 05/31/2020 | 10:00:14 AM | 05/31/2020 | 10:45:14 AM | 00:45:00 | 0.75 | 12.5 | 9.38
| Nathan Billis | 00:45:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:45:00 | 00:45:00 | Meetings | SWEng Group 4 | Meeting about presentation |  | Jun Ma | jm2285@york.ac.uk |  | Yes | 05/31/2020 | 10:00:00 AM | 05/31/2020 | 10:45:00 AM | 00:45:00 | 0.75 | 12.5 | 9.38
| Jun Ma | 00:45:00 | 00:00:00 | 00:00:00 | 00:45:00 | 00:00:00 | 00:00:00 | 00:45:00 | 02:15:00 | 02:15:00 | Sales Presentation | SWEng Group 4 | Sales Presentation |  | Louis Newman | lifn501@york.ac.uk |  | Yes | 05/31/2020 | 09:00:00 AM | 05/31/2020 | 11:00:00 AM | 02:00:00 | 2 | 12.5 | 25
| Joe Butler | 00:00:00 | 00:00:00 | 00:00:00 | 00:45:00 | 00:00:00 | 00:00:00 | 00:45:00 | 01:30:00 | 01:30:00 | Sales Presentation | SWEng Group 4 |  |  | Rebecca Anderson | rea524@york.ac.uk |  | Yes | 05/31/2020 | 09:00:00 AM | 05/31/2020 | 12:00:00 PM | 03:00:00 | 3 | 12.5 | 37.5
| James Clawley | 00:30:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 01:00:00 | 01:30:00 | 01:30:00 | Software | SWEng Group 4 | Bug fixes | User story A12 | James Clawley | jc2421@york.ac.uk |  | Yes | 05/31/2020 | 09:00:00 AM | 05/31/2020 | 02:00:00 PM | 05:00:00 | 5 | 12.5 | 62.5
Software - SWEng Group 4 |  | 04:00:00 | 07:45:00 | 07:00:00 | 13:00:00 | 06:00:00 | 10:30:00 | 07:15:00 | 55:30:00 | 55:30:00 | Sales Presentation | SWEng Group 4 | Sales Presentation |  | James Pearson | jp1439@york.ac.uk |  | Yes | 05/31/2020 | 09:00:00 AM | 05/31/2020 | 01:00:00 PM | 04:00:00 | 4 | 12.5 | 50
| James Pearson | 00:00:00 | 00:00:00 | 00:00:00 | 05:00:00 | 03:00:00 | 03:00:00 | 00:00:00 | 11:00:00 | 11:00:00 | Software | SWEng Group 4 | Shopping list design fix + review | User story C5 | Joe Butler | jb2200@york.ac.uk |  | Yes | 05/30/2020 | 04:00:00 PM | 05/30/2020 | 04:30:00 PM | 00:30:00 | 0.5 | 12.5 | 6.25
| Louis Newman | 04:00:00 | 03:45:00 | 01:00:00 | 03:00:00 | 00:00:00 | 01:00:00 | 00:00:00 | 12:45:00 | 12:45:00 | Sales Presentation | SWEng Group 4 | Making gifs for presentation + filling in related slides. (Will be replaced with newer scripted gifs) |  | Joe Butler | jb2200@york.ac.uk |  | Yes | 05/30/2020 | 02:00:00 PM | 05/30/2020 | 02:30:00 PM | 00:30:00 | 0.5 | 12.5 | 6.25
| Rebecca Anderson | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 02:00:00 | 00:00:00 | 02:00:00 | 02:00:00 | Sales Presentation | SWEng Group 4 | Sales presentation |  | James Pearson | jp1439@york.ac.uk |  | Yes | 05/30/2020 | 01:00:00 PM | 05/30/2020 | 02:00:00 PM | 01:00:00 | 1 | 12.5 | 12.5
| Nathan Billis | 00:00:00 | 04:00:00 | 06:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 10:00:00 | 10:00:00 | Sales Presentation | SWEng Group 4 |  |  | Rebecca Anderson | rea524@york.ac.uk |  | Yes | 05/30/2020 | 11:00:00 AM | 05/30/2020 | 01:00:00 PM | 02:00:00 | 2 | 12.5 | 25
| Jun Ma | 00:00:00 | 00:00:00 | 00:00:00 | 01:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 01:00:00 | 01:00:00 | Software | SWEng Group 4 | Fixing bugs and integration |  | Louis Newman | lifn501@york.ac.uk |  | Yes | 05/30/2020 | 09:00:00 AM | 05/30/2020 | 10:00:00 AM | 01:00:00 | 1 | 12.5 | 12.5
| Joe Butler | 00:00:00 | 00:00:00 | 00:00:00 | 04:00:00 | 00:00:00 | 00:30:00 | 02:15:00 | 06:45:00 | 06:45:00 | Software | SWEng Group 4 |  |  | Rebecca Anderson | rea524@york.ac.uk |  | Yes | 05/30/2020 | 09:00:00 AM | 05/30/2020 | 11:00:00 AM | 02:00:00 | 2 | 12.5 | 25
| James Clawley | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 03:00:00 | 04:00:00 | 05:00:00 | 12:00:00 | 12:00:00 | Software | SWEng Group 4 |  | User story A12 | James Clawley | jc2421@york.ac.uk |  | Yes | 05/30/2020 | 09:00:00 AM | 05/30/2020 | 01:00:00 PM | 04:00:00 | 4 | 12.5 | 50
Testing - SWEng Group 4 |  | 00:00:00 | 02:00:00 | 00:00:00 | 01:00:00 | 01:00:00 | 00:00:00 | 00:00:00 | 04:00:00 | 04:00:00 | Software | SWEng Group 4 | Bug fixing |  | James Pearson | jp1439@york.ac.uk |  | Yes | 05/30/2020 | 09:00:00 AM | 05/30/2020 | 12:00:00 PM | 03:00:00 | 3 | 12.5 | 37.5
| Rebecca Anderson | 00:00:00 | 02:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 02:00:00 | 02:00:00 | Testing | SWEng Group 4 | review recipe review | C11 | Nathan Billis | ncab500@york.ac.uk |  | Yes | 05/29/2020 | 05:00:00 PM | 05/29/2020 | 06:00:00 PM | 01:00:00 | 1 | 12.5 | 12.5
| Nathan Billis | 00:00:00 | 00:00:00 | 00:00:00 | 01:00:00 | 01:00:00 | 00:00:00 | 00:00:00 | 02:00:00 | 02:00:00 | Administration | SWEng Group 4 | Sales Presentation |  | James Pearson | jp1439@york.ac.uk |  | Yes | 05/29/2020 | 03:00:00 PM | 05/29/2020 | 04:00:00 PM | 01:00:00 | 1 | 12.5 | 12.5
Marketing - SWEng Group 4 |  | 00:00:00 | 00:00:00 | 02:30:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 02:30:00 | 02:30:00 | Software | SWEng Group 4 | Bug Fixing |  | James Pearson | jp1439@york.ac.uk |  | Yes | 05/29/2020 | 11:00:00 AM | 05/29/2020 | 02:00:00 PM | 03:00:00 | 3 | 12.5 | 37.5
| Rebecca Anderson | 00:00:00 | 00:00:00 | 02:30:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 02:30:00 | 02:30:00 | Sales Presentation | SWEng Group 4 | Sales presentation |  | Louis Newman | lifn501@york.ac.uk |  | Yes | 05/29/2020 | 09:00:00 AM | 05/29/2020 | 12:00:00 PM | 03:00:00 | 3 | 12.5 | 37.5
Administration - SWEng Group 4 |  | 00:00:00 | 00:00:00 | 00:00:00 | 00:30:00 | 01:00:00 | 00:00:00 | 00:00:00 | 01:30:00 | 01:30:00 | Software | SWEng Group 4 | Bug fixes | User story C11 | James Clawley | jc2421@york.ac.uk |  | Yes | 05/29/2020 | 09:00:00 AM | 05/29/2020 | 12:00:00 PM | 03:00:00 | 3 | 12.5 | 37.5
| James Pearson | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 01:00:00 | 00:00:00 | 00:00:00 | 01:00:00 | 01:00:00 | Software | SWEng Group 4 | Recreate C17 based on the new vision | User story C17 | Jun Ma | jm2285@york.ac.uk |  | Yes | 05/28/2020 | 08:00:00 PM | 05/28/2020 | 09:00:00 PM | 01:00:00 | 1 | 12.5 | 12.5
| Rebecca Anderson | 00:00:00 | 00:00:00 | 00:00:00 | 00:30:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:30:00 | 00:30:00 | Software | SWEng Group 4 | Profile bug fixes + finding profile issues + C17 Timeframe stuff |  | Joe Butler | jb2200@york.ac.uk |  | Yes | 05/28/2020 | 05:00:00 PM | 05/28/2020 | 09:00:00 PM | 04:00:00 | 4 | 12.5 | 50
HTML Tour - SWEng Group 4 |  | 00:00:00 | 00:00:00 | 01:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:30:00 | 01:30:00 | 01:30:00 | Testing | SWEng Group 4 | Review of Following | C26 | Nathan Billis | ncab500@york.ac.uk |  | Yes | 05/28/2020 | 04:00:00 PM | 05/28/2020 | 05:00:00 PM | 01:00:00 | 1 | 12.5 | 12.5
| James Pearson | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:30:00 | 00:30:00 | 00:30:00 | Software | SWEng Group 4 | Fixing issues with profile, posts and deleting |  | Louis Newman | lifn501@york.ac.uk |  | Yes | 05/28/2020 | 01:00:00 PM | 05/28/2020 | 04:00:00 PM | 03:00:00 | 3 | 12.5 | 37.5
| Louis Newman | 00:00:00 | 00:00:00 | 01:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 01:00:00 | 01:00:00 | Administration | SWEng Group 4 |  |  | Rebecca Anderson | rea524@york.ac.uk |  | Yes | 05/28/2020 | 11:00:00 AM | 05/28/2020 | 11:30:00 AM | 00:30:00 | 0.5 | 12.5 | 6.25
Sales Presentation - SWEng Group 4 |  | 02:00:00 | 00:00:00 | 05:00:00 | 02:00:00 | 03:00:00 | 03:30:00 | 12:00:00 | 27:30:00 | 27:30:00 | Meetings | SWEng Group 4 | Team meeting and meeting with Stuart for presentation |  | Louis Newman | lifn501@york.ac.uk |  | Yes | 05/28/2020 | 10:00:00 AM | 05/28/2020 | 12:00:00 PM | 02:00:00 | 2 | 12.5 | 25
| James Pearson | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 01:00:00 | 04:00:00 | 05:00:00 | 05:00:00 | Meetings | SWEng Group 4 | Meetings (Sales presentation) |  | Joe Butler | jb2200@york.ac.uk |  | Yes | 05/28/2020 | 10:00:00 AM | 05/28/2020 | 10:45:00 AM | 00:45:00 | 0.75 | 12.5 | 9.38
| Louis Newman | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 03:00:00 | 00:00:00 | 02:00:00 | 05:00:00 | 05:00:00 | Meetings | SWEng Group 4 | Team meeting about presentation |  | Jun Ma | jm2285@york.ac.uk |  | Yes | 05/28/2020 | 10:00:00 AM | 05/28/2020 | 10:45:00 AM | 00:45:00 | 0.75 | 12.5 | 9.38
| Rebecca Anderson | 02:00:00 | 00:00:00 | 05:00:00 | 02:00:00 | 00:00:00 | 02:00:00 | 03:00:00 | 14:00:00 | 14:00:00 | Software | SWEng Group 4 | Bug Fixing |  | James Pearson | jp1439@york.ac.uk |  | Yes | 05/28/2020 | 10:00:00 AM | 05/28/2020 | 03:00:00 PM | 05:00:00 | 5 | 12.5 | 62.5
| Joe Butler | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:30:00 | 03:00:00 | 03:30:00 | 03:30:00 | Sales Presentation | SWEng Group 4 |  |  | Rebecca Anderson | rea524@york.ac.uk |  | Yes | 05/28/2020 | 09:00:00 AM | 05/28/2020 | 11:00:00 AM | 02:00:00 | 2 | 12.5 | 25
TOTAL |  | 10:15:00 | 10:00:00 | 15:30:00 | 20:00:00 | 11:00:00 | 14:00:00 | 22:15:00 | 103:00:00 | 103:00:00 | Software | SWEng Group 4 | Fixing bugs for C27 and presentation | User story C27 | Louis Newman | lifn501@york.ac.uk |  | Yes | 05/27/2020 | 08:00:00 PM | 05/27/2020 | 09:00:00 PM | 01:00:00 | 1 | 12.5 | 12.5
[11 empty] | Marketing | SWEng Group 4 |  |  | Rebecca Anderson | rea524@york.ac.uk |  | Yes | 05/27/2020 | 02:00:00 PM | 05/27/2020 | 04:30:00 PM | 02:30:00 | 2.5 | 12.5 | 31.25
[9 empty] | Total: | 103 | HTML Tour | SWEng Group 4 | Finance page of HTML tour |  | Louis Newman | lifn501@york.ac.uk |  | Yes | 05/27/2020 | 12:00:00 PM | 05/27/2020 | 01:00:00 PM | 01:00:00 | 1 | 12.5 | 12.5
[11 empty] | Software | SWEng Group 4 | Messaging | User story C26 | Nathan Billis | ncab500@york.ac.uk |  | Yes | 05/27/2020 | 10:00:00 AM | 05/27/2020 | 04:00:00 PM | 06:00:00 | 6 | 12.5 | 75
[11 empty] | Sales Presentation | SWEng Group 4 |  |  | Rebecca Anderson | rea524@york.ac.uk |  | Yes | 05/27/2020 | 09:00:00 AM | 05/27/2020 | 02:00:00 PM | 05:00:00 | 5 | 12.5 | 62.5
[11 empty] | Finance | SWEng Group 4 | Weekly finances |  | Louis Newman | lifn501@york.ac.uk |  | Yes | 05/26/2020 | 05:00:00 PM | 05/26/2020 | 05:15:00 PM | 00:15:00 | 0.25 | 12.5 | 3.13
[11 empty] | Software | SWEng Group 4 | Working on messaging | User story C26 | Nathan Billis | ncab500@york.ac.uk |  | Yes | 05/26/2020 | 11:00:00 AM | 05/26/2020 | 03:00:00 PM | 04:00:00 | 4 | 12.5 | 50
[11 empty] | Software | SWEng Group 4 | Rework login, new look and feel with new visual indication, complex passwords, fixed bugs with following, fixed deletion to delete extra data, added unique user names, wrote tests to pass, testing report | User story C27 | Louis Newman | lifn501@york.ac.uk |  | Yes | 05/26/2020 | 09:00:00 AM | 05/26/2020 | 12:45:00 PM | 03:45:00 | 3.75 | 12.5 | 46.88
[11 empty] | Testing | SWEng Group 4 |  | C5 | Rebecca Anderson | rea524@york.ac.uk |  | Yes | 05/26/2020 | 09:00:00 AM | 05/26/2020 | 11:00:00 AM | 02:00:00 | 2 | 12.5 | 25
[11 empty] | Software | SWEng Group 4 | Working on integrating all of following and unfollowing to work with new privacy set up, showing user name and number of recipes, if you are following a private user you can see their private profile, public users show only one profile and private users who are viewed by someone who isn't following them has a restricted profile | User story C27 | Louis Newman | lifn501@york.ac.uk |  | Yes | 05/25/2020 | 11:00:00 AM | 05/25/2020 | 03:00:00 PM | 04:00:00 | 4 | 12.5 | 50
[11 empty] | Sales Presentation | SWEng Group 4 |  |  | Rebecca Anderson | rea524@york.ac.uk |  | Yes | 05/25/2020 | 10:15:00 AM | 05/25/2020 | 12:15:00 PM | 02:00:00 | 2 | 12.5 | 25
[11 empty] | Meetings | SWEng Group 4 | Weekly meeting |  | Louis Newman | lifn501@york.ac.uk |  | Yes | 05/25/2020 | 10:00:00 AM | 05/25/2020 | 10:45:00 AM | 00:45:00 | 0.75 | 12.5 | 9.38
[11 empty] | Meetings | SWEng Group 4 | Weekly Team Meeting |  | Nathan Billis | ncab500@york.ac.uk |  | Yes | 05/25/2020 | 10:00:00 AM | 05/25/2020 | 10:45:00 AM | 00:45:00 | 0.75 | 12.5 | 9.38
[11 empty] | Meetings | SWEng Group 4 | Weekly meeting |  | Jun Ma | jm2285@york.ac.uk |  | Yes | 05/25/2020 | 10:00:00 AM | 05/25/2020 | 10:45:00 AM | 00:45:00 | 0.75 | 12.5 | 9.38
[11 empty] | Meetings | SWEng Group 4 |  |  | Rebecca Anderson | rea524@york.ac.uk |  | Yes | 05/25/2020 | 09:00:00 AM | 05/25/2020 | 09:45:00 AM | 00:45:00 | 0.75 | 12.5 | 9.38
[11 empty] | Meetings | SWEng Group 4 |  |  | James Clawley | jc2421@york.ac.uk |  | Yes | 05/25/2020 | 09:00:00 AM | 05/25/2020 | 09:30:00 AM | 00:30:00 | 0.5 | 12.5 | 6.25
[11 empty] | Meetings | SWEng Group 4 |  |  | James Pearson | jp1439@york.ac.uk |  | Yes | 05/25/2020 | 09:00:00 AM | 05/25/2020 | 09:45:00 AM | 00:45:00 | 0.75 | 12.5 | 9.38

## Week 36 Labour
Project | User | 06/01/2020 | 06/02/2020 | 06/03/2020 | 06/04/2020 | 06/05/2020 | 06/06/2020 | 06/07/2020 | Total | Billable total | Project | Client | Description | Task | User | Email | Tags | Billable | Start Date | Start Time | End Date | End Time | Duration (h) | Duration (decimal) | Billable Rate (GBP) | Billable Amount (GBP)
Meetings - SWEng Group 4 |  | 04:30:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 04:30:00 | 04:30:00 | Meetings | SWEng Group 4 | Meeting |  | Nathan Billis | ncab500@york.ac.uk |  | Yes | 06/01/2020 | 10:54:00 AM | 06/01/2020 | 11:39:00 AM | 00:45:00 | 0.75 | 12.5 | 9.38
| James Pearson | 00:45:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:45:00 | 00:45:00 | Meetings | SWEng Group 4 | Last meeting |  | James Clawley | jc2421@york.ac.uk |  | Yes | 06/01/2020 | 10:30:00 AM | 06/01/2020 | 11:15:00 AM | 00:45:00 | 0.75 | 12.5 | 9.38
| Louis Newman | 00:45:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:45:00 | 00:45:00 | Meetings | SWEng Group 4 | Last meeting |  | Louis Newman | lifn501@york.ac.uk |  | Yes | 06/01/2020 | 10:00:00 AM | 06/01/2020 | 10:45:00 AM | 00:45:00 | 0.75 | 12.5 | 9.38
| Rebecca Anderson | 00:45:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:45:00 | 00:45:00 | Meetings | SWEng Group 4 | Meeting |  | Joe Butler | jb2200@york.ac.uk |  | Yes | 06/01/2020 | 10:00:00 AM | 06/01/2020 | 10:45:00 AM | 00:45:00 | 0.75 | 12.5 | 9.38
| Nathan Billis | 00:45:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:45:00 | 00:45:00 | Meetings | SWEng Group 4 | Team meeting for Sales Presentation |  | James Pearson | jp1439@york.ac.uk |  | Yes | 06/01/2020 | 10:00:00 AM | 06/01/2020 | 10:45:00 AM | 00:45:00 | 0.75 | 12.5 | 9.38
| Joe Butler | 00:45:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:45:00 | 00:45:00 | Meetings | SWEng Group 4 | Team meeting |  | Rebecca Anderson | rea524@york.ac.uk |  | Yes | 06/01/2020 | 09:45:00 AM | 06/01/2020 | 10:30:00 AM | 00:45:00 | 0.75 | 12.5 | 9.38
| James Clawley | 00:45:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:45:00 | 00:45:00
TOTAL |  | 04:30:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 04:30:00 | 04:30:00
[9 empty] | total | 4.5

## TEST PREDICT
Group 4 Financial Buisness Plan | 38 weeks total
Section | Quantity | price details | Agreed price num | Cost per week in GBP | Total known costs | Date Due | Contract end date
Cost of Labour | 7 | 12.5 GBP per employee per hour | 12.5 | dependant on timesheet |  | Weekly, one week in arrears subject to correct time sheet
Premises Rent | 1400 | 23.50 GBP per sq ft per annum | 23.5 | 632.6923 | 24042.3077 | End of weeks 4, 7 and 10 of each term | Summer end week 10
Utilities Rent | 1 | 50 GBP per week | 50 | 50 | 1900 | End of weeks 6 and 10 of each term | Summer end week 10
IT infrastructure | 1 | 100 GBP per week | 100 | 100 | 3800 | End of weeks 6 and 10 of each term. | Summer end week 10
Interest rates | 1 | 16.86% of balance owed in that week | 0.1686 |  |  | Deducted weekly
Cost of hosting | x1 (single application) |  |  |  | total owed in rent, IT and utilities
Cost of deployment to Play Store | x1 (single application) | 25 USD per application | 25 |  | 29742.3077 | [33 empty] | total overhead | -32411.8018
Marketing
-33.3026
Loans: | 0 | [37 empty] | overhead recovery rate | 2.6642
goal seek
borrowed money | 44577.4268 | [38 empty] | -32411.8018
-33.3026
clockify for recording meeting time etc
[39 empty] | num hours | 973.25
Weekly outgoings table: | [38 empty] | rent & modules | -30142.3077
Week number | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 |  | 2.4777
Week dates | Sep. 30, 2019-Oct. 6, 2019 | Oct. 7, 2019-Oct. 13, 2019 | Oct. 14, 2019-Oct. 20, 2019 | Oct. 21, 2019-Oct. 27, 2019 | Oct. 28, 2019-Nov. 3, 2019 | Nov. 4, 2019-Nov. 10, 2019 | Nov. 11, 2019-Nov. 17, 2019 | Nov. 18, 2019-Nov. 24, 2019 | Nov. 25, 2019-Dec. 1, 2019 | Dec. 2, 2019-Dec. 8, 2019 | Dec. 9, 2019-Dec. 15, 2019 | Dec. 16, 2019-Dec. 22, 2019 | Dec. 23, 2019-Dec. 29, 2019 | Dec. 30, 2019-Jan. 5, 2020 | Jan. 6, 2020-Jan. 12, 2020 | Jan. 13, 2020-Jan. 19, 2020 | Jan. 20, 2020-Jan. 26, 2020 | Jan. 27, 2020-Feb. 2, 2020 | Feb. 3, 2020-Feb. 9, 2020 | Feb. 10, 2020-Feb. 16, 2020 | Feb. 17, 2020-Feb. 23, 2020 | Feb. 24, 2020-Mar. 1, 2020 | Mar. 2, 2020-Mar. 8, 2020 | Mar. 9, 2020-Mar. 15, 2020 | Mar. 16, 2020-Mar. 22, 2020 | Mar. 23, 2020-Mar. 29, 2020 | Mar. 30, 2020-Apr. 5, 2020 | Apr. 6, 2020-Apr. 12, 2020 | Apr. 13, 2020-Apr. 19, 2020 | Apr. 20, 2020-Apr. 26, 2020 | Apr. 27, 2020-May 3, 2020 | May 4, 2020-May 10, 2020 | May 11, 2020-May 17, 2020 | May 18, 2020-May 24, 2020 | May 25, 2020-May 31, 2020 | June 1, 2020-June 7, 2020 | June 8, 2020-June 14, 2020 | June 15, 2020-June 21, 2020
Term week | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | Christmas | Christmas | Christmas | Christmas | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | Easter | Easter | Easter | Easter | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10
Project Iteration Stage | Preparation | Preparation | Preparation | Preparation | Preparation | Preparation | Preparation | Preparation | Preparation | Preparation | Preparation | Preparation | Preparation | Preparation | Preparation | Preparation | Preparation | Preparation | Iteration 1, week 1 | Iteration 1, week 2 | Iteration 1, week 3 | Iteration 1, week 4 | Iteration 1, week 5 | Iteration 1, week 6 | Iteration 2, week 1 | Iteration 2, week 2 | Iteration 2, week 3 | Iteration 2, week 4 | Iteration 2, week 5 | Iteration 3, week 1 | Iteration 3, week 2 | Iteration 3, week 3 | Iteration 3, week 4 | Iteration 3, week 5 | Presentation preparation | Presentation & hand in
Num weekly hours | 0 | 0 | 0 | 7 | 8.25 | 8.25 | 8.5 | 7.75 | 20.25 | 14 | 0 | 0 | 0 | 0 | 0 | 45.25 | 67.5 | 35 | 47.75 | 59 | 58.5 | 42.5 | 46 | 29.25 | 47.25 | 34.75 | 28.5 | 43.5 | 43.5 | 37.25 | 47.25 | 29.75 | 31 | 43.5 | 75.25 | 7 | 0 | 0 | num hours | 973.25
IN
Loans (IN) | [19 empty] | 28243.1471 | [8 empty] | 16334.2796
Module sales (IN)
OUT
Premises Rent |  |  |  | -2530.7692 |  |  | -1898.0769 |  |  | -1898.0769 | [7 empty] | -5061.5385 |  |  | -1898.0769 |  |  | -1898.0769 | [7 empty] | -5061.5385 |  |  | -1898.0769 |  |  | -1898.0769 | Rent | -24042.3077
Utilities Rent | [5 empty] | -300 |  |  |  | -200 | [9 empty] | -500 |  |  |  | -200 | [9 empty] | -500 |  |  |  | -200 | Utilities | -1900
IT infrastructure | [5 empty] | -600 |  |  |  | -400 | [9 empty] | -1000 |  |  |  | -400 | [9 empty] | -1000 |  |  |  | -400 | IT infrastructure | -3800
Cost of Labour (12.5 GBP per hour) | 0 | 0 | 0 | -87.5 | -103.125 | -103.125 | -106.25 | -96.875 | -253.125 | -175 | 0 | 0 | 0 | 0 | 0 | -565.625 | -843.75 | -437.5 | -596.875 | -737.5 | -731.25 | -531.25 | -575 | -365.625 | -590.625 | -434.375 | -356.25 | -543.75 | -543.75 | -465.625 | -590.625 | -371.875 | -387.5 | -543.75 | -940.625 | -87.5 | 0 | 0 | Labour | -12165.625
Weekly interest (16.86% APR) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -91.573 | -91.573 | -91.573 | -91.573 | -91.573 | -91.573 | -91.573 | -91.573 | -91.573 | -144.5337 | -144.5337 | -144.5337 | -144.5337 | -144.5337 | -144.5337 | -144.5337 | -144.5337 | -144.5337 | -144.5337 | Interest | -2269.4941
Module purchases (OUT) | [21 empty] | -100 |  | -300 | [14 empty] | Modules | -400
Creditors | [39 empty] | -44577.4268
Total credit for loans | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28243.1471 | 28243.1471 | 28243.1471 | 28243.1471 | 28243.1471 | 28243.1471 | 28243.1471 | 28243.1471 | 28243.1471 | 44577.4268 | 44577.4268 | 44577.4268 | 44577.4268 | 44577.4268 | 44577.4268 | 44577.4268 | 44577.4268 | 44577.4268 | 44577.4268
Total credit for modules | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 300 | 300 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Opening Balance | 0 | 0 | 0 | 0 | -2618.2692 | -2721.3942 | -3724.5192 | -5728.8462 | -5825.7212 | -6078.8462 | -8751.9231 | -8751.9231 | -8751.9231 | -8751.9231 | -8751.9231 | -8751.9231 | -9317.5481 | -10161.2981 | -15660.3365 | -16257.2115 | 9656.8626 | 6935.9627 | 6213.1398 | 5546.5668 | 2291.2919 | 1609.0939 | 1083.1459 | 635.323 | -1.9327e-12 | 15645.9959 | 15035.8372 | 14300.6784 | 8722.7312 | 8190.6975 | 6002.4138 | 3019.1781 | 2787.1444 | 2642.6107
OUT total | 0 | 0 | 0 | -2618.2692 | -103.125 | -1003.125 | -2004.3269 | -96.875 | -253.125 | -2673.0769 | 0 | 0 | 0 | 0 | 0 | -565.625 | -843.75 | -5499.0385 | -596.875 | -2329.073 | -2720.8999 | -722.823 | -666.573 | -3255.2749 | -682.198 | -525.948 | -447.823 | -635.323 | -688.2837 | -610.1587 | -735.1587 | -5577.9472 | -532.0337 | -2188.2837 | -2983.2357 | -232.0337 | -144.5337 | -2642.6107 | out total | -44577.4268
IN total | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28243.1471 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16334.2796 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | cost of interest and modules | -2669.4941
Closing Balance | 0 | 0 | 0 | -2618.2692 | -2721.3942 | -3724.5192 | -5728.8462 | -5825.7212 | -6078.8462 | -8751.9231 | -8751.9231 | -8751.9231 | -8751.9231 | -8751.9231 | -8751.9231 | -9317.5481 | -10161.2981 | -15660.3365 | -16257.2115 | 9656.8626 | 6935.9627 | 6213.1398 | 5546.5668 | 2291.2919 | 1609.0939 | 1083.1459 | 635.323 | -1.9327e-12 | 15645.9959 | 15035.8372 | 14300.6784 | 8722.7312 | 8190.6975 | 6002.4138 | 3019.1781 | 2787.1444 | 2642.6107 | 1.0004e-11 | cost of rent & utilities | -29742.3077
5869.18
[30 empty] | 47.25 | 34.75 | 28.5 | 43.5 | 43.5
0.5
[19 empty] | 52.5 | 46.5 | 44.5 | 44.5 | 44.5 | 44.5 | 277
279
[19 empty] | 47.75 | 55 | 58.5 | 42.5 | 46 | 29.25 | 279
[25 empty] | 40 | 40 | 40 | 40 | 40 | 39.5 | 39.5 | 39.5 | 39.5 | 39.5
[25 empty] | 47.25 | [6 empty] | 197.5
[30 empty] | 37.25 | 47.25 | 29.75 | 31 | 43.5
[27 empty] | 200 | [8 empty] | 9.25
[25 empty] | 47.25 | 34.75 | 28.5 | 43.5 | 43.5 |  |  | 188.75 | 8.75
extra
[27 empty] | 197.5 | 2.5
200

## Future
Item | Cost | Amount |  |  |  | weeks per iteration
Labour Estimates | [5 empty] | 5
User stories | Each numbered and given iteration
Research | 40% per story | 0
Code review | 25% for each user story | 0.25
Design | 5% per member, per user story | 0.25 |  |  |  | I hour every 2 weeks for 3 people
Ad campaign | 7 hours per ad campaign | 0
Finance | 2 hours per week (From historic data) | 10 |  |  |  | paired design meeting - 2
Management | 2 hours per week (From historic data) | 10
User testing | 5 hours per iteration | 0
Final ammendments | 10 hours per iteration | 0
meetings | 1 hour per person per week | 35
Iteration | Hours | Pair programming | Research | Code review | Design | Ad campaign | Finance | Management | User testing | Ammendments | meetings | Total per week |  | Weekly hours to nearest higher 0.25
First | 62.5 | 125 | 125 | 140.625 | 156.25 | 156.25 | 166.25 | 176.25 | 176.25 | 176.25 | 211.25 | 42.25 | 6.0357 | 46.25
Second | 57 | 114 | 114 | 129.625 | 145.25 | 145.25 | 155.25 | 165.25 | 165.25 | 165.25 | 200.25 | 40.05 | 5.7214 | 44
Third | 54 | 108 | 108 | 123.625 | 139.25 | 139.25 | 149.25 | 159.25 | 159.25 | 159.25 | 194.25 | 38.85 | 5.55 | 42.75
|  | per member | team decision
| number of hours for group tender presentation per user | roughly 4 + 1 | 6 | added to week 7
| number of hours for final ammedments per iteration | roughly 2 | 2
| number of hours for user testing per final iteration | total 3 | 2 total
| number of hours for final demnstration and sales presentation | roughly 5 + 1 | 11 per person
| project wide standards | roughly 1 | 2 | added week 6
| week 8 add contracts hours | roughly 6 |  |  |  | 6 hours
| estimate cost of modules (Have to buy 2) |  |  |  |  | £200 per module
budget max costs
final week also needs meetings
any other things people need hours for

## OLD
| Group 4 Financial Buisness Plan | 38 weeks total
| Section | Quantity | price details | Agreed price num | Cost per week in GBP | Total known costs | Date Due | Contract end date
| Cost of Labour | 7 | 12.5 GBP per employee per hour | 12.5 | dependant on timesheet |  | Weekly, one week in arrears subject to correct time sheet
| Premises Rent | 1400 | 23.50 GBP per sq ft per annum | 23.5 | 632.6923 | 24042.3077 | End of weeks 4, 7 and 10 of each term | Summer end week 10
| Utilities Rent | 1 | 50 GBP per week | 50 | 50 | 1900 | End of weeks 6 and 10 of each term | Summer end week 10
| IT infrastructure | 1 | 100 GBP per week | 100 | 100 | 3800 | End of weeks 6 and 10 of each term. | Summer end week 10
| Interest rates | 1 | 16.86% of balance owed in that week | 0.1686 |  |  | Deducted weekly
| Cost of hosting | x1 (single application) |  |  |  | total owed in rent, IT and utilities
| Cost of deployment to Play Store | x1 (single application) | 25 USD per application | 25 |  | 29742.3077
Marketing
| Loans: | 0
clockify for recording meeting time etc
Num weekly hours | 0 | 0 | 0 | 7 | 8.25 | 8.25 | 8.5 | 7.75 | 20.25 | 14 | 0 | 0 | 0 | 0 | 0 | 45.25 | 67.5 | 35 | 52.5 | 46.5 | 44.5 | 44.5 | 44.5 | 44.5 | 40 | 40 | 40 | 40 | 40 | 39.5 | 39.5 | 39.5 | 39.5 | 39.5 | 38.5 | 38.5 | 0 | #NAME?
Wiggle room: | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12 | -11.75 | 32.75 | 77.25 | 121.75 | 166.25 | 206.25 | 246.25 | 286.25 | 326.25 | 366.25 | 405.75 | 445.25 | 484.75 | 524.25 | 563.75 | 602.25 | 640.75 | 640.75 | #NAME?
Weekly outgoings table:
Week number | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38
Week dates | Sep. 30, 2019-Oct. 6, 2019 | Oct. 7, 2019-Oct. 13, 2019 | Oct. 14, 2019-Oct. 20, 2019 | Oct. 21, 2019-Oct. 27, 2019 | Oct. 28, 2019-Nov. 3, 2019 | Nov. 4, 2019-Nov. 10, 2019 | Nov. 11, 2019-Nov. 17, 2019 | Nov. 18, 2019-Nov. 24, 2019 | Nov. 25, 2019-Dec. 1, 2019 | Dec. 2, 2019-Dec. 8, 2019 | Dec. 9, 2019-Dec. 15, 2019 | Dec. 16, 2019-Dec. 22, 2019 | Dec. 23, 2019-Dec. 29, 2019 | Dec. 30, 2019-Jan. 5, 2020 | Jan. 6, 2020-Jan. 12, 2020 | Jan. 13, 2020-Jan. 19, 2020 | Jan. 20, 2020-Jan. 26, 2020 | Jan. 27, 2020-Feb. 2, 2020 | Feb. 3, 2020-Feb. 9, 2020 | Feb. 10, 2020-Feb. 16, 2020 | Feb. 17, 2020-Feb. 23, 2020 | Feb. 24, 2020-Mar. 1, 2020 | Mar. 2, 2020-Mar. 8, 2020 | Mar. 9, 2020-Mar. 15, 2020 | Mar. 16, 2020-Mar. 22, 2020 | Mar. 23, 2020-Mar. 29, 2020 | Mar. 30, 2020-Apr. 5, 2020 | Apr. 6, 2020-Apr. 12, 2020 | Apr. 13, 2020-Apr. 19, 2020 | Apr. 20, 2020-Apr. 26, 2020 | Apr. 27, 2020-May 3, 2020 | May 4, 2020-May 10, 2020 | May 11, 2020-May 17, 2020 | May 18, 2020-May 24, 2020 | May 25, 2020-May 31, 2020 | June 1, 2020-June 7, 2020 | June 8, 2020-June 14, 2020 | June 15, 2020-June 21, 2020
Term week | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | Christmas | Christmas | Christmas | Christmas | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | Easter | Easter | Easter | Easter | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10
Project Iteration Stage | Preparation | Preparation | Preparation | Preparation | Preparation | Preparation | Preparation | Preparation | Preparation | Preparation | Preparation | Preparation | Preparation | Preparation | Preparation | Preparation | Preparation | Preparation | Iteration 1, week 1 | Iteration 1, week 2 | Iteration 1, week 3 | Iteration 1, week 4 | Iteration 1, week 5 | Iteration 1, week 6 | Iteration 2, week 1 | Iteration 2, week 2 | Iteration 2, week 3 | Iteration 2, week 4 | Iteration 2, week 5 | Iteration 3, week 1 | Iteration 3, week 2 | Iteration 3, week 3 | Iteration 3, week 4 | Iteration 3, week 5 | Presentation preparation | Presentation & hand in
Num weekly hours | 0 | 0 | 0 | 7 | 8.25 | 8.25 | 8.5 | 7.75 | 20.25 | 14 | 0 | 0 | 0 | 0 | 0 | 45.25 | 67.5 | 35 | 40.5 | 70.25
IN
Loans in | [19 empty] | 28243.1471 | [8 empty] | 16334.28
Module purchases IN
OUT
Premises Rent |  |  |  | -2530.7692 |  |  | -1898.0769 |  |  | -1898.0769 | [7 empty] | -5061.5385 |  |  | -1898.0769 |  |  | -1898.0769 | [7 empty] | -5061.5385 |  |  | -1898.0769 |  |  | -1898.0769
Utilities Rent | [5 empty] | -300 |  |  |  | -200 | [9 empty] | -500 |  |  |  | -200 | [9 empty] | -500 |  |  |  | -200
IT infrastructure | [5 empty] | -600 |  |  |  | -400 | [9 empty] | -1000 |  |  |  | -400 | [9 empty] | -1000 |  |  |  | -400
Cost of Labour (12.5 GBP per hour) | 0 | 0 | 0 | -87.5 | -103.125 | -103.125 | -106.25 | -96.875 | -253.125 | -175 | 0 | 0 | 0 | 0 | 0 | -565.625 | -843.75 | -437.5 | -506.25 | -878.125 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Weekly interest (16.86%) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Marketing
Deployment to app stores
Module purchases OUT
Firestore Hosting
Creditors
Total debit
Total credit
Opening Balance | 0 | 0 | 0 | 0 | -2618.2692 | -2721.3942 | -3724.5192 | -5728.8462 | -5825.7212 | -6078.8462 | -8751.9231 | -8751.9231 | -8751.9231 | -8751.9231 | -8751.9231 | -8751.9231 | -9317.5481 | -10161.2981 | -15660.3365 | -16166.5865 | 9698.4356 | 7800.3587 | 7800.3587 | 7800.3587 | 5302.2818 | 5302.2818 | 5302.2818 | 5302.2818 | 5302.2818 | 21636.5618 | 21636.5618 | 21636.5618 | 16575.0233 | 16575.0233 | 15075.0233 | 13176.9464 | 13176.9464 | 13176.9464
OUT total | 0 | 0 | 0 | -2618.2692 | -103.125 | -1003.125 | -2004.3269 | -96.875 | -253.125 | -2673.0769 | 0 | 0 | 0 | 0 | 0 | -565.625 | -843.75 | -5499.0385 | -506.25 | -2378.125 | -1898.0769 | 0 | 0 | -2498.0769 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -5061.5385 | 0 | -1500 | -1898.0769 | 0 | 0 | -2498.0769
IN total | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28243.1471 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16334.28 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Closing Balance | 0 | 0 | 0 | -2618.2692 | -2721.3942 | -3724.5192 | -5728.8462 | -5825.7212 | -6078.8462 | -8751.9231 | -8751.9231 | -8751.9231 | -8751.9231 | -8751.9231 | -8751.9231 | -9317.5481 | -10161.2981 | -15660.3365 | -16166.5865 | 9698.4356 | 7800.3587 | 7800.3587 | 7800.3587 | 5302.2818 | 5302.2818 | 5302.2818 | 5302.2818 | 5302.2818 | 21636.5618 | 21636.5618 | 21636.5618 | 16575.0233 | 16575.0233 | 15075.0233 | 13176.9464 | 13176.9464 | 13176.9464 | 10678.8695

## Business Plan going forward (2)
| Each marketting campaign cost: | 2300
Marketting estimates
Following the first ad campaign - hope to generate 500 daily active users.
Following the second ad campaign - hope to have 2000 daily active users.
Following the third ad campaign - hope to have 5000 daily active users.
Following the fourth ad campaign - hope to generate 11,000daily active users.
Following the fifth ad campaign - hope to have 23,000 daily active users.
Following the sixth ad campaign - hope to have 47,000 daily active users.
If we run one ad campaign every 2 months in the first 6 months we can reach our 5000 DAU goal
Evenly splitting added users over each two month period gives the following results
[14 empty] | 1 | 20.429
[14 empty] | 100 | 2042.9
Revised Product Pricing | [13 empty] | 500 | 10214.5
| Estimating that 10% of userbase opt for gold membership | [12 empty] | 1000 | 20429
| Time Frame | Value | Estimated user % | Averaged over 1 year/User | [9 empty] | 2000 | 40858
| Monthly | 1.99 | 50% | 11.94 | [9 empty] | 5000 | 102145
| Quarterly | 4.99 | 20% | 3.992 | [9 empty] | 10000 | 204290
| Yearly | 14.99 | 30% | 4.497 | [9 empty] | 50000 | 1021450
|  |  | Average monthly per gold user | 20.429 | [9 empty] | 100000 | 2042900
| Free users will have access to the full application without the meal planner and with advetisments | [12 empty] | 1000000 | 20429000
Admob income is very difficult to estimate. As we are working with an application that is available in every country in the world and we need to rely on daily active users making impressions and clicks with the advertising. As we are aiming at students in the UK, we shall make a simplification here and specify that our average daily user is more likely to be from a tier 1 country (i.e. US, UK, Canada and Australia). Due to this we will estimate the average cost per click (CPC) to be around £0.27, we will estimate the click through rate (CTR) of our users to be around 1.1%. We will then estimate that our users will see roughly 4 pages of the application on each visit. This will give us an average Cost Per Thousand (CPM), which means the cost per 1000 pageviews, of £2.94. Using these assumptions, we can estimate potential revenue produced with free daily active users from ADMOB:
|  | Daily Users | Daily Income
|  | 1 | 0.0154 | 1 | 5.621
|  | 100 | 1.54 | 100 | 562.1
|  | 500 | 5.87 | 500 | 2142.55
|  | 1000 | 11.75 | 1000 | 4288.75
|  | 2000 | 23.5 | 2000 | 8577.5
|  | 5000 | 58.74 | 5000 | 21440.1
|  | 10000 | 117.48 | 10000 | 42880.2
|  | 50000 | 587.41 | 50000 | 214404.65
|  | 100000 | 1174.83 | 100000 | 428812.95
|  | 1000000 | 11748.27 | 1000000 | 4288118.55
Current loan | 44577.4268
Costs
Agolia (monthly) | 23.72
Google play store (one off) | 20.43
Labour | Monthly
Developers x 2 | 2500 | (25 HORUS)
Chef x 2 | 1920 | (20 HOURS)
Marketing | 1142.64 | (6 HOURS)
Bookkeeper | 150
5712.64
Month | July | August | September | October | November | December | January | February | March | April | May | June | July
Daily Active Users (start of month) | 0 | 250 | 500 | 1250 | 2000 | 3500 | 5000 | 8000 | 11000 | 17000 | 23000 | 35000 | 47000
Credit
Long term loan | 84577.4268 | 84577.4268 | 84577.4268 | 84577.4268 | 84577.4268 | 101577.4268 | 101577.4268 | 101577.4268 | 101577.4268 | 101577.4268 | 101577.4268 | 101577.4268 | 101577.4268
IN
Loans | 40000 |  |  |  |  | 17000
Montly free user Revenue | 0 | 103.95 | 207.9 | 519.75 | 831.6 | 1455.3 | 2079 | 3326.4 | 4573.8 | 7068.6 | 9563.4 | 14553 | 19542.6
Monthly gold user Revenue | 0 | 510.725 | 1021.45 | 2553.625 | 4085.8 | 7150.15 | 10214.5 | 16343.2 | 22471.9 | 34729.3 | 46986.7 | 71501.5 | 96016.3
OUT
Labour
Developers labour | 2500 | 2500 | 2500 | 2500 | 2500 | 2500 | 2500 | 2500 | 2500 | 2500 | 2500 | 2500 | 2500
Chef labour | 1920 | 1920 | 1920 | 1920 | 1920 | 1920 | 1920 | 1920 | 1920 | 1920 | 1920 | 1920 | 1920
Marketing labour | 1142.64 | 1142.64 | 1142.64 | 1142.64 | 1142.64 | 1142.64 | 1142.64 | 1142.64 | 1142.64 | 1142.64 | 1142.64 | 1142.64 | 1142.64
Bookkeeper | 150 | 150 | 150 | 150 | 150 | 150 | 150 | 150 | 150 | 150 | 150 | 150 | 150
Other Overheads
Marketing Campaign | 1150 | 1150 | 1150 | 1150 | 1150 | 1150 | 1150 | 1150 | 1150 | 1150 | 1150 | 1150 | 1150
Adding to Google Play Store | 20.43 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Agolia | 23.72 | 23.72 | 23.72 | 23.72 | 23.72 | 23.72 | 23.72 | 23.72 | 23.72 | 23.72 | 23.72 | 23.72 | 23.72
Firebase hosting | 0.5945 | 0.5945 | 2.4928 | 8.7002 | 15.047 | 27.6504 | 40.5326 | 65.928 | 91.881 | 142.8522 | 194.9468 | 297.0778 | 401.431
Weekly interest (16.86% APR) | 1188.3128 | 1188.3128 | 1188.3128 | 1188.3128 | 1188.3128 | 1427.1628 | 1427.1628 | 1427.1628 | 1427.1628 | 1427.1628 | 1427.1628 | 1427.1628 | 1427.1628
Totals
Opening Balance | 0 | 31904.3027 | 24443.7103 | 17595.8947 | 12585.8966 | 9413.5768 | 26677.8535 | 30617.2981 | 41907.4472 | 60547.7434 | 93889.2683 | 141930.8987 | 219374.798
Total cash in | 40000 | 614.675 | 1229.35 | 3073.375 | 4917.4 | 25605.45 | 12293.5 | 19669.6 | 27045.7 | 41797.9 | 56550.1 | 86054.5 | 115558.9
Total cash out | 8095.6973 | 8075.2673 | 8077.1656 | 8083.373 | 8089.7198 | 8341.1732 | 8354.0554 | 8379.4508 | 8405.4038 | 8456.375 | 8508.4696 | 8610.6006 | 8714.9538
Net cash flow | 31904.3027 | -7460.5923 | -6847.8156 | -5009.998 | -3172.3198 | 17264.2768 | 3939.4446 | 11290.1492 | 18640.2962 | 33341.525 | 48041.6304 | 77443.8994 | 106843.9462
Closing balance | 31904.3027 | 24443.7103 | 17595.8947 | 12585.8966 | 9413.5768 | 26677.8535 | 30617.2981 | 41907.4472 | 60547.7434 | 93889.2683 | 141930.8987 | 219374.798 | 326218.7442
CoDev Profit & Loss (July 2020 - July 2021) |  |  | CoDev Balance sheet July 2021
Sales Revenue | 377410.45 |  | Fixed Assets
Cost of Sales | 0 |  |  | Tangible fixed assets |  | 0
Gross Profit | 377410.45 |  |  | Financial fixed assets |  | 0
Overheads | 90832.8388
Net Profit (PBIT) | 286577.6112 |  | Current Assets
Interest | 17358.867 |  |  | Cash in hand & at bank |  | 326218.7442
Profit Before Taxation | 269218.7442 |  |  | Stock |  | 0
|  |  |  | Debtors |  | 0
|  |  | Current Liabilities |  |  | 0
|  |  | Long term liabilities |  |  | -101577.4268
|  |  | Net Assets |  |  | 224641.3174
| July | August | September | October | November | December | January | February | March | April | May | June | July
Monthly Revenue | 0 | 614.675 | 1229.35 | 3073.375 | 4917.4 | 8605.45 | 12293.5 | 19669.6 | 27045.7 | 41797.9 | 56550.1 | 86054.5 | 115558.9
Monthly Costs | 8095.6973 | 8075.2673 | 8077.1656 | 8083.373 | 8089.7198 | 8341.1732 | 8354.0554 | 8379.4508 | 8405.4038 | 8456.375 | 8508.4696 | 8610.6006 | 8714.9538
CoDev Balance sheet July 2021
Fixed Assets
[15 empty] | Tangible fixed assets | 0
[15 empty] | Financial fixed assets | 0
Current Assets
[15 empty] | Cash in hand & at bank | 37151.3817
[15 empty] | Stock | 0
[15 empty] | Debtors | 0
[14 empty] | Current Liabilities |  | 0
[14 empty] | Long term liabilities |  | -101577.4268
[14 empty] | Net Assets |  | -64426.0451